CARE Australia – Typhoon Ketsana Response

Sample M&E Framework

DRAFT version Tuesday 13 October 2009

This is sample monitoring and evaluation (M&E) framework that can be used in the Typhoon Ketsana response.

A few tips for planning M&E: Establish your M&E systems from the outset of the emergency. Assess the capacity for M&E. If there aren’t enough resources, ask for more resources or downscale your M&E plans to be ‘good enough’. If you don’t think there is capacity to analyse and make sense of the information collected, then don’t collect it. Collect less information, but use it. Ensure that managers review and act on the monitoring data. If you have existing M&E systems, adapt them to be appropriate to an emergency response (activities in short timeframes with quick turnaround). Make sure that information is used in a timely manner. Make sure that the information gathered give a realistic picture of what is happening.

For helpdesk support, please email both Zalynn Peishi zalynn.peishi@careaustralia.org.au and Laura Taylor laura.taylor@careaustralia.org.au or phone + 61 2 6279 0200.

# Why are we monitoring and evaluating

The purpose of this M&E framework is:

- To provide accountability both ‘downward’ and ‘upward’ for the emergency response.

- To gain feedback so as to adjust and adapt our response appropriately

- To contribute to learning so as to improve on our current and future emergency responses

# How we will monitor and evaluate

To monitor and evaluate this response, CARE will:

- Collect baseline information where appropriate and feasible during the assessment phase.

- Collect information on an ongoing basis as per M&E matrix (Attachment 1).

- Conduct an evaluation and endline survey.

- Hold an after action review (AAR)

| Baseline information | For the immediate emergency and recovery phase, CARE will use information from the assessment as baseline information. For later rehabilitation phases, baseline information will be collected as determined in the project design. |
| --- | --- |
| Ongoing data collection | The M&E matrix (Attachment 1) details the information that is to be collected. The main ways that information is to be collected are: Lists of actual recipients disaggregated by sex and other diversity or inclusiveness indicators (such as age, ethnicity, female-headed households) Post-distribution surveys (particularly for food and cash activities) Direct observation Information will be collected and reported on a fortnightly basis. |
| Evaluation | The evaluation will be conducted at the completion of the emergency and recovery phase (after the first three months). This evaluation will be conducted by an independent evaluator as a cluster evaluation of the response in Vietnam, Cambodia and Laos. The evaluation will seek to ask the following (adapted from the CET): Achievement: What has been achieved? How do we know that the project caused the results? Assessing progress against standards: Are the objectives being met? Is the level of assistance per individual or per family meeting standards (e.g. Sphere) or are significant gaps remaining? Is the project doing what the plans said it would do or are there unintended impacts? Monitoring of project management: Is the project well managed? What issues or bottlenecks should be addressed? Gender and inclusiveness: Have women and vulnerable groups been appropriately and meaningfully included in the project? Has we ensured that our interventions have not lowered the status of women? Identifying strengths and weaknesses: Where does the project need improvement and how can it be done? Are the original objectives still appropriate? Checking effectiveness: Was the targeting appropriate? What difference is the project making? Can the impact be improved? Accountability: Are there any unintended issues or negative consequences arising as a result of the response? How should these be addressed? Have we held ourselves accountable to the communities we serve? Cost effectiveness: Are the costs reasonable? Sharing learning: Can we help to prevent similar mistakes or to encourage positive approaches? The evaluation will also be used to assess achievements against standards (such as Sphere standards) that CARE is signatory to. |
| AAR | A regional AAR (including all three countries) or internally-facilitated AARs in each country (using AAR methodology) will be conducted three months after the disaster. The AAR format includes: Timeline of the Emergency Response Lessons Learned Part 1: What we did well Lessons Learned Part 2: What we would do differently next time Action Planning |

# How we will make sense of the information

All the information collected will be analysed and ‘sense’ will be made of it.  Attachment 2 includes an example flow chart of how sense will be made of information.

# How we will use and share the information

|  | How information will be used and shared | Product |
| --- | --- | --- |
| Baseline information | Verified and shared with local authorities, community leaders and other NGOs | Assessment report Information sheet (if required) |
|  | Summarised and shared with CARE members and donors to raise funds | Assessment report and Emergency Response Strategy |
|  | Used as a baseline to assess the effectiveness of our response | Assessment report |
| Ongoing data collection | Shared with emergency response team (ERT) and senior management team (SMT). Decisions are to be made to improve activities. | Sitreps, post-distribution monitoring reports, standing item on weekly ERT and SMT meetings. |
|  | Verified and shared with local authorities and other NGOs | Summary sitrep (monthly) |
|  | Verified and shared with community (women, men, boys and girls). Gather feedback from community on how to improve response, and feedback is to be provided to ERT and SMT. | Information sheet for community information board and community meetings (monthly) |
|  | Shared with CARE members and donors | Sitreps (monthly) and donor reports |
| Evaluation | Shared with emergency response team (ERT) and senior management team (SMT). Decisions are to be made to improve activities. | Evaluation report and presentation by evaluators |
|  | Verified and shared with local authorities and communities (women, men, boys and girls). | Summary evaluation report, translated |
|  | Shared within CARE International, other NGOs and donors | Evaluation report |
| AAR | Shared with emergency response team (ERT) and senior management team (SMT). Decisions are to be made to improve activities. | AAR workshop and AAR report |
|  | Shared within CARE International | AAR report |

# Resources needed

The resources needed are as follows:

- A focal point for M&E who will take leadership of M&E.  This includes ensuring that data is collected, analysed, and real-time information what is happening is made available.  This should be a senior staff member with requisite skills.

- A data entry officer will be assigned to each response to support input of data.

- A translator (part-time) to translate key documents, such as community information sheets.

- Necessary computers to undertake the analysis.

- Training of field staff to develop their skills in collecting data, consultation and gathering feedback.

- Time for field staff for collecting data, consultation and gathering feedback.

Quality and Impact (QI) Team, CARE Australia

October 2009

# Attachment 1: M&E Matrix (example)

- The following are some proposed indicators and tools / methods for collecting them.  You may want to add, subtract or adjust this list.  Please also feel free to add targets for % of households or numbers of beneficiaries reached.

- Data must be disaggregated by sex and other key diversity factors (eg. age, ethnicity, female headed households).

- Some tools are available from the helpdesk.  Email both zalynn.peishi@careaustralia.org.au and laura.taylor@careaustralia.org.au.

| Types of Activity | Indicators | Tool / Method | Timing of data collection | Reporting and use |
| --- | --- | --- | --- | --- |
| Gender |  |  |  |  |
| Women and men participate equitably in activities | Proportion of women and men who participate in community meetings (We realise that this is not a meaningful indicator, but it is easy to do in an emergency context.) | A count of women and men | At meetings | Sitreps (fortnightly) |
| Women’s status does not deteriorate | Reports of gender-based violence or women and girls undertaking hazardous or harmful livelihood strategies such as transactional sex. (Might be difficult to collect this data) | ? Dependent on context, but this may be through networks, formal or informal, or organisations that screen for GBV | Weekly or fortnightly through the response | ? Propose that information goes to SMT and ERT for decisions on how to adjust activities. |
| Food Security and Livelihoods | Higher level indicators: x% of women, men, girls and boys report eating two or more meals each day (This needs to be adjusted according to local context, but this indicator is easier than estimating kCal consumed.) Incidence of malnutrition is at pre-Typhoon levels (optional) x% of households report replacement of household assets | Household surveys Nutrition assessment (see footnote below) | End-of-project (at evaluation and endline survey) | Community information boards or meetings End-of-project reporting Donor reporting |
| Food distribution | Number of women and men who receive the food items. x% of women and men who consume the food items | Disaggregated list of recipients Post-distribution surveys of a sample of beneficiaries | At distribution One month after distribution | Community information boards or meetings Sitreps (fortnightly) Post-distribution monitoring report Donor reports |
| Cash distribution | Number of women and men who receive the cash vouchers / grants x% of households report replacement of household assets | Disaggregated list of recipients Post-distribution surveys of a sample of beneficiaries Direct observation | At distribution One month after distribution | Community information boards or meetings Sitreps (fortnightly) Post-distribution monitoring report Donor reports |
| Cash for work | Number of women and men who receive cash payment for agreed work x% of households report replacement of household assets (Other possible indicators, depending on type of work X area of land is cleared X metres of flood protection is constructed) | Disaggregated list of recipients Post-distribution surveys of sample of beneficiaries Direct observation and other methods depending on type of work | At distribution One month after distribution | Community information boards or meetings Sitreps (fortnightly) Post-distribution monitoring report Donor reports |
| Livelihoods recovery | x% of women and men who report recovery of household income to pre-Typhoon levels x% of households report replacement of productive household assets (Other possible indicators, depending on livelihood type: X% of farming land is replanted X% of micro-enterprises are re-established) | Activity reports (eg., distribution of farming materials, etc) Disaggregated list of recipients Household surveys Direct observation and other methods, depending on livelihood type | Baseline / assessment At distribution Monthly Endline | Community information boards or meetings Sitreps Endline report Donor reports |
| Shelter | Number of women and men who have reconstructed homes Number of women and men who have temporary shelter | Post-distribution surveys of sample of beneficiaries Direct observation | Immediately after distribution and one month after distribution | Community information boards or meetings Sitreps Donor reports |
| Distribution of shelter materials | Number of women and men who receive the shelter materials | Disaggregated list of recipients | At distribution | Community information boards or meetings Sitreps (fortnightly) Donor reports |
| WASH | % of households who meet the Sphere standard to access to water and sanitation in a timely manner | Community meetings or focus group discussion | At completion of activity Evaluation | Community information boards or meetings Donor reports |
| Hygiene promotion | Number of women and men who have been trained in hygiene promotion | Count of women and men participating Activity reports | At time of training | Community information boards or meetings Sitreps (fortnightly) Donor reports |
| Distribution of non-food items | Number of women and men who have received the NFIs | Disaggregated list of recipients | At distribution | Community information boards or meetings Sitreps (fortnightly) Donor reports |
| Water trucking or provision of bottled water | Number of women and men who have received the water, and volume of water distributed. | Activity reports | At distribution | Community information boards or meetings Sitreps (fortnightly) Donor reports |
| Rehabilitation of wells / water points / etc | Number of wells rehabilitated Number of women and men who have improved access to water | Activity reports | During and at the end of rehabilitation At evaluation or endline | Community information boards or meetings Sitreps Donor reports |

# Attachment 2: Flowchart (example)

# Footnotes

The assessment should include a rapid gender analysis.

It might be best to avoid collecting nutrition data unless we have an existing health / nutrition program, and existing projects already track this information.  Alternatively, we could use secondary sources.  Eg., data from a health NGO.

# Text boxes

Collect data

Field staff

Enter data into spreadsheet

Data entry officer

Analyse data

M&E Coordinator or Team Leader

Prepare a communication product

E.g. Information sheet for community, report or presentation for managers / staff

M&E Coordinator or Team Leader

Communicate to stakeholders

E.g. community, local authorities, staff, managers, donors

Team Leader or Field staff

Make timely adjustments or changes to improve emergency response

Team Leader and Senior Managers