CARE Sudan

Emergency Preparedness Plan

Draft, June 2008

Table of Content

Executive Summary	4

1.	Emergency Response Team	5

2.	Information Collection	10

3.	Country Office Capacity Inventory	11

3.1.	Country Office Organization Chart	11

3.2.	Country Office Human Resources	12

3.3.	Country Office Physical Resources	21

3.4.	Country Office Key Staff Contact Information	23

3.5.	RMU, CARE Lead Member, and CARE International Key Contacts	25

3.6.	In Country Coordination Mechanisms and Contacts	26

4.	Risk Analysis	44

5.	Scenario Development	46

5.1.	Scenario 1 – Drought and Conflict in Darfur	46

5.1.1.	Scenario Description	46

5.1.2.	Impact Analysis and Risk Reduction Measures	48

5.1.3.	CARE Prevention and Mitigation Measures	51

5.1.4.	CARE Response Strategy	52

5.1.4.1.	Goal and objectives of CARE’s response	52

5.1.4.2.	Criteria for engagement	52

5.1.4.3.	Partnership Analysis	53

5.1.4.4.	Geographic areas	54

5.1.4.5.	Program interventions	55

5.1.4.6.	Target beneficiaries	55

5.1.4.7.	Partnership Arrangements	55

5.1.4.8.	Key personnel requirements	56

5.1.4.9.	Immediate procurement requirements	57

5.1.4.10.	Logistics requirements	57

5.1.4.11.	Trigger Indicators	58

5.1.4.12.	Entry and Exit/Transition Strategy	58

5.1.5.	Local Considerations	58

5.2.	Scenario 2 – South Kordofan – increased displacement	60

5.2.1.	Scenario Description	60

5.2.2.	Impact Analysis and Risk Reduction Measures	62

5.2.3.	CARE Prevention and Mitigation Measures	64

5.2.4.	CARE Response Strategy	64

5.2.4.1.	Goal and objectives of CARE’s response	64

5.2.4.2.	Geographic areas	65

5.2.4.3.	Program interventions	65

5.2.4.4.	Target beneficiaries	65

5.2.4.5.	Partnership Arrangements	65

5.2.4.6.	Key personnel requirements	66

5.2.4.7.	Immediate procurement requirements	66

5.2.4.8.	Logistics requirements	67

5.2.4.9.	Trigger Indicators	68

5.2.4.10.	Entry and Exit/Transition Strategy	69

5.2.5.	Local Considerations	69

5.3.	Scenario 3 – Drought in North Kordofan	70

5.3.1.	Scenario Description	70

5.3.2.	Impact Analysis and Risk Reduction Measures	72

5.3.3.	CARE Prevention and Mitigation Measures	75

5.3.4.	CARE Response Strategy	75

5.3.4.1.	Goal and objectives of CARE’s response	75

5.3.4.2.	Geographic areas	75

5.3.4.3.	Program interventions	75

5.3.4.4.	Target beneficiaries Vulnerable	75

5.3.4.5.	Partnership Arrangements	76

5.3.4.6.	Key personnel requirements Darfur table)	77

5.3.4.7.	Immediate procurement requirements	77

5.3.4.8.	Logistics requirements	78

5.3.4.9.	`Trigger Indicators	78

5.3.4.10.	Entry and Exit/Transition Strategy (use common entry/exit strategy)	79

5.3.5.	Local Considerations	79

6.	Management Considerations and Gap Analysis	81

6.1.1.1.	Personnel Requirements	81

6.1.1.2.	Assessment and Analysis	82

6.1.1.3.	Design, Monitoring and Evaluation	83

6.1.1.4.	Human Resource Unit	84

6.1.1.5.	Finance	87

6.1.1.6.	Administration	88

6.1.1.7.	Procurement	89

6.1.1.8.	Program Logistics	90

6.1.1.9.	Information Technology and Telecommunications	91

6.1.1.10.	Staff Safety	92

6.1.1.11.	Fundraising	93

6.1.1.12.	Media	94

6.1.1.13.	Information Management	96

7.	Action Plan	97

# Executive Summary

This EPP was developed by CARE Sudan Emergency Response Team (ERT) during the EPP workshop on February 17-21, 2008.  The ERT has identified three highest disaster risk scenarios and developed a range of CARE mitigation and response measures in response to these scenarios.

Scenario 1: Due to the shortfall of the main rain season in year 2007 which contributed to low food production, further this aggravated by lack of free access to productive lands as a result of the continued conflict and war, low acceptance of the UN peace keeping forces by the populace, fighting between fragmented factions and GoS and border tensions and deterioration of humanitarian operations space there will be internal and external displacement, epidemic, lack of basic social services, environmental resource damage, loss of livelihoods, lack of individual and household security, malnutrition, food shortage, etc in South, West and North Darfur now and through the year 2008 and beyond.

Impact:

Total number of affected population	4.5 million people of which 2.5 million are living in IDP camps (Source Darfur Humanitarian Profile No. 29)

Number of affected population in CARE working areas: 1,749,231 people

Children (% affected pop.): 20% of the affected populations are children in Darfur

Women (% of affected pop.):  30% are women population

Scenario 2:  As a result of heavy rainy season in Jun–October in South Kordofan which will cause floods in Southern and Eastern Jeble’s, Kadugli County and Locality and Talodi and Abu Jebha localities? People will be displaced due to the floods in search more secure places and roads will not be accessible, crops will be destroyed causing food insecurity. In addition the escalating tribal conflict due to political affiliations and dispute over land, livestock and water, most likely to affect Abyei, Lagawa, El-Sounoul, Dilling, Meiram, Muglad, Higlig and Karasana will cause displacement of people to the larger town in Kadugli, Dilling, En-nuhud and El Obeid.

Impact:

Total number of affected population 500,000 people

Number of affected population in CARE working areas: 100,000 people

Children (% of affected pop.):  48% (48,000)

Women (% of affected pop.):  32% (32,000)

Scenario 3: Due to reduced and change in the cycle of rainfall in North Kordofan the rain season from Jul-Oct in year 2007 was below the average. As a result the food production was not good in most of the rural areas of the state which will cause significant amount food shortage for rural people and lack of water both for human and livestock. In addition assets of people will deplete, loss of income, malnutrition, increased morbidity and mortality, displacement for other income opportunities/survival, increased food & water prices, cattle prices decreases, as people sell cattle to survive and cattle are not in the healthiest state, school attendance is affected, poor nutritional food as substitute. Also there will be significant effect on livestock pasture and water and health.

Impact:

Total number of affected population: 500,000 people (Rural) and 1,000,000 (indirectly affected in Urban)

Number of affected population in CARE working areas: Not operational

Children (% of affected pop.): 45% (225,000 children)

Women (% of affected pop.):  30% (150,000 women)

# Emergency Response Team

| ERT Function | Title, Name of Staff | Title and Name of Back Up | Preparedness Responsibilities | Response Responsibilities |
| --- | --- | --- | --- | --- |
| Emergency Response Coordinator | Program Coordinator, Salah Mohamed | ACD/P Liz McLaughlin | Finalize and regularly review EPP plan. Coordinate EPP activities. Assure development and implementation of risk reduction activities. Liaise with other stakeholders, including government. | Provide strategic guidance to emergency response activities. Ensure the Mission Office provides adequate support to emergency response operations. Oversee government, media, and other agency relations in capital. Assure adequate funding for emergency response. |
| Field Coordinator | Darfur Team Leader Dereje Adugna Rest of Sudan (RoS) Coordinator Jacqueline George South Kordofan TL, Cecilia Poni | PM, Benson Wakoli PM, Zainab El Nur Senior M&E officer, Yousif Idris | Develop and implement risk reduction activities for development programs in risk areas. Monitor early warning signals. Conduct needs assessment at the early stage of the emergency. | Lead response in the field, including planning and implementation of activities, staff supervision and coordination with ongoing development programs. Oversee government, media, and other agency relations in affected area, with support from Accra. |
| Procurement | Procurement Coordinator, Ibrahim El Nour | Senior Procurement Officer, Manal Shawgi | Pre-position relief items on timely basis ensuring quality and cost as necessary. Keep updated lists of vendors, transporters, and warehouses. Arrange logistics. Provide updated prices for the supplies and materials Establish and maintain a system which will ensure accountability and efficiency appropriate to the emergency context and in line with donor, CARE policies and procedure | Assure procurement support to the Emergency Operation will continue in more efficient and timely manner Ensure procurement team capacity developed and placed on timely manner when required Provide up to date information on the status of procurement to the ERT |
| Information Management | Program Development and Information Officer, Adil Eisa Saad | Project Manager , May Abdel Azim | Set up information flow system for the CO to suit during emergency operation. Ensure knowledge of communication formats and systems is in placed Establish and maintain information and communication channels with Crisis Coordination Group and CARE International Members. | Write situation reports for country office and CI readers. Gather and disseminate information on the emergency situation and CARE’s response back to CARE International Member offices for use in emergency response, fundraising and communications activities. Contribute information and facts for projects design and development. Write press releases, disseminate to local, international media with the consent of CD and ERT. Attend internal briefings, review existing documentation, meet with CARE staff and ERT and undertake field visits as appropriate to remain up to date on the unfolding emergency situation and CARE’s response. Attend external briefings and meetings with CD/ACD-P and ERT Coordinator or delegate to collect information for CARE. |
| Staff Safety | HQ Staff Safety Officer, Abdeen Fadl El Moula Regional Safety Coordinator Darfur, Ake Torringer | Administration Manager, Tayfour Osman Team Leader, Dereje Adugna | Ensure safety/security measures are reviewed and regularly updating to the evolving situation on the ground. Ensure that all staff are familiarized with staff safety and wellness protocols Ensure that in conflict scenarios all the premises and vehicles are meeting the Minimum Operational Safety Standards (MOSS). Focal person trained and put in place for first aid, fire control, etc. | Ensure newly hired staffs are fully aware of the safety/security procedures of CARE. Produce a regular SitRep to provide update for the ERT and CARE Lead Members Regularly visit field offices and meet the staff on the ground to ensure their safety Establish a good working relationship with the local authorities to ensure their support for staff safety |
| IT/Tele-communication | Senior IT Officer, Sami Elkurdi | IT Officer, Salah Bilal Communication Officer, Ashraf Ibrahim | Ensure that all existing communication equipment including base radio, mobile radio, Thuraya, VSAT, Mobile phone are functioning. Identify available and functional IT and communication equipment that can be deployed in emergency situation. Ensure that any gaps in terms of communication and IT equipment are filled. Train staff on the use of IT and communication equipment and ensure all protocols both in English and Arabic language have been understood | Handle emergency IT requirements. Provide regular technical support in ensuring the proper operation and maintenance of IT and Communication equipment |
| Media | Country Director, Navaraja Gaywali | ACD/P, Liz McLaughlin | Set up media policy | Handle media during emergencies |
| Administration/ Logistics | Administration Manager, Tayfour Osman | Senior Administration Officer, Abu Baker Gadien | Prepare Back-Up plan (vehicles, equipment) with identification of the items/costs. | Ensure timely logistic support for emergency operations |
| Finance | Director Finance, Yassir Defalla | Head of finance for budget and reporting, Idris Mansour | Develop financial procedures during emergencies. Define mechanism for accessing cash during emergencies. Ensure knowledge of finance staff of finance procedures during emergencies | Assure timely and efficient finance support to the Emergency Operation |
| Human resources | HRD Manager, Shazali Ibrahim | Deputy HRD Manager, Salah Abdel Raheem | Update JDs of ERT members. Develop Emergency Hiring Procedures. Review staff support needs during emergencies Establish and maintain an emergency staff roaster. | Ensure timely deployment and hiring of the required staff during emergencies. Accountability mechanism put in place for ERT members Ensure a mechanism placed for staff wellness |
| Fundraising | ACD/P, Liz McLaughlin | Team Leaders, and Coordinators, Dereje Adugna and Jacqueline George | Contribute to development and implementation of risk reduction activities. | Assure quality of emergency response activities. Help attract adequate funding for emergency response. |

ERT matrix and Organization Charts for Field Offices

Rest of Sudan other than South Kordofan and Darfur States will be using the same ERT.

CARE Darfur ERT members based in Nyala office are the following:

| ERT member title | Name of the First Person | Name of Back-up Person |
| --- | --- | --- |
| Team Leader | Dereje Adugna | Benson Wakoli |
| Livelihood Coordinator | Benson Wakoli | Issam Bahar |
| WatSan Coordinator | Tom Maisiba | Chaungo Barasa |
| Food Aid | Charles Mule | Henry Khoyouwnga and Prime Nkurunziza |
| NFI | Zuhal Ahmed Abakr | Mohammed Elgoni |
| Human Resource | Ibrahim El-Tayeb | Omar El-Tahir |
| Finance | Binod Maskey | Mariam Mohammed |
| Procurement | Aisha Basher | Shukri |
| Admin | Sara El-Saddig | Kur Mayok |
| Warehouse | El-Saddig Ababkr | Ahmed Isag |
| Staff Safety | Ake Torinnger | Dereje Adugna and El-Thair Babiker |
| IT | Aamir Awad Hamid | Sara Abdurrahman |

Field offices located in Zalingi, Mukjar, Kubum and Kass will be using the ERT in Nyala and the Safety and Security Coordinator of each field office will be the focal point for coordination with the field offices.

CARE South Kordofan ERT members based in Kadugli office are the following:

| ERT member title | Name of the First Person | Name of Back-up Person |
| --- | --- | --- |
| Team Leader/Project Coordinator | Team leader Cecilia Poni | Logistics officer Jayendra |
| Field Coordinator | A/PM Yousef Idris | Program Officer Abbass Mohamed |
| WatSan Coordinator |  |  |
| Food Aid | Food PM, Kenneth D Murye | Logistics officer Jayendra |
| NFI | Logistics officer Jayendra | Bashier Ali Assistant logistics officer - JLC |
| Human Resource | HR Focal point person Yassin Ali | A/PM Programme Officer Yousif Idris |
| Finance | Eissa Gaidoum Finance Officer | Ahmed Shreif Sub grant Manager |
| Admin/Procurement | Procurement Yassin Ali | Bashier Ali Assistant logistics officer - JLC |
| Staff Safety | Team leader Cecilia Poni | Logistic officer Jayandara |
| Communication and information | Radio operator Abu agala Ahmed | Ahmed Shreif Sub grant Manager |

# Information Collection

CARE Sudan has identified the following information, which has been used during the preparation of this EPP:

- CARE USA EPP Guidelines.

- Historical natural and man-made disasters in the country.

- Evaluation reports for CARE responses to disasters

- Country maps in both hard copies and electronic formats.

- Country statistical data: number of population per each administrative unit (province, region, district, city, village, etc).

- Basic CARE program data - population numbers of villages where CARE is currently working, project beneficiary numbers.

- Emergency Preparedness Plans (or similar documents) from the Government and UN.

- CARE Sudan Country Office Organization Chart.

- List of Country Office personnel.

- Country Office physical inventories, including offices, guesthouses, vehicles, and equipment per each office and location.

- Country Office key staffs contact information.

- Contact information for the Government, UN, International and Local organizations active in the country and in the project areas.

# Country Office Capacity Inventory

## Country Office Organization Chart

All Mission organization charts

Key words:

WatSan: Water and Sanitation Project.

WORLP: Women Right and Leadership Promotion.

## Country Office Human Resources

| Function or Sector | Number of Staff | Name of Staff | Positions of Staff |
| --- | --- | --- | --- |
| Program functions |  |  |  |
| National Emergency Coordination | 3 | 1- Salah Mohammed Hassan. 2- Sarah McNiece 3- Ashraf A. Elmaghrabi 4- Dereje Adugna | P. Program Coordinator NFI Logistics Coordinator NFI Logistics Officer Team Leader |
| Food Security Early Warning | 1 | 1- Mohamed Elgoni 2- Dereje Adugna | M & E Officer Team Leader |
| Political Early Warning | 1 | Fleur Just Navaraj Gyawali | Advocacy Advisor Country Director |
| Emergency Assessment | 30 | 1- Ashraf Ibrahim 2- Amani Khalifa 3- Izz Eldin Abass 4- Abdalla Amlas 5-Jayendra 6- Mohamed Elgoni 7-Elsadig Moh. Hashim 8- Sarah McNiece 9- Md. Shah Alam 10- Ashraf A. Elmaghrabi 11- Benson Wakoli 12. Tom Maisiba 13. Chaungo Barasa 14. Charles Mule 15. Prime Nkurinziza 16- Caroline Waithira 17- Margret Kariku 18. Henry Khonyongwa 19. Virendra Chalamati 20. Binod Maskey 21. Dereje Adugna 22. Ibrahim El-Tayeb 23. Omer El-Tahir 24. Aamir Hamid 25. Ahmed Mansour 26. Mohammed Ali 27. Ibrahim Dawod 28. Kamal Yousif 29. Mariam Abubakr 30. Sakena Yousuf 31. Mohammed El-Hassen | Telecommunication Travel arrangement Sr. Driver Driver LO M & E Officer Field Monitor NFI Logistics Coordinator NFI Deputy LC NFI Logistics Officer CDU Project Coordinator WatSan Project Coordinator WatSan Field Coordinator Food Project Coordinator Deputy Food Coordinator Deputy Food Coordinator Nutrition Manager Deputy Food Coordinator Deputy Food Coordinator Finance & Admin Head Team Leader HR Manager HR Officer IT Officer Drilling Manager Camp Supervisor Camp Operation Manager Food Distribution Coordinator Senior Program Officer Food Distribution Coordinator Field Officer |
| Project Design | 6 | 1- Tom Maisiba 2. Indira Sarma 3. Benson Wakoli 4. Dereje Adugna 5.Chaungo Barasa 6- Sarah McNiece | Water project Coordinator Report & Proposal Writer Livelihood Coordinator Team Leader WatSan Field Coordinator NFI Logistics Coordinator |
| Camp Management | 5 | 1. Mohamed Musa 2. Mohammed Ali 3. Mohammed Abdalla 4., El-Tahir Babiker 5. Adam | Field Monitor Camp Supervisor Camp Supervisor Camp Supervisor Camp Supervisor |
| Warehouse & Logistics | 32 | 1-Mohamed Abdelmutalab 2-Elfateh Hamad 3- Mohamed Adam 4- Bashir Ali 5- Zuhal Ahmed Abakar 6- Eltigani Ismail 7- Abu baker Omer 8- Nasser Eldeen Musa Ahmed 9-Faiza Hassan Mohamed 10- Jamal Zakaria Simo 11- Mohasen Ahmed 12- Eltayeb Musa Mohamed 13- Abdelhakam Seifedien 14- Ibrahim Tahir 15- Abdelmoneim Ibrahim 16- Elsadig Mohamed Hashim 17- Eltayeb Mussa Gadam 18- A/ moniem Ahmed 19- Ismail Idris Suliman 20- Salah Ahmed Elshami 21- Sarah McNiece 22- Md. Shah Alam 23- Richard Terer 24- A/Wahid Haj Majid 25- Abdalla Moh. Ibrahim 26- Huzaifa Yagoub 27- Hind Mohamed Bashir (Logistics) 28- Ashraf A. Elmaghrabi 29- Salwa Yousif Breima 30- Adam Teirab Ahmed (Warehousing) 31- A/Razig Mohammed 32. El-Saddig) | Program S. Asst. W/H in charge Store keeper ALO Asst. Logistic Officer Logistic Officer WH Supervisor Storekeeper Asst Logistic Officer Admin. Officer Field Monitor Radio Operator Logistic Officer Assistant Logistic Officer Warehouse keeper NFI Logistics Coordinator NFI Deputy LC CTS Officer Operations Officer Warehouse Keeper Commodity Accountant Admin Officer NFI Logistics Officer Assist. LO Warehouse Keeper Assist. W/HK Storekeeper |
| Distribution of Food & Non-food | 20 | 1- May Abdel Azeem 2- Rosemary Zakaria 3-Khalid Hashim 4- Intisar Mohammed 5- Ali Abdalla 6- Shaza Hassan 7- Jayendra 8- Mohamed Elgoni 9- Mohamed Musa 10-Nema Adam Abdelrahman 11- Abu baker Omer 12- Nasser Eldeen Musa Ahmed 13-Faiza Hassan Mohamed 14- Jamal Zakaria Simo 15- Mohasen Ahmed 16- Eltayeb Musa Mohamed 17- Ismail Idris 18- Salah Ahmed 19- Ashraf A. Elmaghrabi 20 Salwa Yousif Breima | PM M&E Officer M&E Officer Field Monitor Field Monitor Field Monitor LO M & E Officer Field Monitor Field Monitor Assistant Logistic Officer Warehouse keeper NFI Logistics Officer Assist. LO |
| Supplementary & Therapeutic Feeding | 6 | 1- Nada Eltayeb 2- Hanadi Omer 3- Mary Sunday 4- Ibrahim Eltahir 5- Margaret Kariuki 6- Salwa Yousif Breima | Nutritionist Assistant Nutrition Field Monitor PM- Health /Nutrition Nutrition Officer NFI Assist LO |
| Primary Health Care | 5 | 1-Hala Hassab Elrasoul (EC) 2-Dr Amir A/rahman 3-Benson Wakoli 4- Abdalla Mohamed 5- Jayendra | SPO SPO Heath Program Coordinator Health Educator LO |
| Reproductive Health | 4 | 1- Hala Hassab Elrasoul (EC) 2- Margeret 3- Dr. Amir 4- Benson Wakoli | SPO PM- Health /Nutrition SPO Heath |
| Water & Sanitation | 12 | 1- Yasir Hassen 2- Bakhait Moh Musa 3- Mohamed Mehadi Hamid 4- Babiker Moh. Toum 5-Abdalla Adam Hussain 6- Suliman Mekadi Kuku 7- Philip Abouy 8- Mohamed Abdala 9- Eltahir Babiker 10- Haroon Nawiya 11- Tom Maisiba 12- Chaungo Barasa | PM Water Engineer M& E officer Field Officer Field Officer Field Officer Camp Supervisor Camp Supervisor PM Project Coordinator WatSan Field Advisor |
| Shelter | 2 | Charles Mule Dereje Adugna | Food Project Coordinator Team Leader |
| Road & Infrastructure Construction | 3 | Charles Mule Dereje Adugna Henry Khonyongwa | Food Project Coordinator Team Leader Depty Food Coordinator |
| Social Services | 6 | 1- A/Wahid Haj Majid 2- Abdalla Moh. Ibrahim 3- Huzaifa Yagoub 4- Hind Mohamed Bashir 5- Salwa Yousif Breima 6- Farah Ahmed Mudawi | Operations Officer Warehouse Keeper Commodity Accountant Admin Officer Assist. LO Admin assistant |
| Environmental Protection & Management | 2 | 1-Chaungo Barasa 2- Dereje Adugna | WatSan Field Coordinator Team Leader |
| Humanitarian Protection | 1 | 1- Abdalla Moh. Ibrahim | Warehouse Keeper |
| Staff Safety | 3 | 1-Abdin Eltayeb 2- Gasim Badawi 3- Ake Torringer | Staff Safety Officer Radio operator / admin. Assist. Regional Staff Safety Coordinator |
| Advocacy | 2 | 1- Fleur Just 2- Ahlam Abdelmajid | Advocacy & Policy Advisor Community Dev’t Coord |
| Conflict Sensitivity | 3 | 1-Mathew Francis Jumaa 2-Mariam Abubakar 3- Asim Alhadi | Training officer (Kadugli) Senior Program Officer (Darfur) Program Officer (Darfur) |
| Mechanics, Drivers and Radio Operators | 3 | 1-Ebedala Abdurrahman 2- Stephen Aldo 3- Mohammed Osman | Driver Mechanic (Darfur) Workshop Supervisor (Darfur) Radio Operator |
| Program Managers and Field Monitors | 11 | 1-Zeinab ElNour Ali 2- Faisal Ishag 3- Suliman Abdalla Suliman 4- Amira Mohamed 5- Ihsan Hassan 6- Shuaib Musa 7- Mawahib Awadalla 8- Adla Abubakr 9- Limia Dafalla 10-Ensaf Mohamed Abdalla 11- Esadig Mohamed Hashim | PM (EC) PM (FSWD) Training Officer Field Monitor M& E officer Institutional training officer Training Officer Field Monitor Field Monitor Field Monitor Field Monitor |
| Support functions |  |  |  |
| Staff Recruitment: | 9 | 1-Mehad Ahmed 2-Ehsan Ahmed 3-Ibrahim Eltayeb 4- Abdelmoneim Ibrahim 5- Hind Mohammed Bashir 6- Ashraf A. Elmaghrabi 7- Omer Al-Tahir 8-El-Shazali Ibrahim 9- Osailat Osman Ibrahim | Recruitment &Payroll Officer HRO (Darfur) HRM (Darfur) Admin. Officer Admin Officer LO (Darfur) HRO (Darfur) HRM HRO |
| Staff Payroll: | 11 | 1- Hafiz Haroon 2- Heba Suleman 3-Abdelmoneim Ibrahim 4- Hind Mohammed Bashir 5- Adam Teirab Ahmed 6-Mehad Ahmed 7-Ehsan Ahmed 8-Ibrahim Eltayeb 9- Omer Al-Tahir 10-El-Shazali Ibrahim 11- Osailat Osman Ibrahim | Finance Admin. Admin. Officer Admin Officer Warehouse Keeper Recruitment &Payroll Officer HRO (Darfur) HRM (Darfur) HRO (Darfur) HRM HRO |
| Procurement: | 17 | 1-Ibrahim Elnoor 2-Shadia Kamil 3-Manal Shawgi 4- Hafiz Haroon 5-Heba Suleman 6- Shukri Omer 7- Abdelmoneim Ibrahim 8- Elsadig Mohamed Hashim 9- Ikram Mukhtar 10 Salah Ahmed Elshami 11- A/Wahid Haj Majid 12- Huzaifa Yagoub 13- Hind Mohamed Bashir 14- Ashraf A. Elmaghrabi 15- Salwa Yousif Breima 16- Farah Ahmed Mudawi 17- Aisha Basher | Procumbent Coordinator Sr. Procu. Officer Sr. Procu. Officer Finance Admin. Procurement Officer (Darfur) Admin. Officer Field Monitor Admin Assistant Warehouse keeper Operation Officer Commodity Accountant Admin Officer LO ALO Admin Assistant Sen Procurement Officer (Darfur) |
| Inventory: | 21 | 1-Estifanous 2- Hafiz Haroon 3- Heba Suleman 4- Basher 5- Jayendra 5- Hassan Ahmed Ibrahim 7- Elsadig Hassan Abaker 8- Abdelhakam Seifeldien 9- Ibrahim Tahir Yassir 10- Abdelmoniem Ibrahim Elhaj 11- Elsadig Mohamed Hashim 12- Salah Ahmed Elshami 13- A/Wahid Haj Majid 14- Huzaifa Yagoub 15- Ashraf A. Elmaghrabi 16- Salwa Yousif Breima 17- Farah Ahmed Mudawi 18- Adam Teirab Ahmed 19-Binod Maskey 20- Kur Mayok 21- Sara El-Saddig 22-Tayfour Osman 23- Abubakr Gadin | W/house Supervisor Finance (Darfur) Admin. (Darfur) ALO LO Admin / Finance Officer Warehouse Keeper (Darfur) Storekeeper Asst logistic Officer Admin. Officer Warehouse Keeper Warehouse keeper Operation Officer Commodity Accountant LO ALO Admin Assistant W/H K Head of Fin & Admin (Darfur) Operation Manager (Darfur) Admin Officer (Darfur) Admin Manager Senior Admin Officer |
| Transport: | 20 | 1- Hafiz Haroon 2- Heba Suleman 3- Salih Isamail Ibrahim 4- Abdalla Gafar Elhassan 5- Ibrahim Eldoura Abdalla 6- Abdelhakam Seifeldien 7- Ibrahim Tahir Yassir 8- Abdelmoniem Ibrahim Elhaj 9- A/ Moniem Ahmed 10- Ismail Idris 11-Salah Ahmed 12- Ikram Mukhtar 13- A/Wahid Haj Majid 14- Huzaifa Yagoub 15- Ashraf A. Elmaghrabi 16- Salwa Yousif Breima 17- Adam Teirab Ahmed 18- Hind Mohamed Bashir 19- Stephen Aldo 20- Kamal Bakri | Finance (Darfur) Admin. (Darfur) Driver Driver Driver Storekeeper Asst logistic Officer Admin. Officer Logistic officer Assistant Logistic Officer Warehouse keeper Admin Assistant Operation Officer Commodity Accountant LO (Darfur) ALO W/H K Admin Officer Workshop Supervisor (Darfur) Ass. Mechanic (Darfur) |
| Vehicle Management | 10 | 1-Abu Bakar Gadain 2- Hafiz Haroon 3- Mohamed Ahmed Ibrahim 4- Abdelmoniem Ibrahim Elhaj 5- A/ Moniem Ahmed 6- Ikram Mukhtar 7- Hind Mohammed Bashir 8- Ashraf A. Elmaghrabi 9-Stephen Aldo 10- Kamal Nakri | Sr. Admin. Officer Finance (Darfur) Mechanic / driver Admin. Officer Logistic officer Admin Assistant Admin Officer LO Workshop Supervisor (Darfur) Ass. Mechanic (Darfur) |
| Finance: | 21 | 1- Yasir Deafalla 2- Idris Mansour 3- Mona Elamin 4- Issam Bala 5- Rebecca Yawa 6- Sarra Mustafa 7- Tahani Nour Elhadi 8- Hafiz Haroon 9- Heba Suleman 10- Hassan Ahmed Ibrahim 11- Abdelmoniem Ibrahim Elhaj 12-Binod Maskey 13 A/Wahid Haj Majid 14- Huzaifa Yagoub 15- Ashraf A. Elmaghrabi 16- Salwa Yousif Breima 17- Adam Teirab Ahmed 18- Hind Mohamed Bashir 19- Mariam Mohammed 20- Karamldin Ahmed 21-Yacoub Mohammed | Direct of Finance & admin. Budget Head of Fin. & Budget reporting Assistant Finance Manager Assistant Finance Manager Accountant Accountant Finance Secretary Finance (Darfur) Admin. (Darfur) Admin/ Finance Officer Admin. Officer Head of Fin & Admin (Darfur) Operation Officer Commodity Accountant ALO W/H K Admin Officer Senior Accountant (Darfur) Finance Officer (Darfur) Accountant (Darfur) |
| Staff Psycho Social Support | 2 | 1-Ibrahim Eltayeb 2- Sakena Yousif | HRM (Darfur) M&E |
| Commodity Management: | 22 | 1- Ahmed Mohamed Nasr 2- Huzaifa Yagoup 3- Abdalla Mohammed 4- Abdul Wahid Hajmajid 5- Hind Mohamed 6- Basher 7- Jayendra 8- Zuhal Ahmed Abakar 9- Eltigani Ismail 10- Ibrahim Tahir Yassir 11- A/ Moniem Ahmed 12- Ismail Idris 13- Richard Terer 14- Ashraf A. Elmaghrabi 15- Salwa Yousif Breima 16- Adam Teirab Ahmed 17-Kamal Yusuf 18- Adam 19- Virendra Chalamati 20- Prime Nkurunziza 21-Henry Khonyowngo 22-Caroline Withherd | Commodity Accountant Commodity Accountant Store keeper Operation Officer Admin. Assistant ALO LO Logistic Officer WH Supervisor Asst. Logistic Officer Logistic officer Assistant Logistic officer CTS Officer LO ALO W/H K Food M&E (Darfur) Warehouse Keeper (Darfur) Deputy Food Coordinator Deputy Food Coordinator Deputy Food Coordinator Deputy Food Coordinator |
| Communications/Radio | 21 | 1- Bakri Mohammed 2- Mustafa Babikir 3- Abdel Rahman 4- Alhadi Elnagi 5- Izz Eldin Tirab 6- Osman Ali 7- Gasim Badawi 8- Ahmed Ishag Ali 9- Eltayeb Mussa Gadam 10- Ibrahim Tahir Yassir 11- Ashraf A. Elmaghrabi 12- Salwa Yousif Breima 13- Adam Teirab Ahmed 14- A/Razig Mohammed 15- Farah Ahmed Mudawi 16- Mohammed Osman 17- Ahmed Ishag 18- Mohammed El-Hassan 19- Abuakela Ahmed 20- Abulgasim Badawi 21- Salah Ahmed Mudawi | Radio Operator (Khartoum) Radio Operator (Khartoum) Radio Operator Radio Operator (Darfur) Driver Driver Radio operator / admin. Assist. Radio Operator Asst. Logistic Officer LO ALO W/H K Assistant W/H K Admin Assist/ Radio Operator Radio Operator (Darfur) Radio Operator (Darfur) Radio Operator (Darfur) Radio Operator (Kadugli) Radio Operator (Dilling) Radio Operator (Elf Asher) |
| Other (Driver, electrician, messenger, cleaner, Generator operator, etc) | 17 | 1- Faisal M. Tahir 2- Husham Mohamed 3- Taj Elsir Abdalla 4- Osman Hassan 5- Omud Joseph 6- Isam Eldin Elhadi 7- Rahma Eisa 8- Kamal Mustafa 9- Amir Ahmed 10- Mosa Abdel 11- Ibrahim Ramdan 12- Abdin Eltayeb Zaid 13-Salah Abdal Alrahman 14- Magid Eldein Mohamed 15- Tarig A/alla Elkareem 16- Agek Manchol Majok 17- Abdulbaki | Electrician Sr. driver Driver Driver Driver Driver Driver Driver Messenger Messenger Messenger Cleaner Guard Guard Office Assistant Office Assistant Gen/Electric Operator (Darfur) |
| Other: | 12 | 1- Tayfour Osman 1- Shazali Ibrahim 2- Salah ALshareef 3- Osaliat Osman 4- Ibrahim Ahmed 5- Aymen Musmar 6- Elhadi Yahia 7- Abu Bakr Ahmed 8- Ilham Hamid Saydna 9- Adil Eisa 10- Rihab Tag Eldin 11- Kur Mayok 12-Sara Elsadig | Admin. Manager HR administration HR Administration HR Administration HR Administration Canada Fund Coordinator. Internal Editor Liaison Officer Program Coordinator Information Officer Admin. Secretary Operation Manager (Darfur) Admin Officer (Darfur) |
| Other: (IT) | 3 | 1- Sami Salim 2- Salah Khadir 3-Aamir Awad Hamid | Sr. IT Officer IT Officer IT Officer (Darfur) |

## Country Office Physical Resources

| Item # | Asset Description | Number of assets per each office (indicate name of sub-office) | TOTAL |
| --- | --- | --- | --- |
|  |  | KHT | OBD | KAD | FAS | NYA | GEN | MUK | KASS | ZAL | KUB | DLG |  |
| 1 | Offices | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 13 |
| 2 | Guesthouses | 1 | 1 | 1 | 1 | 3 | 1 | 2 | 3 | 1 | 1 | 0 | 15 |
| 3 | Light Vehicles 2WD | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 03 |
| 4 | Light Vehicles 4WD | 19 | 1 | 7 | 1 | 9 | 0 | 8 | 9 | 4 | 1 | 5 | 64 |
| 5 | Trucks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 01 |
| 6 | Motorcycles | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 03 |
| 7 | Computers (Desk tops) | 65 | 2 | 7 | 2 | 34 | 2 | 8 | 10 | 2 | 2 | 5 | 139 |
| 8 | Computers (Lap Tops) | 0 | 1 | 8 | 2 | 15 | 1 | 3 | 0 | 1 | 0 | 1 | 32 |
| 9 | HF Radios – base stations | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 09 |
| 10 | HF Radios - mobile | 1 | 0 | 2 | 0 | 5 | 0 | 4 | 4 | 3 | 0 | 0 | 19 |
| 11 | VHF Radios - Base Stations | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 08 |
| 12 | VHF Radios - Mobile Units | 2 | 0 | 2 | 0 | 6 | 0 | 2 | 4 | 3 | 0 | 0 | 19 |
| 13 | VHF Radios - Handhelds | 3 | 0 | 0 | 6 | 14 | 4 | 4 | 11 | 4 | 1 | 0 | 47 |
| 14 | VHF Repeaters | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 02 |
| 15 | Generators | 5 | 0 | 3 | 1 | 10 | 2 | 3 | 0 | 1 | 1 | 2 | 28 |
| 16 | Satellite phones | 2 | 0 | 2 | 1 | 9 | 1 | 6 | 3 | 1 | 1 | 1 | 27 |
| 17 | Mobile Phones | 30 | 1 | 0 | 1 | 13 | 1 | 0 | 0 | 1 | 0 | 1 | 48 |
| 18 | Printers | 22 | 1 | 6 | 2 | 17 | 1 | 3 | 3 | 3 | 1 | 3 | 62 |
| 19 | Photocopiers | 6 | 1 | 2 | 2 | 7 | 1 | 1 | 2 | 1 | 0 | 1 | 24 |
| 20 | Fax Machines | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 09 |
| 21 | Water Drilling Rigs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 01 |
| 22 | Backhoe | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 00 |
| 23 | Water Tanks | 1 | 0 | 6 | 0 | 42 | 0 | 42 | 9 | 0 | 0 | 0 | 100 |
| 24 | Water Bladders | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 09 |
| 25 | Portable Warehouses (Rub Halls) | 0 | 2 | 2 | 5 | 3 | 5 | 0 | 1 | 0 | 0 | 0 | 18 |
| 26 | Tents for Beneficiaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 00 |
| 27 | Other (Residence) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 05 |
| 28 | Other (Warehouses) | 3 | 3 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 |
| 29 | Other (Digital Camera) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 03 |
| 30 | Other (Portable Safe) | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 04 |
| 31 | Other (Scanner) | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 05 |
| 32 | Other (Projector) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 02 |
| 33 | Other (Air Compressor) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 01 |
| 34 | Other (Rbgan) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 01 |
| 35 | Other (Air Coolers) | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 06 |
| 36 | Other (External fax modem) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 01 |
| 37 | Other (Air Conditions) | 16 | 0 | 0 | 0 | 13 |  | 2 | 0 | 0 | 0 | 0 | 41 |
| 38 | Other (V-Sat) | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 06 |

## Country Office Key Staff Contact Information

| Position | Name | Telephone | Email | Radio Call Sign |
| --- | --- | --- | --- | --- |
| Khartoum |
| ACD/P | Liz Mclaughlin | 0912167340 | liz@sdn.care.org |  |
| D of Finance / Admin / IT /Program support | Yassir Deafalla | 0912348040 | deafalla@sdn.care.org |  |
| ROS/P Liaison Coordinator | Salah Mohammed Hassan |  | salahm@sdn.care.org |  |
| NFI Logistics Coordinator | Sarah McNiece | 0912394031 | sarah@sdn.care.org |  |
| NFI DLC | MD. Shah Alam | 0912160869 | shahalam@sdn.care.org |  |
| NFI CTS Officer | Richard Terer | 0912160852 | terer@sdn.care.org |  |
| Program Advisor | Fleur Just | 0912139026 | fleur@sdn.care.org |  |
| Country PC | Jacqueline George | 0912395219 | Jacqui@sdn.care.org |  |
| Capacity / Advocacy Coordinator | Ahlam Abdulmajid | 0912348060 | ahlam@sdn.care.org |  |
| Admin Manager | Tayfour Osman | 0912395021 | tayfour@sdn.care.org |  |
| HR Manager | Elshazali Ibrahim | 0912348020 | Shazali@sdn.care.org |  |
| S&S Officer | Adbein Fadlelmoula | 0915938977 | abdeen@sdn.care.org |  |
| Communication Officer | Ashraf Ibrahim | 0912167723 | Ashraf@sdn.care.org |  |
| Internal Auditor | Elhadi Yahia | 0121800031 | elhadi@sdn.care.org |  |
| Grants | Idris Mansour | 0122369050 | idris@sdn.care.org |  |
| Procurement Coordinator | Ibrahim Mohammed Elnour | 0912160851 | elnour@sdn.care.org |  |
| P Development Information Officer | Adil Eisa Saad | 0911901514 | adilsaad@sdn.care.org |  |
| Sr Admin liaison Officer | Abubakr Salah | 0912308819 | abubakrsalah@sdn.care.org |  |
| Sr. Admin Officer | Abubakr Jadain | 0912306364 | bakr@sdn.care.org |  |
| Canada Fund Coordinator | Aymen Ali Musmar | 0912309183 | aymen@sdn.care.org |  |
| FSWD PM | Faisal Ishag | 0912348050 | faisal@sdn.care.org |  |
| EC PM | Zainab Elnour | 0912306359 | zainabn@sdn.care.org |  |
| GED Program coordinator | Ilham Hamid | 0912170448 | Ilham.say@sdn.care.org |  |
| El-Fasher Office |
| Logistics Officer | Ashraf A. Elmaghrabi | 0122095580 | ashrafa@sdn.care.org | FXZ 3 |
|  |  | 0923437840 | ashraf_ibt@yahoo.com |  |
|  |  | 0122398917 | maghrabi3rd@gmail.com |  |
| Assistant Logistics Officer | Salwa Yousif Briema | 0915021616 | salwa@sdn.care.org | FXZ 3.1 |
| Radio Operator/Admin Assistant | Farah Ahmed Mudawi | 0122017997 | farah@sdn.care.org | FXZ Base |
| El-Geneina Office |
| Logistics Officer | Mario Nduna | 0912167344 | marion@sdn.care.org | GXZ 3 |
| Assistant Logistics Officer | Ibrahim Tahir | 0912160856 |  | GXZ 3.1. |
| El-Obeid Office |
| Logistics Officer | Abdulmoniem Ahmed | 0122434588 | moniema@sdn.care.org |  |
| Assistant Logistics Officer | Ismail Idris | 0912170185 | ismail@sdn.care.org |  |
| Admin Assistant | Ikram Mukhtar | 0911106212 | ikram@sdn.care.org |  |
| El-Dilling Office |
| PM | Bakhit Mohammed Musa | 0912167057 | bakheit@sdn.care.org |  |
| M&E Officer | Babikir Mohammed toum |  | babikerm@sdn.care.org |  |
| Kadugli Office |
| SK Team Leader | Cecilia Poni | 0918247308 | Cecilia@sdn.care.org |  |
| Assistant PM | Awadalla Kingi |  |  |  |
| Logistics Officer | Jayendra Rathore | 0912167725 | jrathore@sdn.care.org |  |
| Assist LO | Bashir Ali Bashir | 0914034755 |  |  |
| Nyala Office |
| Team Leader | Dereje Adugna | 0912170446 | derejea@sdn.care.org |  |
| CDU PM | Benson Wakoli | 0912160874 | benson@sdn.care.org |  |
| WATSAN PM | Tom Maisiba | 0912167341 | maisib@sdn.care.org |  |
| FOOD PM | Chalamati Virendra | 0912160873 | chalamativs@sdn.care.org |  |
| Finance Manager | Binod Mosky | 0912167342 | binod@sdn.care.org |  |
| Logistics Officer | Zuhal Ahmed | 0912695006 | zuhal@sdn.care.org |  |
| Assist LO | El-Tigani Ismail | 0912983774 | eltigani@sdn.care.org |  |
| Sr. Program Officer CDU | Issam Eldin Bahar | 0912170447 | issambahar@sdn.care.org |  |
| HR Manager Nyala | Ibrahim Eltayeb | 0912170453 | Ibrahim@sdn.care.org |  |
| WATSAN coordinator | Chango Barasa | +254727688457 |  |  |
| Food Project Coordinator | Charles Mule | 0912160853 | mule@sdn.care.org |  |
| VAM Coordinator | Buba Jafali | 0912170434 | buba@sdn.care.org |  |
| Kass Office |
| Site Manager Kass | Caroline Muchai | +254738424032 | caroline@sdn.care.org |  |
| WATSAN Coordinator | Haroun Ali Naweia | 0121658910 | haroonn@sdn.care.org |  |
| Mukjar Office |
| DEAP Deputy Coordinator | Prime Nukurunziza | 0912167056 | prime@sdn.care.org |  |
| Zalengei Office |
| Nutritionist | Margrate Kariuki | 0912170440 | Margaret@sdn.care.org |  |

## RMU, CARE Lead Member, and CARE International Key Contacts

| Office | Position | Name | Telephone | Email |
| --- | --- | --- | --- | --- |
| RMU | Deputy Regional Director | Teresa Kamara | +254727262658 | kamara@ci.or.ke |
| RMU | Regional Director | Steve Wallace | +254723542967 | Wallace@ci.or.ke |
| RMU | Regional Emergency Coordinator | Mohamed Khalid | +2540202807107 | mkhaled@ci.or.ke |
| CARE USA | ECARMU | Amy Wing | +14049799359 | wing@care.org |
| CARE USA | ECARMU | Emanuel Mogabi | +14049799275 | emogabi@care.org |
| CARE USA | Deputy Director / Senior Advisor for Emergency Preparedness | David Gazashvili | +1.404.979.9244 | dgazashvili@care.org |
| CARE Nederland | Senior Program Coordinator | Wouter Schaap | +31070 310 50 54 | schaap@carenederland.org |
| CARE Deutschland | Program Director | Wolfgang Tyderle | +4922897563 | tyderle@care.de |
| CARE UK | Desk Officer | Alan Thomlinson | +442079349364 | thomlinson@careinternational.org |
| CARE Australia | Senior Program Officer | Cecilia Valla | +61262790217 | Cecilia.valla@careaustralia.org.au |
| CARE Canada | Regional Director for Africa | Michael Adams | +16132285643 | michael@care.ca |

## In Country Coordination Mechanisms and Contacts

INGO Contacts Khartoum: Coordination mechanism through bi-weekly meeting.

| Name | Mobile # | Organization | Title | E-mail |
| --- | --- | --- | --- | --- |
| Noriko Takasaki |  | AAR Japan | Country Director | khartoum@aarjapan.gr.jp |
| Patrick Andrey | 0912-344-060 | ACF | Head of Mission | headofmission@su.missions-acf.org |
| Haik Zakrzewski | 0123-954-173 | ACTED | Reporting Officer | haik.zakrzewski@acted.org, khartoum.reporting@acted.org |
| Osman Aelrahim | 0912-309-465 | ADD Sudan | Country Director | osman.aelrahim@add.org.sd |
| Vergiel Ramirez | 0912-357-525 | ADRA | Acting Country Director/Associate | associate.cd@adrasudan.org |
| Mary Mulvihill | 0914-856-964 | AED | Country Director | mmulvihill@aed.org |
| Alemayehu Sissay | 0918-282-979 | AHA | Country Director | ahasudan@yahoo.com |
| Emmanuel Kailie | 0911-335-412 | ARC | Country Director | emmanuelK@arc-sudan.org |
| Imogen Wall |  | BBC World Service Trust | Projects Manager, Africa (London) | imogen.wall@bbc.co.uk |
| Rosalind Yarde | 0911-236-258 | BBC World Service Trust | Project Director | rosalind.yarde@bbcwst.net |
| Mauro Ansaldi |  | CAFOD | Country Representative | mansaldi@cafod.org.uk |
| Ghotai Ghazialam | 0912-161-458 | CHF International | Country Director | gghazialam@chfsudan.org |
| Sarah King | 0913-466-447 | Christian Aid | Emergency Manager | sking@christian-aid.org |
| Robert Hayward | 092-4938-188 | Christian Aid | Country Manager | rhayward@christian-aid.org |
| David Murphy | 0912-168-648 | Concern | Programme Advisor | david.murphy@concern.net |
| Janardhan Rao | 0912-158-945 | Concern | Country Director | sudan.cd@concern.net |
| Michele Mottolese |  | COOPI | Country Director | khartoum@coopi.org, mottolese@coopi.org |
| Francesca Cerri | 0915-936-316 | COSV | Deputy Country Rep | cosvdarfur@yahoo.it |
| Hani El-Mahdi | 0918-210-935 | CRS | Head of Programming | hanielmahdi@hotmail.com |
| Mark Snyder | 0912-172-014 | CRS | Country Director | msnyder@crskhartoum.org |
| Marco Buono | 0912 979513 | Danish Church Aid | Programme Manager | pm.sudan@dca.dk |
| Amgad George | 0915-166-195 | Dorcas Aid | Country Coordinator | office@Sudan.dorcas.org, georgeamgad@yahoo.com |
| Natalie Groom | 0911-344-115 | DRC | Head of Office | drc.khartoum@drc.dk |
| Joel Weiler | 0912-155-459 | EM-DH | Country Director | hom.sudan@emdh.org |
| Louise Norton-Smith |  | EM-DH | Deputy Country Director | emdhsudan@emdh.org |
| Cressida Thompson | 0912-133-108 | FAR | Program Director | programdirector@farsudan.org |
| Mark Simmons | 0912-163-877 | FAR | Country Director | countrydirector@farsudan.org |
| Manfred Oehm |  | Friedrich Ebert Foundation | Resident Representative | moehm@fessudan.org |
| Maria Abbas |  | Friedrich Ebert Foundation | Programme Officer | mabbas@fessudan.org |
| Johan van der Kamp | 0912-393-297 | G A A | Regional Director | johan.vanderkamp@dwhh.org |
| Montasir Abdelrahim |  | G A A | Financial Director | Montasir.Abdelrahim@dwhh.org |
| Conor Elliott | 0912-306-490 | GOAL | Country Director | cd@goalsudan.com |
| Susan Robertson | 0912-163-895 | GOAL | Assistant Country Director | acdprog@goalsudan.com |
| Marie Chiche | 091-614-7965 | Handicap International | Country Representative | hisudan.khartoum@yahoo.com |
| GS Azam | 0912-172-706 | HelpAge International | Country Director | director@helpagesudan.org |
| Leif Zetterlund | 0912-790-123 | IAS | Country Director | leif.zetterlund@ias.nu |
| Susan Muis | +249-922 72 62 79 | ICCO | Prog Coord / Field Rep Krt | susan.muis@icco.nl |
| Rebecca Brazell | 0912-305-536 | IDRB | Country Director | sudan@idrb.org |
| Solomon Kebede | 0912-174-256 | IMC | Country Director | skebede@imcworldwide.org |
| Carol Sherman | 0912-170-348 | IRC | Country Representative Sudan | Carol.Sherman@theIRC.org |
| Nadia Ali El Toum |  | IRC | Deputy Director Programs North&E | ddsudan@theirc.org |
| Mohamed Mao |  | IRW | Country Director | mohamed.mao@islamic-relief.org.sd |
| Ibrahim Mohammed | 0912-161-041 | IRW | Snr Program Manager | Ibrahim.mohammed@islamic-relief.org.sd |
| Mohammed Majzoub Fidiel | 0912-347-010 | ITDG/Practical Action | Country Director | majzoubm@practicalaction.org.sd |
| Sandra Poveda | 0924-958-997 | Jesuit Refugee Service | Project Director | jrsdarfurfasher@gmail.com |
| Stephan Titze | 0912-173-080 | Johanniter | Head of Mission | coordinator.sudan@thejohanniter.org |
| Wilson Lado | 0912 946 235 | Leprosy Mission | Acting Country Director | wilsonl@tlmsudan.org |
| Adrienne Rashford | 0918-042-124 | Malaria Consortium | Country Coordinator | a.rashford@malariaconsortium.org |
| Ute Kirch | 0918-089-076 | Malteser International | Program Coordinator | darfur-coordinator@malteser-africa.org |
| Bruna Sironi | 0913-075-169 | Manitese | Country Representative | bruna@manitese.it |
| Ivor Morgan | 0912-354-148 | Medair | Country Director | cd-khartoum@medair.org |
| Fabrice Bosslini | 0923-488-983 | Médecins du Monde France | Representative | mdmsudancd@gmail.com |
| Gaele Lavone | 0918-212-226 | Medecins du Monde France | Admin Coordinator | mdmsudanga@gmail.com |
| Richard Haselwood | 0912-501-041 | Mercy Corps | Country Director | rhaselwood@sd.mercycorps.org |
| Marie Chicke | 091-564-5564 | Mercy Corps | Operations Manager | banurantha@sd.mercycorps.com |
| Linda Edwards | 0918-275-658 | Merlin | Country Director | cd@merlin-sudan.org |
| Dr Zeidan Abdu Zeidan | 0912-303-446 | Muslim Aid | Country Director | drziedan@muslimaid.org |
| Fethelgaleel Mohamed Ahmed | 0918-238-899 | Muslim Aid - Sudan Field Office | Head of Programme | fethelgaleilm@yahoo.com |
| Thor-Arne Prois | 0912-300-283 | NCA | Country Representative | resrep@ncasudan.org |
| Dave McEntee | 0912-172-467 | NCA / ACT / Caritas | Head of Office | dave@ncasudan.org |
| Philippe Mougin | 0922-100-351 | NCA / ACT / Caritas | Darfur Director | darfurdirector@ncasudan.org |
| Alex Jones | 0915-300-110 | NRC | Country Director | c-director@sudan.nrc.no |
| Williams Scaltriti | 0922-741-180 | OVCI | Resident Representative | Khartoum2@ovci.org |
| Raymond Genesse | (+) 613 237 5236 ext. 232 | Oxfam Canada | Program Manager | raymondg@oxfam.ca |
| Alison Giffen | 0912-161-584 | Oxfam GB | Sudan Advisor | agiffen@oxfam.org.uk |
| Auriol Miller | 0912-170-407 | Oxfam GB | Country Program Manager | amiller@oxfam.org.uk |
| Isaac Williams | 0914-274-260 | PAI | Manager, Khartoum office | williams@partner-aid-international.org |
| Don McPhee | 0912-130-005 | PLAN International | Country Director | don.mcphee@plan-international.org |
| Manuel Manuel | 0923-521-007 | PLAN International | Manager – Northern Program | Manuel.Manuel@plan-international.org |
| Silva Lauffer | 0912-157-062 | RedR | Country Director/IP Director | cdsudan@redr.org |
| Randhir Singh | 0915-166-037 | Relief International | Country Director | randhir@ri.org |
| John Brett | 0 924 67 10 68 | Samaritans Purse | Deputy Country Director | JBrett@samaritan.org |
| John El-Saliby | 0912-172-290 | Samaritans Purse | Country Director | jsalibi@samaritan.org |
| Amin El Fadil | 0912-392-376 | Save the Children Sweden | Country Director | aminelfadil@gmail.com |
| Abebaw Zeleke | 0192-501-294 | Save the Children UK | Country Director | A.Zeleke@scuk-sd.org |
| Hussein Halane | 0912-155-318 | Save the Children US | Country Director | HHalane@savechildren.org.sd |
| Musa Ali | 0912-365-299 | Save the Children US | Programme Advisor | Matroun@savechildren.org.sd |
| Caroline Courtois | 0912-501-487 | Solidarites | HOM Assistant | cdmassistantsol@yahoo.fr |
| Céline BEAUDIC | 0912.172.486 Th: 00.88.216.502.08.686 | Solidarities (based in Nyala) | Country Director | homsolsudan@yahoo.fr |
| Alice M. Ngari | 0913-439-425 / 0121164403 | Stromme Foundation | Programme Coordinator | alice.murugure@stromme.org |
| Hani Khamis |  | Swedish Free Mission | Project Manager | hkapaya@yahoo.com |
| Helena Colliander | 0122-544-348 | Swedish Free Mission | Project Coordinator | heco77@hotmail.com |
| Tony Fish |  | Swiss Demining Foundation | Program Manager | anthony.fish@fsd.ch |
| Ed Walker | 0912-161-946 | Tearfund | Programme Director | dmt-northsudanpd@tearfund.org |
| Tim Holmes | 0912-172-916 | Tearfund | Deputy Programme Director | dmt-northsudan-dpd@tearfund.org |
| Jerome Combes | 0911-387-576 | Terre des Hommes | Head of Mission | jco@tdh.ch |
| Juergen Maresch |  | THW | Head of Mission | thw_sudan@yahoo.de |
| Alexandra Carrie | 0912-276-954 | Triangle GH | Head of Mission | soudan@trianglegh.org |
| Natalie Perkins | 0129-542-972 | UMCOR | Program Development Officer | nperkins@umcor-sudan.org |
| Andreas Jenet | 00254-736-192759 | Vétérinaires Sans Frontières (VSF) | Head of Programmes | jenet@vsfg.org |
| Andrea Naletto | 0915-716-442 | VIS | Country Representative | sudanvis@gmail.com |
| Salvatore Sortino | 0121-541-466 | VIS | Programme Manager | vis.sudan@gmail.com |
| Rochelle Johnston | 0915-984-665 | War Child Canada | Program Manager/Head of Mission | rochellenjohnston@yahoo.com |
| Natacha Vorholter | 0912-161-483 | War Child Holland | Location Manager - Northern Sector | natacha.vorholter@warchild.nl |
| Sandra Renew | 0912-172-751 | War Child Holland | Country Director | sandra.renew@warchild.nl |
| Wendy Barron | 0924-361-055 | Windle Trust International | Country Director | windlesudan@hotmail.com |
| Joanna Trevor | 0912-174-505 | World Vision | Technical Advisor | joanna_trevor@wvi.org |
| Maereg Tafere | 0912-155-667 | World Vision | Country Program Director | maereg_tafere@wvi.org |
| Hans van Oosten | 0918-280-045 | ZOA | Country Director | cd-khartoum@zoa.nl |
| Margaret Simbi | 0918-249-429 | ZOA | Program Advisor | nyakuromba@yahoo.com |
| Douwe Slot | 0122-002-677 | ZOA | Deputy Director | d.slot@zoa.nl |

RCO Contacts: Coordination mechanism through weekly meetings.

| Name | Mobile # | Region | Duty Station | Title | E-mail |
| --- | --- | --- | --- | --- | --- |
| Kiki Gbeho | 912166246 | Khartoum & N. States | H.Q. | Head of RC Office a.i | gbehok@un.org |
| John CLARKE | 0 912501302 |  |  | Deputy Head of RC Office | john.clarke@undp.org |
| Luca Zampetti | 0 9121 59420 |  |  | External Relations Advisor | luca.zampetti@undp.org |
| Hege Magnus | 0 912154657 |  |  | Coordination & Information Officer a.i. | hege.magnus@undp.org |
| Ali Tahsin JUMAH | 0 912140741 |  |  | Operations Manager | ali.tahsin.jumah@undp.org |
| Aymen Elshiekh’ | 0 912171002 |  |  | Field Coordination Officer | ayman.elsheikh@undp.org |
| Nanna Ahlmark | 0 912166294 |  |  | Planning Officer a.i. | nanna.ahlmark@unp.org |
| Amani Atif Mahmoud Ibrahim | 0 912168 216 |  |  | Administrative Associate | amani.atif@undp.org |
| Afrah Habiballah | 0 912176834 |  |  | Finance Assistant | afrah.habiballah@undp.org |
| Mukhtar M. AHMED | 0 912168205 |  |  | Driver | mukhtar.ahmed@undp.org |
| Motaz Abdel Gadir Mohd Salih | 912118136 |  |  | Driver |  |
| Olivier Mukarji | 0 912171791 |  |  | Field Coordination Officer | olivier.mukarji@undp.org |
| Suman Kumar | 0 912500482 |  |  | Khartoum Urban Coordinator | suman.kumar@undp.org |
| Adil SULEIMAN | 0 912130340 |  |  | Driver |  |
| Monique FIENBERG | 0 912166132 | East Sudan | KASSALA | Head of RC Field Office | mounique.fienberg@undp.org |
| Hege Magnus | 0 912154657 |  |  | Field Coordination Officer (currently in Khartoum) | hege.magnus@undp.org |
| Hayder HAMADNALLA | 0 912166403 |  |  | National Field Coordinator | hayder.hamadnalla@undp.org |
| Mario SABIT | 0912197904 |  |  | Driver |  |
| Clifford MBIZI | 0 912166134 |  | PORT SUDAN | Field Coordinator & Head of RC Sub Office | clifford.mbizi@undp.org |
| Baha TAHA | 0 912171004 |  |  | National Field Coordinator | baha.taha@undp.org |
| Abdalla BADAWI |  |  |  | Driver |  |
| Mohamed Ali BABIKER | 0 912176828 | Three Areas Blue Nile / South Kurdufan / Abyei | DAMAZIN | National Field Coordinator | mohamed.babiker@undp.org |
| Soenke Ziesche | 0 9121 78326 |  |  | HAO/UNMIS & Head of RC Field Office a.i. | soenke.ziesche@undp.org |
| Logman Agla |  |  |  | Admin Assistant | logman.agla@undp.org |
| Mahmoud HASSAN | 0 911107670 |  |  | Driver |  |
| Philip DIVE | 0 912501092 |  | KADUGLI/Kauda | Head of RC Field Office | philip.dive@undp.org |
| Abuel-Gasim KHAMIS | 0 923500136 |  |  | M&E Officer | abugassim.khamis@undp.org |
| Mohamed RAHAL | 0 923515683 |  |  | Driver |  |
| Musa IDRIS | 0 912460972 |  |  | Driver |  |
| Mahmoud Musa | 0 923130470 |  |  | Data and reports associate SSA equal to G6 | mahmoud.musa@undp.org |
| Takako Ugaya | 0 923878587 |  |  | HAO/UNMIS | ugaya@un.org |
| Amani HAWIT |  |  |  | National Officer | amani.hawit@undp.org |
| Said TAWIR |  |  |  | Driver |  |
| Jason Matus | 0 912501930 / 0 9140 7970 |  | ABYEI | Head of RC Field Office | jason.matus@undp.org |
| AbdulWahab Idris |  |  |  | Driver |  |
| Sunil Jojo | 0 912323680 | Darfur | El-Fashir | Darfur Head of RC Field Office | sunil.jojo@undp.org |
| Mey El Tayib Ahmed | 0 912326780 |  |  | National Field Coordination Officer | mey.ahmed@undp.org |
| Dawelbite Younis |  |  |  | Driver |  |
| Sunil Jojo | 0 912323680 |  | El-Genina | Darfur Field Coordination Officer (currently in El Fasher) | sunil.jojo@undp.org |
| Hashim Saad | 0 912328793 |  |  | National Field Coordination Officer (currently in El Fasher) | hashim.saad@undp.org |
|  |  |  |  | Driver |  |
| Manzoor Khoso | 0 912130308 |  | Nyala | Darfur Field Coordination Officer | manzoor.khoso@undp.org |
| Mohammed El Nur | 0 91238940 |  |  | National Field Coordination Officer | mohamed.elnor@unpd.org |
| Nooreldin Mohamed | 0 915057673 |  |  | Driver |  |

OCHA Contacts: Coordination mechanism through weekly meetings.

| Name | Mobile # | Sat. phone | Title | E-mail |
| --- | --- | --- | --- | --- |
| North Darfur |
| Randa Hassan | 912160337 |  | Humanitarian Affairs Officer | hassan50@un.org |
| Morlu Duwor | 912167599 |  | Humanitarian Affairs Officer | duwor@un.org |
| Derk Segaar | 912160334 | 88 216 511 91667 | Humanitarian Affairs Officer | segaar@un.org |
| Zeljko Nikolic | 912170947 | 88 2165 1129 443 | Humanitarian Affairs Officer | nikolic@un.org |
| Myriam Mohammedi | 09 1216 7760 | 09 1216 7760 | Humanitarian Affairs Officer | mohammedi1@un.org |
| Elizabeth Pender | 912178709 |  | Humanitarian Affairs Officer | pendere@un.org |
| Karen Moore (UNDP) | 912501337 |  | Field Coordinator | karen.moore@undp.org |
| NKSherstha | 912392562 |  | GIS Officer-IMU | sherstha@un.org |
| Diaz Okeny | 912170789 | 88 216511 93405 | Coordinator for IDP gatherings | okeny@un.org |
| Mohammed Haroun Dimbo | 912895460 |  | National Field Officer | dimbo@un.org |
| Maha Sheriff | 912545928 |  | National Field Officer | Sheriff1@un.org |
| Ahmed El-Mustafa | 911235476 |  | Admin / Finance Assistant | aelmustafa@un.org |
| South Darfur |
| Amal Saeed | 09121 790 12 | N/A | Humanitarian Affairs Officer | saeed5@un.org |
| Clea Kahn | 912160418 | 88 216 5119 3407 | Humanitarian Affairs Officer | kahnc@un.org |
| Yusuf Salah | 912167043 | 8.82165E+12 | Humanitarian Affairs Officer | salahy@un.org |
| Christina Blunt | 912160361 | 8.82165E+12 | Humanitarian Affairs Officer | blunt@un.org |
| Robyn Kerrison | 91 12 167 497 |  | Humanitarian Affairs Officer | kerrison@un.org |
| Omer Saad | 912167408 | N/A | National Field Officer | sado@un.org |
| Ghada Abdelgadir | 912636223 | N/A | National Field Officer (Out) | nsereldeen@un.org |
| Idriss Yousif | 918092937 | N/A | National Field Officer | yousif4@un.org |
| Ahadi Wali | 912160468 | 8.82165E+12 | IMU | ahadia@un.org |
| Jabeldin Abdalla | 923568598 | N/A | Admin / Finance Assistant | abdallaj@un.org |
| Mohamed Omer Ibrahim | 918172145 |  | Finance Officer | ibrahim56@un.org |
| David Lubari | 0912 174809 |  | National Field Officer | lubari@un.org |
| Emad Hussein | 912179077 | 88 216 451193406 | IT assistant | abdallah12@un.org |
| West Darfur |
| Amy Martin | 09 1217 0936 | 882 16511 91671 | Area Coordinator/Team Leader | martin23@un.org |
| Andrew Barash | 09 1216 0066 | 882 16511 25221 | Humanitarian Affairs Officer | barash@un.org |
| Katrine Wold | 09 1215 0726 | 882 16511 93401 | Humanitarian Affairs Officer | wold@un.org |
| Rita Mazzocchi | 09 1216 0417 |  | Humanitarian Affairs Officer | mazzocchi@un.org |
| Mohamed Gimish | 09 1217 4437 |  | National Field Officer | gimish@un.org |
| el Hassan el Hassan | 09 1217 8032 |  | National Field Officer | elhassane@un.org |
| Farah Omer Bello | 09 1217 7959 |  | National Field Officer | omerf@un.org |
| Zalingi WD |
| Paul Thomas | 912170417 | 88 21651125311 | Team Leader | thomasp@un.org |
| Adam Yahia Ibrahim | 915668038 | 8.82165E+12 | National Field Officer | ibrahim32@un.org |
| Mohammed Ali Arbab | 091 11118546 |  | National Field Officer | arbabm@un.org |
| Abdalla Saeed Eltelaib | 122587286 |  | National Field Officer | eltelaib@un.org |
| Inger-Johanne Tjoflaat | 09 121 78708 | 0088 216 511 25 307 | Humanitarian Affairs Officer | tjoflaat@un.org |
| Tom Otunga | 912167460 | 00882 165 112 9444 | UNV | otunga@un.org |
| Khartoum |
| Mike McDonagh | 912306469 |  | Senior Humanitarian Affairs Officer | mcdonaghm@un.org |
| Antoine Gerard | 912160991 |  | Senior Humanitarian Affairs Officer | gerard1@un.org |
| Maximiliano Dachary | 9121 79 087 |  | Humanitarian Affairs Officer | dachary@un.org |
| Raffaele Richetti | 912170425 |  | Humanitarian Affairs Officer | richetti@un.org |
| Annette Hearns | 09121-70946 | 0088216- 511 948 65 | Humanitarian Affairs Officer | hearns@un.org |
| Christian Smets | 0912 167042 |  | Field Liaison/Reporting Officer | smets@un.org |
| Michael Niedermayr | 912170426 |  | Civil Military Coordination Officer | niedermayr@un.org |
| Yasir Omer Taha | 912178033 |  | National Field Officer | tahay@un.org |
| Salah Koko | 091221-4580 | 0088216-5420 3030 | National Field Officer | koko@un.org |

INGO contacts South Darfur

| Name | Mobile # | Organization | Title | E-mail |
| --- | --- | --- | --- | --- |
| Arthur | 091 217 0396 | IRC |  | skype: arthur4883 |
|  | +88 216 511 90 164 |  |  |  |
| Stephan | 091 2173080 | JOHANNITER |  |  |
| Scott | 0918182347 0923406819 | MERCY CORPS |  | skype: scott.dubin |
|  | +88 216 542 09 123 |  |  |  |
| Richard | 091 483 8004 | GLOBAL HOPE NET |  |  |
|  | +88 216 211 28 388 |  |  |  |
| Ywodo | 091 217 5140 | SAFE HARBOUR |  |  |
|  | +88 216 652 81 675 |  |  |  |
| Fernando | 912174436 | OCHA |  |  |
| Christina | 912160361 |  |  |  |
|  | +88 216 511 93 409 |  |  |  |
| Abdallah | 0912 501 183 | UNDSS |  |  |
|  | +88 216 511 91619 |  |  |  |
| Corinna | 091 25 32 399 / | ECHO |  |  |
|  | 092 33 44 788 |  |  |  |
|  | +88 216 211 72 755 |  |  |  |
| Mickey | 09112160816 0923712285 | USAID |  |  |
|  | 2579431054 |  |  |  |
| Rashid | 091 217 5083 | ACF |  | skype: acf.south.darfur |
|  | +88 2165 119 1639 |  |  |  |
| Jon | 912501381 | Solidarités |  | skype: solsudsec |
|  | 8.82165E+12 |  |  |  |
|  | 091 217 0617 | ICRC |  |  |
|  | +88 216 511 90 286 |  |  |  |
| Asbjorn | 091 216 1592 | NCA |  | skype: asbjorn.moe1 |
|  | +88 216 542 05 852 |  |  |  |
| Robert | 091 217 9393 | CHF |  | skype: r_lankenau |
|  | +88 216 520 17 780 |  |  |  |
| Margaret | 091 824 9429 | ZOA |  |  |
|  | +88 216 511 29 712 |  |  |  |
| Aftab | 914823336 | MERLIN |  |  |
|  | 012 278 3350 |  |  |  |
|  | +88 216 511 97 831 |  |  |  |
| Demere | 126204871 |  |  | Skype: dswoldeyes |
| Patrick Mondaca | 915957694 | SP |  |  |
| Andy Shaver- | 912172291 |  |  |  |
| Nadia | 091 827 5478 | AMI |  | skype: nadia.ami |
|  | +88 216 502 08 509 |  |  |  |
| Dayan | 091 217 4255 | IMC |  |  |
|  | +88 216 511 90 446 |  |  |  |
| Yacoub | 091 243 8162 | OXFAM GB |  |  |
|  | +88 216 511 93 753 |  |  |  |
| Amir | 091 215 7061 | RED R |  | skype: amir_71010 |
|  | +88 216 511 94 676 |  |  |  |
| Sabir | 091 237 0482 | MUSLIM AID |  |  |
| Eman | 0912 167 428 | BBC World Serv. Trust |  |  |
|  | +88 216 211 57 072 |  |  |  |
| Banu | 091 216 1532 | MSF-H |  | skype: msf-hom |
|  | +88 216 511 28 629 |  |  |  |
| Dereje Adugna | 091 217 0446 | CARE | Team Leader | skype: dereje4 |
|  | +88 216 511 93 949 |  |  |  |
| Beatriz | 012 908 0695 | SPANISH RED CR. |  |  |
|  | +88 216 311 6776 |  |  |  |
| Augustin | 091 213 3246 | MSF-F |  |  |
| Pinar | 092 478 9868 | TURKISH RED CR. |  |  |
| Patrick/Stanley | 0910711468/0919603898 | AED |  |  |
|  | +88 216 4309 4727 |  |  |  |
| Gillian | 091 216 1948 | TEARFUND |  | skype: gillianmoyes |
|  | +88 216 211 59 376 |  |  |  |
| Sario (Samir) | 0915314361/0923096946 | ARC |  |  |
|  | +88 216 311 61 875 |  |  |  |
| Magdi | 091 250 1620 | DAI |  | skype: magdi_mukhtar |
|  | +88 216 511 97 129 |  |  |  |
| Huda | 091 251 0470 | CORDAID |  |  |
|  | +88 216 512 00 235 |  |  |  |
|  | +88 216 414 68 939 | HUMEDICA |  |  |
| Robert | 091 216 7971 | WORLD VISION |  |  |
|  | +88 216 511 29 381 |  |  |  |
| Marc | 091 809 3327 | MDM |  | skype: vandermullen |
|  | +88 216 502 62 588 |  |  |  |
| Juhani | 091 834 9260 | FINNISH RED CR. |  |  |
|  | +88 216 542 07 105 |  |  |  |

North Darfur International Organizations Contacts

| Name | Mobile #Cell | Organization | Title | E-mail |
| --- | --- | --- | --- | --- |
| David | Dandres | 912167035 | ICRC | Kutum Head of Office | al-fashir.wsd@icrc.org |
| Yvan | Loehle |  |  | Kabkabiya Head of Office | al-fashir.wsd@icrc.org |
| Perrne | Louart | 912167147 |  | Head of Sub Delegation | al-fashir.wsd@icrc.org |
| Aiman | Hassan | 912155472 | IOM | Admin. officer | ahamad@iom.int |
| Elaine | Jepsen | 918677369 |  | Protection Officer | ejepsen@iom.int |
| Sergio | Rodrigues | 915306030 |  | project coordinator | srodrigues@iom.int |
| Mahmoud | Adam | 912564635 |  | VMU Senior | vmuteam-nd@iom.int |
| International NGOs |
| Jorge | Jimeno | 0912163568 | ACF | Program Coordinator North Darfur | progco-northdarfur@su.missions-acf.org |
| Dorothy | Dickson | 0915345692 |  | Nutrition officer | nut-elfasher@su.missions-acf.org |
| Loretto | Palmaera | 0912175084 |  | Food Security Coordinator | foodsecco-darfur@su.missions-acf.org |
| Christopher | Monnon | 0914567941 |  | Log - Admin Shangil Tobay | shangil@su.missions-acf.org |
| Abdulkreem | Adam | 915487061 | AHA | Logistic Officer | ahadarfur@yahoo.com |
| Belay | Yimer | 911357221 |  | Project Coordinator | ahasudan@yahoo.com |
| Mesfin | Zelake | 914623370 |  | Programme officer | ahadarfur@yahoo.com |
| Martin Tom | Gurtner | 915936355 or 0122875832 | ASLAN | assistant Director | maritom@rapidmsg.net |
| Manfired | Schumacher | 915555918 |  | Director | msschumi@gmx.de |
| Ashraf | A. El Meghrabi | 912160854 | CARE | Logistic Officer | ashrafa@sdn.care.org |
| Salwa | Yousif Breima | 915021616 |  | Assistant Logistics Officer | salwa@sdn.care.org |
| El Zein | A. Saeed | 912172146 | CHF | Head of office | elzeinabbas@chfsudan.org |
| Edward | Farrell | 912161423 |  | Senior program coordinator | efarrell@chfsudan.org |
| Mohamed | Majid | 121815960 |  | Programme coordinator | melmajid@chfsudan.org |
| Haroon | Haroon | 915316608 |  | security officer |  |
| Amira | Teeman | 911108606 |  | Livelihoods Coordinator | ateeman@chfsudan.org |
| Michele | Mottolese | 918248447 | COOPI | Country Director | mottolese@coopi.org |
| Daniela | D'Urso | 911267849 |  | Program Assistant | durso@coopi.org |
| Roberto | Goglio | 918248591 |  | Project Manager (FSL) | goglio@coopi.org |
| Hashim | Mohamed | 122248920 / 918172086 | SpRc | Assistant Programme Officer | hashimwadi@hotmail.com |
| Abdul | Bagi Seifeldin | 918276125 | DAI | Programme Development Officer | abagiseif@yahoo.com |
| Noemi | Rios | 919602048 |  | Senior Programme Development Officer | Noemi_Rios@dai.com |
| Dario | Bertetto | 912172763 | EMDH | Programme Coordinator + (09248232697) | emdhdarfur@emdh.org |
| Hadrien | Segard | 924330637 |  | Administrator - Logistician | admin.darfur@emdh.org |
| Ute | Alketib | 912145934 | GAA | Head of Finance and Administration ND | gaasudan.prog2@dwhh.org |
| Abdul Rahman | Ismail | 912561500 |  | Head of Sub-Office Kutum | gaand6@skyfile.com |
| Victor | Makuoth | 912161648 |  | Deputy Head of Projects ND | gaasudan.prog2@dwhh.org |
| Mike | Bratzke | 912172491 |  | Head of Projects ND | gaasudan.prog4@dwhh.org |
| Deirdre | Connolly | 912163531 | GOAL | Operation Manager | elfasherops@goalsudan.com |
| Gerry | Carty | 912178109 |  | Area Coordinator | acdarfur@goalsudan.com |
| Milena | Ribotto | 914598136 |  | Health Manager | kutumhealth@goalsudan.com |
| Elizabeth | Whittaker | 912178155 |  | Assistant Area Coordinator | astacdarfur@goalsudan.com |
| Abdulrasaull | Abdalla | 914936159 | GRC | Health coordinator (OIC) | Abdulrasoull61@yahoo.com |
| Michelle | Kelsey | 09121 74336 | IRC | Programme Coordinator | michelle.kelsey@theirc.org |
| Michael | Johnston | 9121 70366 |  | Human Resource Manager | michael.johnston@theirc.org |
| Arthur | Amolo | 912170396 |  | Field Coordinator – Kutum | arthura@theirc.org |
| Rebecca | Chandler | 912155958 |  | Child Protection Coordinator | rebecca.chandler@theirc.org |
| Sandro | Paveda | 924938997 | JRS | Project Director | jrsdarfurfasher@gmail.com |
| Dominic | Kithendu | 924378573 |  | Education Coordinator | kithendu@yahoo.com |
| El Fadil | El Kajam | 912162296 | KPHF | Assistant Program Officer | Akajam50@hotmail.com |
| Mohamed | Hassan | 915025899 |  | Programme Coordinator | Fungi_44@hotmail.com |
| Nagi | Abdalla | 912849813 | MALTESER | Senior Logistician | darfur-log@malteser-africa.org |
| Ute | Kirch | 918089076 |  | Coordinator | darfur-coordinator@malteser-africa.org |
| Vanessa | Werner | 915186233 |  | Programme Administrator | darfur-admin@malteser-africa.org |
| Tareck | Daher | 912161308 | MSF-B | Head of Mission | Msfb-khartoum-hom@brussels.msf.org |
| Victor | Ackel | 912712247 |  | Field Coordinator | msfb-el.fasher-cord@brussels.msf.org |
| Mónica | Camacho | 912179089 | MSF-E | Head of Darfur mission | msfe-khartoum-cg@barcelona.msf.org |
| Timothy | Orie | 912172301 |  | Logistics Coordinator | msfe-khartoum-conf@barcelona.msf.org |
| Sammy | Chagali | 912155983 | OXFAM | Area Programme Manager, Kebkabiya | schagali@oxfam.org.uk |
| Francisco | Yermo | 912334974 |  | Program Coordinator North Darfur | fyermo@oxfam.org.uk |
| Esther | Mayieka | 912163494 |  | Area Programme Manager- El Fasher | emayieka@oxfam.org.uk |
| Azeem | Imam | 918026493 | PA | Project Manger | azimi@itdg-sudan.org |
| M Siddig | Suliman | 912492291 |  | Programme Coordinator | Siddigm@itdg-sudan.org |
| Rob | Graves | 123004123 | PAI | country director | graves@partner-aid-international.org |
| Russell | Atonson | 912817480 |  | Medical Coordinator | rdadoc@gmail.com |
| Syzann | Harlan | 9129080658 |  | health promotion | bintilnil@gmail.com |
| Mark | Harlan | 9129080683 |  | Ed. Coordinator | harlanhouse@gmail.com |
| Kamal Mohamed | Abdalla Awouda | 122895008 | PS | Darfur Project Coordinator |  |
| Ali | Ahamed ibrahim | 912540493 |  | Program manager - North Darfur | ali.ahmed@plan-international.org |
| Fabian | Chimakati | 912166145 | RedR | team leader | fabian.chimakati@redr.org |
| Elamin | Mohammedin | 915756468 |  | area coordinator | Fasher@RedR.org |
| Wali | Abdelsalam | 912288197 | RI | National Country Director | wali@ri.org |
| George | Mikeladze | 911270408 |  | Regional Finance | george@ri.org |
| Elizabeth | Ross |  |  | Program Manager HQ. |  |
| Randhir | Singh | 915166037 |  | Country Director | randhir@ri.org |
| Abdel Rahaman | Abdalla Yahya |  | SC-S | Field coordinator - Kutum |  |
| Amin | El Fadil |  |  | Country Director | amin.elfadil@gmail.com |
| Babiker | Mohammed Hamid |  |  | Field Coordinator - Tawila | Babikmoh@yahoo.com |
| Rasha | Ibrahim | 914928492 | SOS | technical Psychologist |  |
| Dirk | Gerke | 924549940 / 918210151 | THW |  | Thw_sudan@yahoo.de |
| Juergen | Maresch | 924981424 / 918119740 |  | Head of Mission | Thw_sudan@yahoo.de |
| Joerg | Ropel | 924550065 / 918275156 |  |  | Thw_sudan@yahoo.de |
| Mamoun | Mohammed | 912838121 | BBCwst | Research Officer | mamoun.mohammed@bbcwst.net |
| Eman | Eltigani | 912167428 |  | Research out reach Leader |  |
| Mary | Mulvihill | 914856964 | AED | country director | mmulvihill@aed.org |
| Patrick | Opio | 910711468 |  | regional operation manager (Darfur region | popioQaed.org |
| Local Partners |
| Mohammed | El Sayed Hassan | 918057678 | AM | Head of El Fasher Sub Office | almassarorg@yahoo.com |
| Zeinab | Ghandour | 912608246 |  |  | almassarorg@yahoo.com |
| Adam | Hamid | 122587978 |  | Admin officer |  |
| Dr. Isam | Wadai | 912215669 | AOPR | Project manager | ajaweed_darfur@yahoo.com, issamwadai@yahoo.co.uk |
| Ahamed | Adam Yousif | 912251484 |  | Manager | gahmedadam@yahoo.com |
| Adam Ishaq | Tajedin | 122328958 | HAD | Health coordinator |  |
|  |  |  | SRC |  |  |
| Barakat | Faris Badri | 918051650 |  | Branch Director | srcsndarfur@yahoo.com |
| Ibrahim | Omer Mohamed | 912586222 |  | food distribution focal point |  |
| Osman | Munsour | 914579175 | SUDO | Head of Office | dosmansooka@yahoo.co.uk, munsour@sudosudan.org |
| United Nations |
| Mulugeta | Shibru | 912396702 | FAO | Head of Sub-Office | Ecu_elfashir@yahoo.com |
| Bashir | Abed El Rahman | 912396710 |  | Agriculture Field Officer | Ecu_elfashir@yahoo.com |
| Randa | Hassan (OIC) | 912160337 | OCHA | Humanitarian Affairs Officer, (OIC) | hassan50@un.org |
| Katrine | Wold | 912150726 |  | Humanitarian Affairs Officer | wold@un.org |
| Kimberly | Lietz | 913571491 |  | M&E Specialist | lietz@un.org |
| Jean | Wabo | 912501141 | UNDP | Head of Office | Jean.wabo@undp.org |
| Omer | Haroun | 912179384 |  | National Field Officer | Omer.haron@undp.org |
| Joel | Gaunt | 912500277 |  | Rule of Law Officer | joel.gaunt@undp.org |
| Mumtaz | Abdulsatar | 915938556 | UNDSS | Field Security Officer (SIU) | abdulsatar@un.org |
| Alexandra | Rugimescu | 914832053 |  |  | ruginescu@un.org |
| Jenny | Ariano | 912304065 |  | Field Security Coordination Officer - North Darfur Team | ariano@un.org |
| Sunday | Adeosun | 912502107 |  | Security Officer | adeosun@un.org |
| Ashruf | Ishag | 0121463526 | UNFPA | RH Officer | ishag@unfpa.org |
| Ezizgeldi | Hellenov | 121844721 |  | Team Leader | khellenov@unfpa.org |
| Halima | Yagoub | 122018252 |  | GBV Assistant | yagoob@unfpa.org |
| Amilu | Chilingulo | 912160740 | UNICEF | PO-Education | achilingulo@unicef.org |
| Haydar | Nasser | 912174639 |  | Chief Field Office | hnasser@unicef.org |
| Azzedine | Zeroual | 912167630 |  | PO-Health | zazzedine@unicef.org |
| Simon | Salimini | 912133997 | UNJLC | Field Logistics Officer | simon.salimini@wfp.org |
| Adil | Kamoun | 912170732 |  | Field Logistics Assistant | Adil.kamoun@wfp.org, kamoun_adil@yahoo.com |
| Sarah | Rossman | 912532353 | UNMAS | Programme Officer | rossmanns@un.org |
| Phil | Rowe | 912167221 |  | Operations Coordinator | rowep@un.org, (absent) |
| Magda | Abdalla Ibrahim | 912496860 | UNAMID | Gender Affairs Officer | Ahmed63@un.org |
| Enos | Chuma | 910114855 |  | Humanitarian Liaison unit |  |
| Traver | Mullign | 9i2502036 |  | UNAMID/civi affairs | muigan@un.org |
| Deom | May |  | UNAMID/Military | UNAMIDCMLO | deonmay@webmail.co.za |
| Zephyd | Nkhuwa | 924840691 |  | CMLO 1 | znkhuwa@yahoo.com |
| Karen | Perrin | 912178768 | UNMIS | Protection Officer | perrink@un.org |
| Mamane | Sani Moussa |  |  | Protection Officer | Mamane Sani Moussa/UNMIS@UNMIS |
| Ryan | Anderson | 0912177401 | WFP | Programme Officer | ryan.anderson@wfp.org |
| Laurent | Bukera | 912177318 |  | Head of area office | laurent.bukera@wfp.org |
| Mikdad | Lawi | 0912167052 |  | Air Transport Officer | mikdad.lawi@wfp.org |
| Patrick | Yankuba | 912167960 |  | Head of Field Office, Kutum | Patrick.yankuba@wfp.org |
| Mohamed | Shalaby | 912175771 | UNOPS | engineering Manager | Mshalaby@unops.org |
| Makkawi | Eisa | 911120048 | WHO | Secretary | eisam@sud.emro.who.int |
| Julius | Wekesa | 912174695 |  | Head of Sub-Office | wekesaj@sud.emro.who.int |
| Simone | Cllisoluoch Olunya | 192323716 | UNAIDS | Zonal coordinator | simone.olunyo@undp.org |
| Alias | Ahmad | 912141169 | UNCHR | Head of Office El Fasher | ahmad@unhcr.org |
| Tayba | Sharif | 912174670 |  | Protection Officer | sharif@unhcr.org |
| Donors |
|  |  |  | Organization Acronym |  |  |
| Sophie | Battas | 912172743 | ECHO | ECHO TA Nyala | sophie.battas@echosudan-nyala.org |
| Corinna | Kreidler | 912532399 |  | ECHO Nyala | corinna.kreidler@echosudan-nyala.org |
| Ayoub Mahamed | Ibrahim | 918319778 | USAID | Admin Assistant | Admin.fash@gmail.com, aibrahim@ofda.gov |
| Oumar | M'Bareck | 912174495 |  | Field Officer | ombareck@ofda.gov |
| Embassies |
| Eythan | Sontag | 91-579-7200 | USA |  | SontagEM@state.gov |
| Sjoerd | Smit | 912167565 | Netherlands | Liaison officer | sjoerdsmit@gmail.com |
| Government bilateral coordination (As per needs) |
| Eltayib | Abakasee |  | GOS | Kebkabiya Local Counselor |  |
| Fouzia | Abass Abdulhameed | 915427336, 122329140 |  | Advisor to the Governor |  |
| Idris | Abdalah Hassan | 911249467, 122012429 |  | Minister of Local Authority & Service |  |
| Hasaballah | Abdallah H. | 912810126 |  | Director General Ministry of Education |  |
| Ibrahim | Ahmed Hamid | 912142410 |  | HAC Commissioner, North Darfur |  |
| Eltijani | Ahmed Senin | 912300366, 122207581 |  | Mayor of El Fasher |  |
| Khalid | Ali Fagirry | 912588807 |  | Presidency Mayor |  |
| Nasr | Eldeen Bagaal Sirag | 912807248 |  | Minister Of Health |  |
| Ismail | Elhaj Yousif | 912349477 |  | Minister of Public Urban Utilities |  |
| Abdulrahman | Elsiddig Ismail | 912645829 |  | Mayor of Kebkabiya |  |
| Adam | Herry Bosh | 912800138 |  | Minister Of Agriculture & ARAI |  |
| Abdelshafy | Issa Mustafa | 912547127 |  | Minister of Culture, Youth & Sport |  |
| Ali Mansoor | Mineese | 912231064 |  | El Fasher Local Councilor |  |
| Issa | Mohamed Abdallah | 912817188 |  | Mayor of Kutum |  |
| Omer | Mohamed Elbashir | 912328083 |  | Minister of Education |  |
| Abdallah | Mohamed Elzubir | 912684109, 122018521 |  | Advisor to the Governor |  |
| Hussin | Mohamed Hamid Elnahala | 918081667, 911278206 |  | Mayor of Alwaha |  |
| Ahmed | Salih Ahmed | 912809680 |  | Minister Of Social Affairs |  |
| Eltayib | Salih Gadal | 912161226 |  | Minister of Finance & Economy |  |
| Mohamed | Salih Mohamed Ismail |  |  | Health Advisor |  |
| Osman | Yousif Kibir | 912570240 |  | Governor Of North Darfur |  |

# Risk Analysis

ERT identified the following disasters that occurred in Sudan in the past 50 years:

a. Drought

b. Floods

c. Displacements

d. Civil War

e. Outbreaks of meningitis/cholera

f. Regional Wars

g. Locust Infestation

h. Desertification

i. Civil Unrest

j. Famine

k. Land mines

Based on this, as well as other factors, the ERT identified all potential disasters in country within the next 12-18 months:

a. Drought for Kordofan

b. Drought in Darfur complemented by displacement

c. Drought in East Sudan

d. Floods in Khartoum

e. Floods in Kordofan

f. Floods in Eastern Sudan

g. Floods in Central Sudan

h. Displacement in Darfur as a result of conflict

i. Displacement in South Kordofan (Abeyi and others)

j. Displacement in the East (refugees from the Eritrea)

k. Civil Unrest all Sudan

l. Epidemic all Sudan cholera, Meningitis

Lastly the ERT has prioritized these disasters, with the Highest Risk levels first, terms of probability and impact on livelihoods, economy, environment and infrastructure as described in the below table:

| Hazard Event | Probability (1-10) | Impact (1-10) | Risk Level |
| --- | --- | --- | --- |
|  |  |  | (Probability x Impact) |
| Displacement in South Kordofan (ABYE + other) | 10 | 8 | 80 |
| Displacement in Darfur – conflict | 9 | 8 | 72 |
| Drought Kordofan | 8 | 8 | 64 |
| Drought in Darfur – displacement | 8 | 8 | 64 |
| Drought in East Sudan | 8 | 7 | 56 |
| Floods in Eastern Sudan | 5 | 7 | 35 |
| Floods in Khartoum | 6 | 4 | 24 |
| Floods in Central Sudan | 6 | 3 | 18 |
| Displacement in the East (refugees from the Eritrea) | 5 | 3 | 15 |
| Floods in Kordofan | 3 | 2 | 6 |

# Scenario Development

## Scenario 1 – Drought and Conflict in Darfur

### Scenario Description

- What is the disaster that is occurring? Internal and external displacement, epidemic, lack of basic social services, environmental resource damage, loss of livelihoods, lack of individual and household security, malnutrition, food shortage, etc

- Why is this disaster occurring?  Because of the

- Shortfall of the main rain season in year 2007 (started early and cessation was early)contributed for low food production

- Lack free access to productive lands as a result of conflict and war

- Low acceptance of the UN peacekeeping forces by the populace

- Fighting between fragmented factions and GoS and boarder tension

- Deterioration of humanitarian agencies operational environment

  - Where is it happening?

- South Darfur State (Kass, Buram, Gereida, Ed-Alfursan, El-Daen, Tulus, Menawashi)

- West Darfur State (Mukjar, Zalingi, Wadi-Salih, Umdukhun, Binidisi, UmKheir)

- North Darfur State (Millet, Malha, Tawila, Kutum, DarZagawa)

  - When is it happening? Now and throughout the year 2008 And for how long? At least for one year provided that immediate response delivered

  - How are people being affected? Deterioration and loss of the basic livelihood (means of living) and lives and exposed for unnecessary harassment which will take their human dignity.

  - Who is being affected? The prime victim of the disaster will be children, mother (pregnant, lactating), female, disabled and elders.

  - Estimated number of affected people by region/area. In all the region/area the number of people that will be affected by the disaster indicated above will be estimated to be 70% additional to the current affected people CARE serving. See the table below for detail number of affected population and estimated number by locations.

Estimated number children and women affected per each region/area.

| Location | Current IDP | Current Target IDPs | Estimated |
| --- | --- | --- | --- |
|  |  | Children | Women | Total | IDP Population | Children | Women | Total |
| Otash | 60,984 | 12,197 | 18,295 | 30,492 | 91,476 | 18,295 | 27,443 | 45,738 |
| Al-Salaam | 65,000 | 13,000 | 19,500 | 32,500 | 97,500 | 19,500 | 29,250 | 48,750 |
| Kalma | 91,680 | 18,336 | 27,504 | 45,840 | 137,520 | 27,504 | 41,256 | 68,760 |
| El-Serif | 13,758 | 2,752 | 4,127 | 6,879 | 20,637 | 4,127 | 6,191 | 10,319 |
| Kass East | 41,526 | 8,305 | 12,458 | 20,763 | 62,289 | 12,458 | 18,687 | 31,145 |
| Kass South | 7,635 | 1,527 | 2,291 | 3,818 | 11,453 | 2,291 | 3,436 | 5,726 |
| Kass IDP | 91,526 | 18,305 | 27,458 | 45,763 | 137,289 | 27,458 | 41,187 | 68,645 |
| Eumlabas | 623 | 125 | 187 | 312 | 935 | 187 | 280 | 467 |
| Dagadusa | 2,621 | 524 | 786 | 1,311 | 3,932 | 786 | 1,179 | 1,966 |
| Kubum | 2,208 | 442 | 662 | 1,104 | 3,312 | 662 | 994 | 1,656 |
| Ed-Fursan | 62,413 | 12,483 | 18,724 | 31,207 | 93,620 | 18,724 | 28,086 | 46,810 |
| Kass North | 15,115 | 3,023 | 4,535 | 7,558 | 22,673 | 4,535 | 6,802 | 11,336 |
| Gasila | 25,611 | 5,122 | 7,683 | 12,806 | 38,417 | 7,683 | 11,525 | 19,208 |
| Mukjar | 14,769 | 2,954 | 4,431 | 7,385 | 22,154 | 4,431 | 6,646 | 11,077 |
| UmkHeir | 16,510 | 3,302 | 4,953 | 8,255 | 24,765 | 4,953 | 7,430 | 12,383 |
| Umdhukun | 33,992 | 6,798 | 10,198 | 16,996 | 50,988 | 10,198 | 15,296 | 25,494 |
| Deleji | 17,820 | 3,564 | 5,346 | 8,910 | 26,730 | 5,346 | 8,019 | 13,365 |
| Bindisi | 12,885 | 2,577 | 3,866 | 6,443 | 19,328 | 3,866 | 5,798 | 9,664 |
| Zalingi | 99,431 | 19,886 | 29,829 | 49,716 | 149,147 | 29,829 | 44,744 | 74,573 |
| Gereida | 123,076 | 24,615 | 36,923 | 61,538 | 184,614 | 36,923 | 55,384 | 92,307 |
| Kutum | 66702 | 13,340 | 20,011 | 33,351 | 100,053 | 20,011 | 30,016 | 50,027 |
| Kabkabiya | 96,224 | 19,245 | 28,867 | 48,112 | 144,336 | 28,867 | 43,301 | 72,168 |
| Millet | 9,830 | 1,966 | 2,949 | 4,915 | 14,745 | 2,949 | 4,424 | 7,373 |
| Kafod | 8,000 | 1,600 | 2,400 | 4,000 | 12,000 | 2,400 | 3,600 | 6,000 |
| Dar-Zagawa | 54078 | 10,816 | 16,223 | 27,039 | 81,117 | 16,223 | 24,335 | 40,559 |
| Tawila | 37379 | 7,476 | 11,214 | 18,690 | 56,069 | 11,214 | 16,821 | 28,034 |
| Saraf-omra | 24110 | 4,822 | 7,233 | 12,055 | 36,165 | 7,233 | 10,850 | 18,083 |
| Um-Tajok | 24753 | 4,951 | 7,426 | 12,377 | 37,130 | 7,426 | 11,139 | 18,565 |
| Zamzam | 45895 | 9,179 | 13,769 | 22,948 | 68,843 | 13,769 | 20,653 | 34,421 |
|  | 1,166,154 | 233,231 | 349,846 | 583,077 | 1,749,231 | 349,846 | 524,769 | 874,616 |

- What is their capacity to cope? The capacity to cope is significantly affected by the on-going war and conflict and it can not be relied to overcome the disaster. What are the coping strategies and capacities of men and women? Women and children in general are the prime victim of the disaster compared to the men and they do not have enough mechanisms to cope the disaster. Currently the only coping mechanism which considered by the men and women is displacement to the IDP camps, where they are expecting humanitarian support.

- What are the most immediate needs of the affected population? (E.g. food, shelter, non-food items, etc.) Food, Water, Health, Shelter, protection, psychosocial support, NFI, environmental supports such as fuel wood.

- What are the key constraints that actors in the response are confronting? Access to the affected people, staff safety and wellness, poor infrastructure and services, coordination challenge at the start, governmental procedures and policies,

### Impact Analysis and Risk Reduction Measures

| Impact on Social, Economy, Environment, Infrastructure | Prevention Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Reduced quality of life, changes in lifestyle | Provide life skill training. Support with IGA (income generation activity) Providing basic assets for protecting existing ones Support on strengthening traditional coping mechanisms | Identify life skill need, & inputs Identification of realistic IGA for women and vulnerable groups Study the asset resources of vulnerable people Identify indigenous coping mechanism | Immediate life skill training with seed capital provision. Immediate support for IGA Immediate provision of basic assets for up keeping the family life | Establish a life skill community managed centres establishing a community managed revolving fund for IGA Food-For-Asset project Cash For Work (CFW) projects |
| Population migrations | Provide livelihood support in the area of origin with the assumption that migration is because of drought not conflict Protection of civil life | Identify the type of support, target people, implementation modalities, etc using the EPP Identify vulnerable groups of civil society | Immediate provision of WatSan services Immediate support for Health facilities Establishment of Nutrition services Provision of Food Aid Support on school (infrastructure, material, feeding, etc) Provision of protection service to female and vulnerable groups | Launching sustainable livelihood projects in their area of origin Support in building the service provision of basic social services (Health, school, water, market, etc) Support on peace building and community initiatives |
| Disruption in the local and governmental services | Support the local grass root institutions to build their capacity for sustainable up-keeping of existing services | Identify existing local institution which has acceptance by the people and local authorities Identify capacity gaps of the grass root institutions | Immediate support on training to build capacity of local institutions for sustaining services training Ensuring all communities involvement and participation in decision making process at all stage Immediate support in resumption of basic services (health, school, market, water, road, etc) | Establishment of community management system for smooth running of basic services Building the basic social services infrastructure to address the growing need in participation of the community. Food-For-Work, FFT, FFA, CFW project implementation to revive the livelihood To support the community initiation for peaceful co-existence |
| Health status of population (epidemic, malnutrition) | Support and strengthen existing health services for PHC, TFC, SFC, campaign outbreak. Building the capacity of health services to handle additional caseloads when emergency occurs Ensuring health professionals are trained in IMCI (Integrated Management of Childhood illness) Dissemination of household latrine services with proper hygiene promotion | Identify the most vulnerable areas and target groups. Identifying potential partners. Identifying existing resources from internal and external Ensuring the basic stocks are procured and kept close to the area Establishing a working relation with potential training institution for IMCI and other capacity building | Immediate and direct support to the existing health facilities on PHC, TFC, SFC and IMCI. Establishment of TFC, SFC linked with the existing facilities. Providing NFIs (Blankets, mosquito nets, soap) Immediate blanket distribution of supplementary food Immediate distribution of food aid | Continuous support on building the capacity of Health services in rural areas Provision of medical facilities and medicines to be used on revolving fund Implementation of FFW for infrastructure rehabilitation and maintenance Establishing a community managed health services such community health promoters, etc |
| Water Supplies source shortage | Identifying possible areas of water sources shortages Establishing a ground water source monitoring system Establishing alternative source of water such as rain water catchments through FFW, CFW and expansion of network | Identify technical capacities and inputs. Building the materials and supplies reserve for water services. Establishing a realistic partnership. Conducting geophysical surveys. Mapping possible areas of water shortage and potential | Immediate maintenance and rehabilitation of the damage sources of water. Immediate support on the establishment of water management system from the target beneficiaries Establishment of emergency water distribution system such water tankering, erecting bladder and tankers, etc Hygiene promotion and training of proper water usage among the community. | Establishment of water source monitoring mechanism. Establishing alternative source of water such as rain water catchments through FFW, CFW and expansion of network. Establishment of water management association for sustaining the services |
| Deforestation | Awareness creation among the communities on environment Developing community action plans for environmental conservation Creating linkage with the local universities in the area for technical support on environment Encouraging agricultural practices promoting soil fertility enrichment Support on training and visit extension system | Identify areas of possible interventions Identify and building the internal capacity for environmental interventions Identifying the existing community capacities for coping environmental issues Identify possible institution and universities engaged in environmental promotion | Immediate support in the provision of alternative energy sources Immediate training for communities on importance of environment | Establishment of community managed nurseries. Support for community clubs in management of environmental issues. Promotion of alternative IGA linked with environment interventions Promotion of agro-forestry in appropriate areas (intercropping, soil and water conservations, etc) |

### CARE Prevention and Mitigation Measures

| Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible Person |
| --- | --- | --- | --- |
| Provide life skill training. Support with IGA (income generation activity) Providing basic assets for protecting existing ones Support on strengthening traditional coping mechanisms | MOFA III DCPSF (new) ECHO WFP III Darfur Pooled Fund DEC DEAP-OFDA CIDA JLC/NFI | March 1, 2008 April 1, 2008 On-going On-going On-going On-going On-going On-going Ongoing | Benson/Tom/Mariam/Haroon Liz/Dereje Issam/Benson Charles Benson/Tom/Dereje Tom/Benson Tom Benson/Margaret Zuhal/Sarah |
| Provide livelihood support in the area of origin with the assumption that migration is because of drought not conflict Protection of civil life | MOFA III DCPSF (new) ECHO WFP III Darfur Pooled Fund DEC CIDA | March 1, 2008 April 1, 2008 On-going On-going On-going On-going On-going | Benson/Tom Liz/Dereje Benson Charles Benson/Tom/Dereje Tom/Benson Benson/Margaret |
| Support the local grass root institutions to build their capacity for sustainable up-keeping of existing services | MOFA III DCPSF (new) ECHO Darfur Pooled Fund DEC CIDA | March 1, 2008 April 1, 2008 On-going On-going On-going On-going | Benson/Tom Liz/Dereje Benson Benson/Tom/Dereje Tom/Benson Benson/Margaret |
| Support and strengthen existing health services for PHC, TFC, SFC, campaign outbreak. Building the capacity of health services to handle additional caseloads when emergency occurs Ensuring health professionals are trained in IMCI (Integrated Management of Childhood illness) Dissemination of household latrine services with proper hygiene promotion | Gates Foundation CIDA ECHO | On-going On-going On-going | Benson/Tom Benson/Margret Issam/Benson |
| Identifying possible areas of water sources shortages Establishing a ground water source monitoring system Establishing alternative source of water such as rain water catchments through FFW, CFW and expansion of network | DEAP-OFDA BMZ (Germany new) DSPCF (New) CHF | On-going Jul 1, 2008 April 1, 2008 April 1, 2008 | Tom/Haroon Tom/Haroon Liz/Dereje Tom/Haroon |
| Awareness creation among the communities on environment Developing community action plans for environmental conservation Creating linkage with the local universities in the area for technical support on environment Encouraging agricultural practices promoting soil fertility enrichment Support on training and visit extension system | DCPSF (New) Darfur Pooled Fund MOFA III (New) | April 1, 2008 On-going March 1, 2008 | Liz/Dereje Benson/Tom/Dereje Benson/Tom/Mariam/Haroon |

### CARE Response Strategy

#### Goal and objectives of CARE’s response

To improve the livelihood of war and drought affected people and create resilience to shocks in South, North and West Darfur. The specific objectives of the emergency response are the following:

- To provide immediate support to improve the quality of life of affected people through provision of life skill training., IGA support and capacity building

- To provide immediate needs of affected people through access for potable water, health service, food aid, basic education, NFI (mosquito nets, plastic sheet, blankets, etc) and addressing malnutrition through TFC/SFC.

- To provide immediate support for alternative sources of energy for affected population through provision of fuel efficient stove, training of target beneficiaries in construction and understanding of impact of deforestation.

#### Criteria for engagement

| Criteria for Engagement | Check if present |
| --- | --- |
| National authorities formally declare an emergency. | X |
| There is significant loss of life or threat to livelihoods (define if possible). | X |
| At least more 1,000 households are estimated to be displaced and affected. | X |
| Local or national authorities have requested assistance. | X |
| Needs outstrip the capacity of local and national responders. | X |
| International agencies close to the emergency have been given support and time to respond. | X |
| Needs outstrip the capacity of international responders. | X |
| CARE has offered support to local or international responders. | X |
| CARE has an operational presence in the affected area. | X |
| CARE has ongoing programs in affected communities. | X |
| CARE has the experience and skills to respond competently. | X |
| CARE has the operational capacity (staff, assets, transport) to respond. | X |
| CARE has a timely opportunity to help affected communities with mitigation and prevention. | X |
| There are good local partners with whom CARE can work. |  |
| CARE has a responsibility to respond to WatSan needs in the IDP camps and taking a lead role in the sector | X |
| People will die if CARE does not respond. | X |

#### Partnership Analysis

NGOs and UN Organizations

| Stakeholder | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| UN-OCHA | Coordination of humanitarian interventions | Formal | Strengthening the existing working relation to bring further synergy through sharing information |
| UN- WFP | Responsible for food aid coordination | FLA contracts | Conducting joint assessment for identifying the vulnerable people in the target area. |
| UN-FAO | Food and livelihood security sector coordinator | CHF Contracts (LoA) | Joint food and livelihood security need assessment and building the capacity for the response |
| UN-JLC | Coordinating the logistical support for NFI | Contracts | Pre-positioning of NFIs for the target areas |
| UNICEF | Sector lead agency for WatSan, nutrition, Health, NFI procuring and Education | PCA/contracts depending | Joint planning for pre-positioning and procurement of NFI, working on nutrition and health assessments |
| UN-IOM | UN agency mandated for returns | Formal coordination through RWG | Information sharing and planning |
| Humedica | Coordinating IDP camp operations, provision of emergency health services | Formal coordination | Sharing information and engaging in joint assessment |
| IRC | Working jointly in the camp on water and sanitation | Formal coordination | Maintaining the existing relationship to be more efficient |
| Oxfam | Partner working in water and sanitation, NFI distribution and health interventions both in the camp and rural | Formal coordination | Maintaining the existing relationship to be more efficient |
| GOAL | Involved in NFI distribution | Formal coordination | Information sharing and joint planning |
| GAA | Involved in the distribution of NFIs | Formal coordination | Information sharing and joint planning |

Government and Local Organizations

| Stakeholder | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| HAC | Coordinating body of government for humanitarian interventions | MoU/TA/Contract | Involving in the planning of the preparedness through sharing information on regular basis |
| WES | Coordinating WatSan intervention and sector lead to sign TAs | TAs | Working in collaboration for materializing the preparedness plan and sharing information and actions. |
| SMoH | Coordinating on Health and Nutrition intervention | TAs | Working closely in implementation of the EPP |
| SMoA | Coordinating on Food security and agricultural supports during emergency | TAs | Ensuring their full involvement in the application of the EPP |

Donors

| Stakeholder | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| OFDA | Providing Funding for emergency response | Formal relationship in the past | Maintaining the existing working relationship with OFDA and understanding any newly developed formats and guidelines |
| CI (Netherlands, Germany, UK, etc) | Raising funding during emergency | Formal agreement | Strengthening more on the area of potential fund raising |
| Foundations (Gates, Howard Buffet, Omidayr, etc) | Major private donors during emergency | Formal working relationship | Maintaining the existing relationship |
| ECHO | Major donor for humanitarian support | Formal working relationship | Maintaining and strengthening existing working relationship |

Other Stakeholders

| Stakeholder | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| SPCR (Sudanese Popular Committee for Relief | Local NGO with developed capacity to implement/respond when emergency occurs | Sub-Grant agreement | Joint planning and information sharing and involving in assessment in areas which can not be accessed by CARE. |
| NOCD (National Organization for Care and Development) | Local NGO with capacity in livelihood in IDP camps, IGA training, RH and PHC in Kass, SGBV in Kass and Community peace building support | Sub-grand agreement | Joint planning and information sharing and involving in areas which can not be accessed by CARE |

#### Geographic areas

The geographic focus areas will remain the same as listed below:

- South Darfur- Kass (Abroum, Gemiza Lagaro, Singita, Dibisi), Kubum, Um-Lambasa, Dagadousa, Markundi, Nyala (Kalama, Otash, El-Serif, and Al-Salam)

- West Darfur – Genina, Mukjar, Zalingi (Hamadiya, Hisa-Hissa, Kemse Dekaike, Tayiba, Shebaba), Garsila, Bindisi, Deleiji, UmKheir, Umdukhun,

- North Darfur- Elfasher, Tawila, El-Salam, Abu-Shook, Zamzam, Kutum, Kafod, Kebkebiya.

In case of significant emergency which will affect the larger part of the geographic focus area CARE Sudan will decide the geographic area expansion based on the EPP protocols (i.e. after carrying out assessment on capacity and externals factors, etc). CARE will approach potential partner to provide emergency response in areas where low presence exists.

#### Program interventions

Objective 1: To provide immediate support to improve the quality of life for 20,000 HH of affected people through provision of life skill training, IGA support and capacity building

Interventions: Life skill training, provision of IGA support and capacity building

Objective 2: To provide immediate needs for 50,000 HH of affected people through access for potable water, health service, food aid, basic education, NFI (mosquito nets, etc) and addressing malnutrition through TFC/SFC.

Interventions: WatSan (O&M, Hygiene and Sanitation, Latrine construction, water point development), Health services (PHC, vector control, epidemic support), food aid (GFD), Education (basic education and Non-formal education for adults), NFI (Distribution of mosquito net, jerry cans, shelter materials, blankets) and nutrition (TFC, SFC and support hospital)

Objective 3: To provide immediate support for alternative sources of energy for10,000 HH of  affected population through provision of fuel efficient stove, training of target beneficiaries in construction of stove and understanding of impact of deforestation.

Interventions: Distributions of fuel efficient stoves, training on construction of fuel efficient stoves, distribution of fuel

#### Target beneficiaries

The target beneficiaries of the response will be people affected by the war and drought with main focus on marginalized, vulnerable and female and children., The total beneficiaries in CARE Darfur operation area will be 291,538 HH (1,749,231 people) of which 50% will be IDPs.

#### Partnership Arrangements

| Stakeholder UN, NGO, GOVT, Local Org, Donor, etc | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| UN-OCHA | Coordination of humanitarian interventions | Formal | Strengthening the existing working relation to bring further synergy through sharing information |
| HAC | Coordinating body of government for humanitarian interventions | MoU/TA/Contract | Involving in the planning of the preparedness through sharing information on regular basis |
| WES | Coordinating WatSan intervention and sector lead to sign TAs | TAs | Working in collaboration for materializing the preparedness plan and sharing information and actions. |
| UN- WFP | Responsible for food aid coordination | FLA contracts | Conducting joint assessment for identifying the vulnerable people in the target area. |
| UN-FAO | Food and livelihood security sector coordinator | CHF Contracts (LoA) | Joint food and livelihood security need assessment and building the capacity for the response |
| UN-JLC | Coordinating the logistical support for NFI | Contracts | Pre-positioning of NFIs for the target areas |
| UNICEF | Sector lead agency for WatSan, nutrition, Health, NFI procuring and Education | PCA/contracts depending | Joint planning for pre-positioning and procurement of NFI, working on nutrition and health assessments |
| SPCR | Local NGO with developed capacity to implement/respond when emergency occurs | Sub-Grant agreement | Joint planning and information sharing and involving in assessment in areas which can not be accessed by CARE. |
| UN-IOM | UN agency mandated for returns | Formal coordination through RWG | Information sharing and planning |
| Humedica | Coordinating IDP camp operations, provision of emergency health services | Formal coordination | Sharing information and engaging in joint assessment |
| IRC | Working jointly in the camp on water and sanitation | Formal coordination |  |
| Oxfam | Partner working in water and sanitation, NFI distribution and health interventions both in the camp and rural | Formal coordination | Maintaining the existing relationship to be more efficient |
| GOAL | Involved in NFI distribution | Formal coordination |  |
| GAA | Involved in the distribution of NFIs | Formal coordination |  |
| OFDA | Providing Funding for emergency response | Formal relationship in the past | Maintaining the existing working relationship with OFDA and understanding any newly developed formats and guidelines |
| CI (Netherlands, Germany, UK, etc) | Raising funding during emergency | Formal agreement | Strengthening more on the area of potential fund raising |
| Foundations (Gates, Howard Buffet, Omidayr, etc) | Major private donors during emergency | Formal working relationship | Maintaining the existing relationship |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Existing Manpower | Need during response | Gap |
| --- | --- | --- | --- |
| Team Leader | 1 | 2 | 1 |
| Livelihood Project Coordinator | 1 | 3 | 2 |
| WatSan Project Coordinator | 1 | 3 | 2 |
| Nutrition and Health Project Officer | 1 | 5 | 4 |
| Food Project Coordinator | 1 | 3 | 2 |
| Human Resource Manager | 3 | 5 | 2 |
| Finance officer | 3 | 5 | 2 |
| Admin Officer | 2 | 4 | 2 |
| Staff Safety Officer | 1 | 3 | 2 |
| Shelter Specialist | 0 | 2 | 2 |
| Environment Specialist | 0 | 1 | 1 |
| Conflict Sensitivity Advisor | 1 | 3 | 2 |

#### Immediate procurement requirements

| S/N | Items | Unit | Qty |
| --- | --- | --- | --- |
| 1 | CSB | Mt | 15 |
| 2 | Plumpy Nut | Mt | 5 |
| 3 | Jerry cans | Pcs | 20,000 |
| 4 | Mosquito nets (treated) | Pcs | 10,000 |
| 5 | Hand Pumps (Indian Mark II) with accessories | Set | 50 |
| 6 | PE Water Pipe (2”) | Roll | 10 |
| 7 | Chlorine tablets | Box | 10 |
| 8 | Water tanker (10,000 litre) | Pcs | 5 |
| 9 | Woven mat for Latrine (at least for 2,000 latrines) | Pcs | 10,000 |
| 10 | Wooden Poles for Latrine (for 2,000 latrines) | Pcs | 16,000 |
| 11 | Cement for Latrine Slabs | Mt | 10 |
| 12 | Reinforcing bars for latrine slabs | Pcs | 200 |

#### Logistics requirements

The logistics requirement are warehousing for food and NFI, communication equipment such as base and mobile radios, Thuraya phone, guest houses for national and international staff, and office space . The table below indicates the existing logistical capacity and the need during response and gaps.

.

| Item | Existing | Need during response | Gap |
| --- | --- | --- | --- |
| Warehouse NFI | 4 | 5 | 1 |
| Warehouse Food | 0 | 1 | 1 |
| Base Radio | 4 | 6 | 2 |
| Thuraya | 21 | 30 | 9 |
| Phone Mobile | 34 | 34 | 0 |
| Guest House Nyala (Int) | 2 | 3 | 1 |
| Guest House Nyala (Natl) | 1 | 1 | 0 |
| Guest house Kass (Intl) | 1 | 1 | 0 |
| Guest house Kass (Natl) | 1 | 1 | 0 |
| Guest House Zalingi (Int) | 1 | 1 | 0 |
| Guest House Zalingi (Natl) | 0 | 1 | 1 |
| Guest House Mukjar (Intl) | 1 | 1 | 0 |
| Guest House Mukjar (Natl) | 1 | 1 | 0 |
| Office Nyala | 2 | 3 | 1 |
| Office Kass | 1 | 1 | 0 |
| Office Zalimgi | 1 | 1 | 0 |
| Office Mukjar | 1 | 1 | 0 |
| Office Kubum | 1 | 1 | 0 |
| Guest house Kubum (Natl & Intl) | 0 | 1 | 1 |

#### Trigger Indicators

| Indicator | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible | Yes/No or Value | Critical Values |
| --- | --- | --- | --- | --- | --- | --- |
| CMR >1 | MoH, WHO | Hospital & Health clinics | Monthly | Nutrition/health project officer | Yes | >1 |
| SAM | UNICEF | Target areas | Monthly | Nutrition/health project officer | Yes | > 5 |
| Morbidity | MoH, WHO | Health clinics, survey | Monthly, quarterly | Nutrition/health project officer | No |  |
| Number of affected people | HAC, CARE Rapids assessment, OCHA, IOM | Affected areas | At the onset of emergency | Program Coordinator | Yes | >10,000 as per CET |

#### Entry and Exit/Transition Strategy

In all operation at the entry point CARE will ensure that the local institutions are engaged in the design, implementation, monitoring and evaluation of emergency response. Identified community based institutions will be provided with capacity building support in the project period.

CARE will hand over to the potential local institutions identified during the emergency response period all the output/outcome of the emergency response for sustaining and smooth operation. In addition, CARE will ensure that transitional recovery activities are included prior to the phase out of the emergency response.

### Local Considerations

| Dimension | Challenge / Consideration (if ANY) | Recommendation (if ANY) |
| --- | --- | --- |
| Language | Language barrier for expatriate | Basic language and culture training should be conducted upon arrival of expat staff Hiring local translators Hiring/including local knowledgeable staff |
| Culture | Mainstreaming of gender and diversity in conflict affected area. | Orientation of expat on cultural issues for sensitivity Awareness rising for both females and males. Encourage female participation in community activities. Including both males and females as community workers. |
| Ethnic tensions | The nomad and sedentary conflict over resources. Pocket tribal clashes. | Provision of equal support for both. Peace building support. |
| Sectoral Violence | None | None |
| Security | Banditry looting, carjacking, abduction. Fight between different groups. | Enforcing staffs S&S (Safety and Security) measures. Using local resources instead of using CARE resources (vehicle, trucks. |
| Economy | Price increase due to big influx of UN personnel. Irregular supply of basic resources such as fuel and projects materials (construction materials), due to road inaccessibility from the main city. | Advocate with UN on common. Regular monitoring of market prices and adjusting. Establishment of basic supplies stocks. |
| Infrastructure | Quality of warehouses in different parts of the project areas. Poor roads infrastructure. Unavailability of appropriate premises. | Erecting of rub halls. Inclusion of realistic alternative means of transport. Prefabricated premises, rehabilitation and modification of available premises to meet the requirements. |
| Local Organization | Poor capacity of existing Local organizations. | Capacity building. |
| NGOs/UN | Lack of co-ordination at time of emergency. | Taking a lead in the areas of CARE operation in terms of coordination. |
| Local Government | Long process in providing support. Complicated and unclear procedures. | Establish of high level of cooperation and relationship. Understanding the process. |
| Regional Implications | Boarder conflicts and fights. | Closely monitor and apply the safety and security measures. |
| Other Human resources. | High staffs turn over, due to influx to join UN. | Establishing of staff retention measures. |

## Scenario 2 – South Kordofan – increased displacement

### Scenario Description

Floods: The rainy season is June – October.  Heavy rains will cause floods, these floods will cause displacement.  Housing quality is low so houses will be easily destroyed.  Crops will be destroyed, causing food insecurity.  Roads will be flooded and damaged.  Floods are more likely to affect southern and eastern Jebel’s – Kadugli County and locality, Talodi locality, and Abu Jebeha locality.

Conflict: Tribal conflicts are increasing due to political affiliations and disputes over land, livestock, and water.  The borders have not been clarified and groups have conflicting ideas about the border. Conflict is most likely to affect Abyei, Lagawa, El Sounoul, Dilling, Meiram, Muglad, Higlig, and Kharasana, and people would be expected to displace to the larger towns of Dilling, Kadugli, Babanusa, En Nuhud and El Obeid (Northern Kordofan).

Result:

Increased displacement in a short period of time and displacement would be internal to Southern Kordofan.  People would have lost their assets either because of flood destroying them or rapid movement.  Displacement would be at least 100,000 but depend on number of villages affected by floods or conflict.  Please note that the year 2007 floods displaced 80,000.  Children and women would be the most vulnerable and most likely to be displaced.

The population is very vulnerable and has limited coping strategies.  Many of them have only recently returned to their original place after 20 years of war between South and government.  Institutions are still weak and almost nonexistent; in Abyei two government systems are still being discussed.  Community ties are not strong so outside support would be needed.

Access would be difficult because flood or conflict would either damage or close roads.  Access to roads would be controlled by tribal affiliation, including for commercial transporters. The disaster would prevent both farming and trade.

The immediate needs of the population would be food and non-food items.  Health interventions will be needed for conflict or flood related affected people which cause displacement.  Natural water sources are very limited so water need to be provided complemented with hygiene and sanitation services for IDPs.

The key constraints would be the prevalence of the two government systems, poor infrastructure, and spread of weapons, difficult to have neutrality accepted.  High probability that SAF and SPLM would become involved because of oil and previous conflicts over the border region and so the conflict would escalate.

### Impact Analysis and Risk Reduction Measures

| Impact on Social, Economy, Environment, Infrastructure | Prevention Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Increased unemployment | Life-skills training program | Coordination with other actors | Provision of immediate support for continuing their means of living | Livelihoods project |
| Increase in crime | Support to the local rule of law and good governance | Advocacy on law and order | Immediate support for community institutions involved in law and order through awareness and training | Community policing |
| Increase in school dropout | Providing support for school infrastructure development and management of the school | Training of local school teachers | Construction of temporary school buildings and school feeding programmes | Rebuilding and rehabilitation of rural schools complemented with strengthening the management system |
| Lack of water/clean water | Stronger water system, chlorinating of water system put in place pre-disaster | Have list of vendors in place and coordination with water department | Water chlorination, water bladders for distributing through tankering | Rehabilitation of water sources |
| Sanitations systems lost/destroyed | Improve household pit latrines | Hygiene and sanitation awareness | Construction of temporary latrines and more hygiene awareness | Sewage system in both areas of displacement and original home |
| Increase in diseases | Health education and immunization | Have stock of immunizations, medicines, have list of likely diseases and coordination with other actors | Use of mobile clinic and providing PHC services | Support to existing health services through local partners |
| Roads and bridges damaged | Build stronger roads and bridges, road regulations | Have alternate routes planned, alternate transport (heli), | Support for alternative way of immediate development of temporary bridges | Construction or repair of roads and bridges |
| Roads cut off (conflict) | Discuss with community leaders, government, militants, UNDSS to secure safe passage | Identification of alternative roads, good relationship with the communities, advocacy | Use of convoys Placement of checkpoints on the roads, use of helicopters |  |
| Psycho-social stress | Strengthen community support mechanisms, through social leaders | Support Community disaster preparedness program initiatives | Psycho-social programmes for affected people | Developing the community capacity in managing stress and post-trauma effects |
| Families broken up | Strengthen social values |  | Child protection Family re-unification |  |
| Increase of commodity prices | Provide support for farmers cooperatives for stabilizing market | Food banking, better storage facilities | Food distribution | Food for work |
| Damaged houses | Stronger building | Stocking of emergency shelter construction materials | NFI distribution | Providing support for shelter reconstruction and rebuilding |
| Savings are lost | Provide support for diversification of household income sources through training | Provide asset protection awareness for communities | Providing support for basic household asset to lead their lives in IDP camp | Support on asset rebuilding intervention through existing community system |
| Damage to crops | Support for establishment of cut-off drain system for reliving floods in the farm and train on crop diversification | Cut-off drain establishment | Free food distribution to feel the gap | Provision of seeds and tools |
| Loss of livestock | Support a system for livestock-off-take to maintain the household asset | Early warning (floods), advocacy – peace building | Traditional reparations/dialogue (conflict), vaccinations of remaining stock | restocking |

### CARE Prevention and Mitigation Measures

| Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible Person |
| --- | --- | --- | --- |
| Building schools from stronger materials to prevent damage in the first place | livelihood | Ongoing | TL - Cecilia |
| Stronger/expanding water system, improve pit latrines | CHF/livelihoods | Ongoing | Water engineer Ali |
| Have list of water/chlorination vendors in place and coordination with water department | CHF/livelihoods | June 1 | Ali |
| Health education, hygiene awareness | Livelihoods | Ongoing | Ali |
| Have alternate routes planned | JLC | June 1 | Jayendra/Bashir |
| Discuss w community leaders, govt re road access during conflict | Livelihoods | May 1 and as needed | Yousif |
| Farmers cooperatives | Food Security | Ongoing | Awad |
| Encourage food banking | Food Security | December 1 | Awad |
| Crop diversification | CHF/food security | Ongoing | Awad |
| Plastic distribution | CHF | May 1 | Cecilia |
| Early warning (floods) | Livelihoods | Ongoing | Yousif |

### CARE Response Strategy

#### Goal and objectives of CARE’s response

To reduce the negative effects of internal displacement caused by floods and/or conflict and reduce the possibility of future conflict and/or mitigate the effects of future floods. The specific objectives will be the following:

- To provide emergency food to the affected communities while meeting the SPHERE standard

- To construct or repair water systems to make clean water accessible and potable for human being as per the accepted standard.

- To raise hygiene awareness through hygiene promotion for the affected communities.

- To distribute NFIs for emergency shelter needs and to reinstate basic household assets

- To promote local communities’ involvements on peace-building related to tribal conflicts and encourage peaceful co-existence and return.

#### Geographic areas

CARE will definitely respond in its current operational areas which are Kadugli, Dilling, and Lagawa. Also depending on the scale of the disaster CARE would respond in: Abyei, Talodi, En Nuhud or El Obeid, and Babanusa

#### Program interventions

Food security, emergency shelter and shelter rehabilitation, NFI distribution, water/sanitation, peace-building

#### Target beneficiaries

Vulnerable and displaced people and host communities, current response capacity is estimated at 40,000 but with surge capacity, could assist as many as 100,000.

#### Partnership Arrangements

| Stakeholder UN, NGO, GOVT, Local Org, etc | Role in Emergency | Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- |
| RCO | Coordination | Information provision, facilitation | Share preparedness plan |
| WFP | Food provider | Food partner | Share preparedness plan, esp.food needs/plans |
| FAO | food security/livestock | Provide seeds, tools | Share preparedness plan, esp. seeds/tools needs/plans |
| UNJLC | NFI coordination | Approve NFI requests | Share preparedness plan, esp. NFI needs/plans |
| Save-US | NGO | Coordination – food and NFI, Abyei | Contact re Abyei |
| HAC | Coordination | Information provision, assist with assessments, facilitation | Share preparedness plan and revise with them as needed |
| NCA | NGO | Coordination – food and NFI distrib | Share preparedness plan, discuss food and NFI distribution plans |
| Medair | NGO | Coordination – wat/san | Share preparedness plan, discuss wat/san needs |
| GOAL | NGO | Abyei - coordination | Need to contact re Abyei |
| FAR | NGO | Coordination – sanitation, food security | Share preparedness plan |
| GAA | NGO | Coordination – food security | Share preparedness plan |
| IRC | NGO | Lagawa coordination – food security | Share preparedness plan, discuss Lagawa response strategy |
| SRC | NGO | Coordination – distributions and monitoring | Share preparedness plan |
| IOM | IO | Information sharing | Share preparedness plan |
| UNDSS | Security | Provision of security information, guidelines |  |
| UNICEF | Wat/san and health lead | Provision of mosquito nets, soap | Share preparedness plan and possible needs for wat/san or health inputs |
| Armed groups |  | neutral |  |
| Ladingra | Local NGO | Joint assessments, partner – NFI, food distribution | Share preparedness plan and work on capacity building regarding preparedness, outline responsibilities |
| Nuba Mtn Assoc | Local NGO | Joint assessments, partner – NFI, food distribution | Share preparedness plan and work on capacity building regarding preparedness, outline responsibilities |
| Village Develpt Committees | Local structures | Assist with assessments, audience for advocacy, pass on advocacy messages | Share preparedness plan and work on capacity building regarding preparedness, outline responsibilities |
| Community Leaders |  | Audience for advocacy, information source, advisors | Share preparedness plan and incorporate their inputs |
| Line Ministries (agriculture, health, rural development and water services) | Coordination |  | Share preparedness plan and incorporate their plans in the CARE plan |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Existing Manpower | Need during response | Gap |
| --- | --- | --- | --- |
| Team Leader | 1 | 2 | 1 |
| Livelihood Project manager | 1 | 2 | 1 |
| WatSan engineer | 1 | 2 | 1 |
| Nutrition and Health Officer | 0 | 2 | 2 |
| Human Resource officer | 0 | 2 | 2 |
| Finance officer | 1 | 2 | 1 |
| Admin Officer | 1 | 2 | 1 |
| Staff Safety Officer | 0 | 1 | 1 |
| Logistics officer | 1 | 2 | 1 |
| Procurement officer | 0 | 2 | 2 |

#### Immediate procurement requirements

| S/N | Items | Unit | Qty |
| --- | --- | --- | --- |
| 1 | Blankets | Pcs | 5,000 |
| 2 | Plastic sheets | Pcs | 5,000 |
| 3 | Iron poles for plastic sheets erection | Pcs | 40,000 |
| 4 | Plastic ropes for plastic sheets erection | Rolls | 2,000 |
| 5 | Empty Jerry cans | Pcs | 10,000 |
| 6 | Mosquito nets (treated) | Pcs | 10,000 |
| 7 | Plastic sleeping mats | Pcs | 10,000 |
| 8 | Washing soap | Boxes | 5,000 |
| 9 | Hand Pumps (Indian Mark II) with accessories | Set | 20 |
| 10 | PE Water Pipe (2”) | Roll | 15 |
| 11 | Chlorine tablets | Box | 8 |
| 12 | Water tanker (10,000 litre) | Pcs | 5 |
| 13 | Water bladders 5,000 litre capacity | Pcs | 5 |

#### Logistics requirements

The logistics requirement are warehousing for food and NFI, communication equipment, guest houses for staff, and office space. The table below indicates the existing logistical capacity and the need during response and gaps.

.

| Item | Existing | Need during response | Gap |
| --- | --- | --- | --- |
| Warehouse NFI | 3 | 0 | 0 |
| Warehouse Food | 0 | 1 | 1 |
| Base Radio | 1 | 1 | 1 |
| Thuraya | 3 | 5 | 2 |
| Phone Mobile | 1 | 5 | 4 |
| Guest House – Kadugli | 1 | 3 | 2 |
| Guest House – Dilling | 0 | 1 | 1 |
| Guest house – Kurchi | 0 | 1 | 1 |
| Office – Kadugli | 2 | 3 | 1 |
| Office – Dilling | 1 | 2 | 1 |
| Office – Kurchi | 1 | 1 | 0 |
| Office – Abujebeha | 1 | 0 | 0 |

#### Trigger Indicators

| Indicator | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible | Yes/No or Value | Critical Values |
| --- | --- | --- | --- | --- | --- | --- |
| Flood - Rain levels | Govt |  | Rainy season | Senior programme officer Yousif | Yes/No | Water flowing over the banks |
| Conflict - Presence of armed groups in public areas | Local community, local staff, UNDSS | Markets, |  | Team Leader Cecilia | Yes/No | Someone killed in public area, self-imposed curfew, empty market |
| Conflict - Stockpiling of grains | Traders | markets | Market days | Abbas | Yes/No | Inflation of grain prices |
| Flood - Stress selling of assets | Local community | CARE project areas | Market days | Abbas | Yes/No | Selling female animals |
| Conflict - Road blocks | UNDSS, UNJLC | All SK |  | Cecilia | Yes/No | # of new roadblocks |

#### Entry and Exit/Transition Strategy

Entry: Through monitoring of the trigger indicators, Team Leader/Field Coordinator determines that assessment is needed and begins work with local partners on the ground to collect information.  Team Leader/Field Coordinator informs Emergency Response Coordinator that a trigger indicator has been reached.  Then, communications sent to other organizations in the operational area. If the disaster response is manageable, response activities would be conducted by the local partners (Ladingra, Nuba Mtn Association) with CARE coordination. Response done by local staff, in coordination with current partners, if manageable, surge capacity called as Team Leader deems necessary.  Response activities would start with assessments with partners on the ground where CARE already operates.  Distribution of NFIs and/or food as needed in those areas.  At same time, discuss with NGOs in other areas where CARE not operational to see if CARE presence is needed.  Then expand to areas where CARE not operational in coordination with the NGOs on the ground

Exit/transition – Following emergency response, transit into rehabilitation activities

### Local Considerations

| Dimension | Challenge / Consideration (if ANY) | Recommendation (if ANY) |
| --- | --- | --- |
| Language |  |  |
| Culture | Current staff have good links, understanding |  |
| Ethnic tensions | Tribal – nomad/pastoralist (messiriya/dinka/nuba), political (SPLM/NCP) | Transparency with programming, meeting with communities and local government officials, |
| Sectoral Violence | Not a big issue |  |
| Security | Some landmines/UXOs, Darfur conflict spillover, oilfields, limited demobilization, small arms available, banditry | Get updated security information from govt, police, UNDSS, communities. Maintain contact list with relevant institutions |
| Economy | Limited skilled labor, small private sector so difficult to purchase or repair items locally, inflation | Maintain list of vendors including outside Kadugli, budget for inflation, |
| Infrastructure | Poor or nonexistent roads – limited rainy season access. Limited flights | Coordinate with other organizations and govt for transport |
| Local Organization | Weak local NGOs – capacity, facilities | Continue current relationships and capacity building, maintain communication |
| NGOs/UN | Coordination difficult, roles not clearly defined – multiple actors (UNMIS, UNDP) | Advocate for clearer roles re coordination |
| Local Government | HAC limited coordination capacity but good facilitation | Advocate with UNDP for improved HAC coordination capacity – provision of communication capacity |
| Regional Implications | Darfur spillover, CPA implications, | Stay informed, stay neutral |

## Scenario 3 – Drought in North Kordofan

### Scenario Description

- Why :	Reduced or changes in the cycle of rainfall

- Detailed areas affected: North Kordufan generally (Rural areas more vulnerable)

- Usual rainy season is from July to October, and any likely effect of drought would happen from August through out the dry season to the next harvest (August in one year to November the next year)

- Effects on humans: food gap for at least 6-12 months, water shortage, depletion of assets, loss of income, malnutrition, increased morbidity and mortality, displacement for other income opportunities/survival, increased food and water prices, cattle prices decreases, as people sell cattle to survive and cattle are not in the healthiest state, school attendance is affected, poor nutritional food as substitute.

- Effect on livestock: food gap, water shortage, morbidity and mortality

- Population affected:

  - Population of rural areas in North Kordufan are directly affected (approx. 500,000)

  - Indirectly affected population in urban areas in North Kordufan and surrounding areas (approx. 1,000,000)

  - Estimated women and children affected: 75% of the respective population

  - Elderly, women and children are the most vulnerable

- Rural communities here are vulnerable as:

  - Do not stock up sufficient food reserves

  - Water shortage in general , so drought worsens the situation

  - The value of their assets (livestock) is significantly reduced as they are equally affected

  - Displacement that causes competition for resources would not support for the peaceful co-existence of people.

  - Increased prices of food in the market

  - Increased crime rate in areas of displacement

  - Health hazard due to over population from displacement

- Coping mechanisms:

  - Seeds of a drought resistant tree that has little nutritional value

  - migration/displacement

  - selling their assets, usually at a low price

  - non-skilled labour in urban areas

- Immediate needs

  - Food aid in areas affected to avoid displacement

  - Food aid, water, shelter and NFIs in areas of displacement

  - Health and water interventions in areas affected

  - Fodder, water and veterinary interventions for livestock

- Actor constraints

- Timely delivery of needs items

- Reaching everybody affected in such a wide spread area (transport access)

- Setting up early warning system

- Co-ordination with the government and other actors

- Health intervention would be the most difficult as no health facilities

### Impact Analysis and Risk Reduction Measures

| Impact on Social, Economy, Environment, Infrastructure | Prevention Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Population migration | Livelihood interventions Constant monitoring of the rainfall and harvests | Early warning system Food reserves for immediate distr. Regular assessments | Food distribution including nutrition interventions Water Tankering | Providing Livelihood support in area of origin |
| Safety and security | Co-ordination with communities | Safety and security regular monitoring and policy update | Vigilance Staff security measures Regular briefing | Livelihood interventions |
| Food insecurity | Encourage better agric. Planning and food reserves Advocate for Gov food reserves | Government food reserves Capacity to deploy Mapping of required resources for deployment | Co-ordination body that includes all actors Access to affected areas | Agricultural and Environmental interventions |
| Water supplies | Construction of haffirs other reservoirs Water tankering | Mapping required resources Capacity to deploy | Co-ordination of response with government and other actors Water tinkering | Haffir assessment and long term maintenance to be adopted by the government |
| Price of major foods | Increasing agricultural production IGA | Government food reserves | Dispatch reserves to the market to normalize prices | Diversified Livelihood interventions to avoid dependence on a single occupation |
| Loss of agricultural and livestock production | Improved seeds Improved livestock management | Mapping resources (food, fodder, e.t.c) | Food distribution Fodder distribution Water for both humans and livestock Health intervention for both | Distribution of seeds Livestock restocking |
| Health status of the population decreased | Health and hygiene Awareness raising Health facilities are maintained | Information on where to acquire mobile clinics, medical procurement, kits and medical staff. To pre-arrange an EPP partnership with the M0H for staffing, | Mobile clinics Nutrition intervention Draining standing waters if applicable | Food security Health education Hygiene awareness Increased access to health services |
| Increased mortality | Health facilities Food security Health & hygiene | Mapping resources Capacity to respond | Mobile clinics Supplementary & therapeutic feeding | Support on RH, PHC, etc |
| Conflict over resources | Construct haffirs Conflict mitigation & peace building | Increase awareness on climate change Be knowledgeable of causes Monitoring tensions | Provision of immediate support for social services | Peace building intervention supported with livelihood component & basic services |
| Loss of income for households | IGA projects Improved agricultural production Improved livestock management | Marketing skills Monitoring household incomes Diversify IGA activities Training on diversified IGAs | Cash for work/training | Provide inputs for IGA Improved agricultural& livestock production |
| Unemployment | IGA and microfinance as alternatives | Designing microfinance and IGA projects | Cash for work | Provision of life skill training and seed capital |
| Loss of biodiversity | Environmental interventions | Awareness and environmental interventions | Supporting tree planting in displacement areas | Working in partnership with forestry department on recovering the bio-diversity |
| Increased number and severity of forest fires | Environmental awareness | Co-ordination with Forestry Department for building fire break. | Immediate support for controlling the forest fire | Environmental interventions |
| Wind and water erosion of soils | Improved agricultural techniques Environmental awareness | Sand bags and plantation of desert plants for sand dune protection | Surface layering Sand bags | Agricultural and Environmental interventions |
| School attendance reduced | Attendance monitoring Health monitoring | Negotiations with UNICEF/WFP for food for education | Prepared meals in schools Clean portable water in schools Sanitation facilities in schools Health awareness and interventions | Provide support to Schools to strengthen the management system so as to increase enrollment |

### CARE Prevention and Mitigation Measures

| Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible Person |
| --- | --- | --- | --- |
| Improved food security Improved agricultural activities Food processing and storage Livestock restocking and management Diversify IGA activities Microfinance | Proposal for EC | Sep 08 | Jacque |
| Water intervention More haffirs Water bladders Sustainable use of water Water containers (UNJLC) | Cooperation with UNJLC | On going | Abdelmoniem |
| Health Status Mobile clinics | Not exist |  |  |

### CARE Response Strategy

#### Goal and objectives of CARE’s response

To provide an immediate and short term emergency response for affected populations in North Kordofan state and long term interventions for Elobied and Bara provinces.

The main purpose of the goal and objective is to reduce the impact of the disaster on vulnerable populations’ estimated at 75% of the total population which includes women, children and elderly people.

#### Geographic areas

North Kordufan state mainly focusing in Elobied and Bara, but not limited to other areas. Drought prone areas include: Sodari, Gabrat Sheikh, El Nuhud, Bara, Sheikhan, Um Ruwaba localities

#### Program interventions

- Water Haffirs, water yards, water tinkering, Latrine construction, hygiene awareness

- Food Security Free food distribution

- Shelter construction through plastic sheeting, tents

#### Target beneficiaries Vulnerable

CARE will address the immediate needs of 75% of populations mainly focusing on the most vulnerable women, children and elderly in North Kordufan which has a population of 2.3 Million (2006 statistics).

#### Partnership Arrangements

| Stakeholder UN, NGO, GOVT, Local Org, etc | Role in Emergency | Current Relationship to CARE | Desired Relationship to CARE | Actions to Improve Relationship During Preparedness |
| --- | --- | --- | --- | --- |
| WFP | Food distribution | Existing Partner |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| UNICEF/WHO | WATSAN and Health and Nutrition, assessment tools | Worked together in the near past |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Plan Sudan | Not involved in emergency other than education long-term support | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Goal |  | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| FAO | Agriculture | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Islamic Relief | Relief, Orphan protection | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| UNMIS | Funding, pipeline, protection | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Government (WES) | Co-ordination, relief, WATSAN | Worked together in the last floods (partners in other areas) |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Local NGOs | Human resource capacity, mobilization | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| Sudanese Red Crescent | Relief | Worked together in the last floods |  | Share EPPs. Encourage others to develop EPPs, resource and capacity mapping with partners, co-ordination role |
| IOM | Migration patterns | Non existent |  | Party/and the above |
| Ministry of Finance, Dept of Development planning | Mobilize other ministries and co-ordinate their participation and manage required resources | CARE has an MOU with them |  | Routine consultation meetings and share information. Clarity on their contribution and support (specific MoUs can be prepared) |

#### Key personnel requirements Darfur table)

| Position | Existing Manpower | Need during response | Gap |
| --- | --- | --- | --- |
| WATSAN and food Assessment teams | 0 | 12 | 12 |
| Team Leader | 0 | 1 | 1 |
| Proposal writer | 0 | 1 | 1 |
| Livelihood Project Coordinator | 0 | 1 | 1 |
| WatSan Project Coordinator | 0 | 1 | 1 |
| Nutrition and Health Project Officers | 0 | 5 | 1 |
| Food Project Coordinator | 0 | 3 | 1 |
| M&E Officer | 0 | 1 | 1 |
| Distribution agents | 0 | 15 | 15 |
| Human Resource Officer | 0 | 2 | 2 |
| Finance officer | 0 | 2 | 2 |
| Logistics Officer | 0 | 1 | 1 |
| Admin Officer | 0 | 2 | 2 |
| Staff Safety Officer | 0 | 1 | 1 |
| Drivers | 0 | 4 | 4 |

Note: Staff to be deployed from other project which needs advance notice.

#### Immediate procurement requirements

| S/N | Items | Unit | Qty |
| --- | --- | --- | --- |
| 1 | CSB | Mt | 15 |
| 2 | Plumpy Nut | Mt | 5 |
| 3 | Jerry cans | Pcs | 20,000 |
| 4 | Mosquito nets (treated) | Pcs | 10,000 |
| 5 | Hand Pumps (Indian Mark II) with accessories | Set | 50 |
| 6 | PE Water Pipe (2”) | Roll | 10 |
| 7 | Chlorine tablets | Box | 10 |
| 8 | Water tanker (10,000 litre) | Pcs | 5 |
| 9 | Sorghum | Mt | 1012 |
| 10 | Lentils | Mt | 173 |
| 11 | Oil | Mt | 68 |
| 12 | Transporters (suggest UNJLC transporters | contract | 10 |
| 13 | Construction materials | Pcs | 200 |

Note: The amounts will depend on the level of impact of the emergency and the assessment reports. However it is important to line up unit costs and suitable vendors/partners who can provide procurement needs at short notice (action for procurement Officer).

#### Logistics requirements

| Item | Existing | Need during response | Gap |
| --- | --- | --- | --- |
| Warehouse NFI | 3 | 5 | 2 |
| Warehouse Food | 0 | 3 | 3 |
| Base Radio | 0 | 4 | 3 |
| Thuraya | 0 | 10 | 10 |
| Phone Mobile | 4 | 15 | 11 |
| Field Offices | 1 | 4 | 3 |
| Generators | 1 | 4 | 3 |
| Computers | 4 | 15 | 11 |
| Printers | 2 | 6 | 4 |
| Vehicles | 4 | 12 | 8 |
| VSAT | 0 | 2 | 2 |
| Money safe | 2 | 4 | 2 |

#### `Trigger Indicators

| Indicator | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible | Yes/No or Value | Critical Values |
| --- | --- | --- | --- | --- | --- | --- |
| migration | CARE/other reports & assessment (IOM) | Alobied/Bara | QuarterlyMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes | > 10,000 as per CET |
| malnutrition | CARE/other reports & assessment, UNICEF/WHO/Health department | El-Obeid/ Bara | QuarterlMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes | <5 SAM >10% |
| Morbidity and mortality | CARE/other reports & assessment, Health department | Alobied/Bara | QuarterlyMonthly Bi-weekly | Emergency Response Cord. & Kordufan team | Yes | >1 |
| Poor harvest | CARE/other reports & assessment | Alobied/Bara | QuarterlyMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes | Price increased by 50% |
| Late/short rain cycles | Meteorological department and early warning system | Alobied/Bara | QuarterlyMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes |  |
| Food prices | CARE/other reports & assessment | Alobied/Bara | QuarterlyMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes | Price increased by 50% |
| Water prices | CARE/other reports & assessment | N Kordufan | QuarterlyMonthlyBi-weekly | Emergency Response Cord. & Kordufan team | Yes | Price increased by 50% |

Note:  Other assessments include IFAR, UNICEF, Government departments, and e.t.c

#### Entry and Exit/Transition Strategy (use common entry/exit strategy)

Based on the objectives and activities of CARE interventions, define the strategy to start the response operations, as well as exit from the emergency response, or transition from short term relief activities into longer term rehabilitation and development programs.

### Local Considerations

| Dimension | Challenge / Consideration (if ANY) | Recommendation (if ANY) |
| --- | --- | --- |
| Language | Arabic for international staff will face problem of communicating with local communities | Hire translators or current staff from local community who are capable of translation |
| Culture | Communication should come through community leaders (Sheikh) Will be offended if you didn’t eat or drink what they offer you. | Team working is the area should be well oriented in the area. And to be open to accept food and drink |
| Ethnic tensions | Staff hired from the local area will be affected directly or indirectly by the tension | CARE need to cross check staff safety in assigning for work |
| Sectoral Violence | May be affect with Darfur conflict. | Be aware and updated about security situation and conflict in surrounding area. |
| Security | Most areas bordering Darfur has been attacked several times. | Movement should be based on security clearance. Travel in convey or a least two vehicles and using flags. |
| Economy | Lack of food, water and fuel | Bring food supplies and others needed |
| Infrastructure | Roads are not well constructed | Use suitable vehicles 4WD |
| Local Organization | Low capacity of local NGO | Sharing of experience and training |
| NGOs/UN | Lack of coordination with other organization | Coordination meetings and inf. Sharing |
| Local Government | Non-cooperation is expected from the local gov. if they not fully involved | Work with gov. as partner. |

# Management Considerations and Gap Analysis

#### Personnel Requirements

Identify the Country Office key personnel requirements for the emergency operations and define their roles and responsibilities during the emergency.

| Position required | Currently Available? YES / NO, number | If currently Available, Name | If not available, action during the preparedness phase (prepare TOR, pre-select, etc) |
| --- | --- | --- | --- |
| A | B | C | D=B-C |
| Emergency Program Coordinator | Y, 2 | Salah Mohammed, Dereje Adugna |  |
| Livelihood Project Officer | Y, 3 | Dereje Adugna, Benson Wakoli, Henry Khonyownga |  |
| Watsan Project Officer | Y, 5 | Tom Maisiba, Chaungo Barasa, Haroon Nawiya, Suleimena Yusuf, Yassir Hassan |  |
| Water engineer | Y, 3 | Chaungo Barasa, Haroon Nawiya, Sulieman Yusuf (Darfur Program) |  |
| Nutrition Officer | Y, 2 | Margaret Kariku, Mary (FSWD, EC, Darfur) |  |
| M&E Officer | N |  | To be recruited soon |
| Information Officer | Y,2 | Adil Issa and May Adbelmiz |  |
| Procurement Officer | Y,4 | Ibrahim Elnoor, Manal Shawig, Aisha Basher, Shukri |  |
| Human Resource Officer | Y, 4 | Shazali Ibrahim, Salah Eldeen, Ibrahim EL-Tayeb, Omer El-Tahir |  |
| Finance Officer | Y, 8 | Yassir Defalla, Idris Mansour, Mona, Rebecca, Issam Bala, Binod Maskey, Mariam Mohammed, Karama Eldin |  |
| Admin Officer | Y, 4 | Tayfour, Kur Mayok, Sarra El-Saddig, Abubakr Gadin |  |
| Safety and Security | Y, 2 | Abdeen Faddul, Ake Torringer |  |
| Logistics Officer | Y, 6 | Mario Nundo, Shah Alam, Sarah Mc, Richard Terrera, Ashraf El-Magrabi, Kur Mayok |  |
| Shelter expert | N (CARE UK) |  | Request to CARE UK to support |
| Proposal writer | Y, 1 | Indira Sarma | To join mission soon |
| Distribution agents | Y | Distribution agents (from FSWD, EC Food Security SK and Darfur program) |  |
| Drivers | Y, 5 | Ali Zain, Idris Zakahria, Abdalla, Abdurahiman (Darfur), Hisham, |  |
| Guards | Y | Guards |  |

Additional Personnel Requirements:

- Training of Personnel

- Real situation practice on regular basis - Simulation

- Updating staff available column quarterly

Equipment, Supplies and Resources Requirements:

- Safety and identification clothing and Safety Kit for staff.

- Emergency tool kit (First Aid, relevant contact numbers, communication equipment, other)

Coordination and Partnership Considerations

- Understanding of partners EPP and potential role to avoid duplication

- Understanding availability of staff for deployment from partner organizations, and ensuring they receive same training e.t.c.

#### Assessment and Analysis

Goal and objectives during emergency: The main objective of assessment and analysis is to create an understanding on the disaster which occurred in a given time and specific areas. The purpose of the assessment will be to:

- Provide an understanding of the disaster situation and a clear analysis of threats to life, dignity, health and livelihoods to determine in consultation with the relevant authorities, whether an external response is required, and if so, the nature of the response.

- Carry out immediate assessment of a rapid on-set emergency as well as continual review and updating for slow on-set.

- Ensures capacity in reviewing scenarios and on-set of emergencies.

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| B | C | D=B-C |
| Assessment format is available (Clear Objectives Team Logistical support Information Requirements Guidelines and tools Data Collection Methods Informants Analysis Frameworks Recommendations Reporting | Yes but needs to be standardized Yes Yes Yes Yes Yes Yes Yes Yes Yes | Standardized the available format in the mission |
| Assessment team/staff have been identified trained Team Leader Program Logistics Security Technical sectors- health, WatSan, food, shelter Media | Team exists but not trained Yes Yes Yes Yes (SSC) Yes except shelter No | Placement of staff for media and training existing key staff on media strategy Get expertise to engage on shelter sector especially in areas where high risk of displacement |

- Additional Personnel Requirements: DM&E, Media, Shelter experts.

- Equipment, Supplies and Resources Requirements: Camping equipment with camping gears (simple and easy to transport), GPS with Altimeter,

- coordination and Partnership Considerations: Informing and sharing with UN-OCHA, INGO, Gov’t, LNGO, Inter-agency and multi-sectoral, multi-functional team

#### Design, Monitoring and Evaluation

Goal and objectives during emergency: The goal and objective of DM&E is to ensure that accurate data and information are gathered and analyzed for designing an emergency interventions and measuring the immediate impact of specific emergency interventions. The purpose of the DM&E will be as follows:

- Provides the strategy and direction for developing programming for mitigation, preparedness, and response activities including the ability for CARE to analyze and assess the impact these programs have in reducing risk

- Provides information for CARE management to make decisions and ensure the quality of emergency programs

- Ensures CARE’s accountability throughout emergency response

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| 1. Full time M&E on the CO level | No full time M&E Person | Recruit M&E person quickly – focal point in the CO |
| 2. Monitoring system and formats developed using and addressing Sphere Standards, Participation, Gender, and Vulnerable groups. | Few were develop and still project based | 1. review the current situation 2.Develop CO Monitoring system and format |
| 3. M&E systems in place to ensure regular collection of information in each of the technical sectors | Worked started, but set back after M&E coordinator left | 1. New M&E Coordinator to activate the system. |
| 4. DM&E standards linked with existing projects, integrating emergency and development into single DM&E procedure. | Review the current situation in projects. Some project does. | Linked emergency and development M&E into single procedures (include trigger indicators) |
| 5. Early Warning Systems, both formal and informal, are included in DM&E | Some project does have system. | - review the current situation in sub offices and project. - finalize trigger indicators foe each scenario - include risk indicators in the ongoing projects M&E systems |
| The CO is aware and capable of conducting the After Action Review required by CARE. | Not existing | - Contact Mohammed Khaled to organize training on how to conduct After Action Reviews. identify staff for evaluation - training identified staff on evaluation |
| Information flow is continual between CARE and communities/partners, enhancing community ownership and response to data collected and its analysis. | Ongoing initiatives on project/regional levels. | - establish system and guidelines to ensure continual information flow - strengthen communities’ capacities to data collection and analysis through training and development of appropriate format. |

Additional Personnel Requirements:

- Recruit CO M&E Coordinator

- Make sure that each project has M&C Officer (existing already)

Equipment, Supplies and Resources Requirements:

- Each project should allocate some resources (funds) for training communities and data collection

- Unrestricted funding for training communities and data collection

Coordination and Partnership Considerations

- ERTs should coordinate with partners in respective project areas in data collection and monitoring of the trigger indicators.

#### Human Resource Unit

Goal and objectives during emergency:

Ensure appropriate policy, procedures and systems are in place to support an emergency response, including any necessary adjustments to existing policy and procedures. Identify and deploy experienced staff through internal deployment, external recruitment, and standby arrangements with partners.  Ensure that CARE ongoing programs continued with minimum disruption during emergency.  Recruitment shall be undertaken in a manner of fairness and respecting CARE Core Values, without any discrimination.  HR plays a role in the organization structure planning and other strategic decision making for emergency planning and responses (safe staff arrivals, orientation and staff support).

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Emergency Response Team Identified | Yes. EPP Coordinator appointed +task force |  |
| Emergency Program Organization Chart in place | Yes. Organizational Chart maintained |  |
| Job Descriptions of ERT members updated to include additional roles in emergencies | No. ERT members operates in the absence of any updated JDs however, concerned members should be appraised against such responsibilities and different task force participation | Supervisors needs to update the JDs to accommodate the additional roles in emergencies |
| Back up Plan in place – to ensure Business Continuity, by anticipating the impact of emergency programming on CAREs operations and staff. | back up personnel are in place | Development plans for National staff to back up international staff |
| Emergency Hiring Procedures updated (how to expedite hiring, how to call upon CERT and CI for additional staff) | Yes. HAC approached during the emergencies to speed timing required to fill positions | Review the internal recruitment process to announce internally for only lower grades in the same geographical areas. Speed the internal process. HR Generalist for ECARMU to be involved in the process to call upon CERT staff considering immediate and specific recruitment processes |
| Databases of existing, former, and potential staff updated. | Yes. HR automated system is in place | Contact address and phone number is to be considered in the process for separated staff. Maintain former staff monthly report |
| Stress Management Plan in place – to ensure provision of ongoing or emergency stress management support. | Yes. Focal persons for staff psychosocial supports are working actively on Stress management in consultation with staff support coordinator and Staff Social Advisors. Stress management training is now a must course for all staff | MOU needs to be finalized with external source-Elfanar |
| Staff Emergency Record updated. | On going | Records, needs to be updated considering the urgent needs for recruiting the staff and the nature of the short term emergency projects |
| Antiterrorism requirements (OFAC) followed. This prohibits CARE from dealing with terrorists, including persons on various antiterrorism lists created by the State Department, FBI, Treasury, etc., and persons we reasonably suspect support terrorist activity even if they are not on lists. | Partially | OFAC rules exist in the CO but not considered in the hiring while assigning a sub analysis code for new recruited staff |
| Orientation for all new staff provided, and Orientation Package (preferably both in hard copy and electronic format) updated to include the recent information (see reference below) | Yes. Orientation considered for most of the new recruited staff and the orientation pack is in place | Circulate the pack to be introduced in all field locations under close follow up of HR focal persons |
| Ensure appropriate conditions, benefits and support are provided to all staff, including, R&R provisions, Insurance, Health and psychosocial support, Living conditions and provisions | Yes. Partially Medical coverage, Catastrophic illnesses fund, family leave and CTOs beside psychosocial support are in place | Staff working in hardship zones needs support in term of accommodation, transportation. Allocate extra fund for some projects ( WFP ) |
| Have up to date personnel contracts and files and ensure contract closure occurs for short term staff. | Yes. Policy issue |  |

Additional Personnel Requirements:

Develop and train HR specialized staffs to be deployed in the emergency locations

Equipment, Supplies and Resources Requirements:

Computers with appropriate accessories such as scanner and printers

Coordination and Partnership Considerations

HAC-Labour Office-MOH

HR net working group through HR forum.

#### Finance

Goal and Objectives:

  - Ensure the establishment of an efficient financial management structure for effective implementation of the program.

  - Coordinate cash flows, and donor reporting for all projects and program support

  - Use effective procedures for the design and management of budgets

  - Establish a capacity to deal with increase in donors, funds and transactions

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Participate with program unit in drafting budgets | Needs to be properly addressed | Ensure that all budgets are being seen by the finance before submitting it to the potential donors |
| Ensure at least one accountant is available at any operational area | Any office has got at least on accountant | Ensure that new CARE offices have at least one accountant |
| Ensure that bank accounts are opened for the new offices | All offices have got bank accounts | All new operational areas should have bank accounts |
| Ensure that all care offices allocated an office to the finance section equipped with a chair, desk and a safe | All offices have finance units equipped with all necessary equipments & a safe | All operational areas should have finance sections equipped with necessary equipments |
| Compile all necessary documents for fund codes requests, like the signed agreements between the donor and CARE budgets | All grants in our active portfolio have separate files containing all documentation | Ensure that all grants old and new have files |
| Ensure fund codes are assigned to the different emergency programs | All active grants have fund codes | All the grants in active portfolio should have fund code |
| Receive cash needs projections monthly from the project managers | Ongoing |  |
| Ensure immediate cash transfers to the emergency operational areas | Ongoing |  |
| Ensure donor financial reports are sent regularly to the donors and project managers | Ongoing |  |

Additional Personnel Requirements:

All filed offices should at least have an accountant during emergency in order to deal with the financial transactions.

Equipment, Supplies and Resources Requirements:

Computers, printers, furniture and safe for additional load of financial works.

Coordination and Partnership Considerations

To work closely with CARE USA and Lead members in establishing an up to date information sharing system with regard to emergency funding utilization.

#### Administration

Goal and Objectives:

- Ensure establishment of an efficient administrative management structure that provides timely support for effective implementation of emergency program.

- Effective administrative procedures and emergency administrative protocols used at CO and field levels

- All assets and inventory requirements are effectively managed

- Effective fleet management to meet emergency needs

- Administrative support provided to staff and visitors for travel, accommodations, supplies and provisions

- Compliance with all Government requirements and permits

- Offices, houses, warehouses and other buildings rented, equipped and maintained

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Roles and responsibilities are clear during emergency | Roles and responsibilities are in practice, but need to be further streamlined and updated to support emergency interventions (including levels of authority/approval) | Review and empowers SO admin units Tayfour. |
| JD in place for Admin staff in emergences | NO JD | Need to be agreed and developed Tayfour/Yasir/Shazali |
| Fleet management system in place | Yes-Nyala No-elsewhere | Identify required vendors Train drivers on preventive maintenance Stock fast moving spare parts |
| Offices have back up systems | All mission lacks back up systems (generators, photocopiers, VSAT ….ECT | All sub officers to work on |
| Communication equipments available | Yes, shortage in radio handsets | Reinforce policy |
| Backup in terms of shifting emergency resources | No plan available | Coordinate with PM to set up backup system Tayfour |
| space | Limited space | Plan to make use of GH, set prefabricated offices, etc. |
| Reliable vendors in potential areas | NO | Collect data and establish connections PMS |
| Coordination with potential partners | NO | PMs to start coordination (office, housing, vehicles, maintenance facilities. |
| Government systems/procedures pertaining to travel/stay/work permits/vehicle purchase are supportive to quick and effective interventions | GOV polices/procedures imposed by the state may hinder efficient and effective response | Liaise with HAC via NGOS forum and direct negotiations to simplify procedures to meet quick and effective emergency interventions. CD Admin Manager |

Additional Personnel Requirements:

Hiring assistant Administration Manager will be crucial

Equipment, Supplies and Resources Requirements:

Computer with accessories, vehicles and communication equipment for additional staff during emergency set-up

Coordination and Partnership Considerations

Coordinating administrative and logistical issues with other agencies working in the area in order to efficiently utilize the resources.

#### Procurement

Goal and Objectives:

- Timely procurement of quality goods and services for effective implementation of the emergency program in adherence to donor requirements and CARE policies.

- Ability to procure internationally.

- Required supplies, specifications and sources quickly identified.

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Procurement policy for emergency situation in place | In place | Learn from other missions on this – potential TDY of the Procurement Officer to another CO Capacity building for in country nation |
| Knowledge of international procurement & import requirements | Yes in place | Need to conduct training for all staff / update the manual |
| Knowledge of major donor procurement guidelines/change in emergency situation | To be addressed | Need to conduct training for donor guide lines / update of procurement manual |
| Knowledge of prohibited items | yes |  |
| Supplies likely to be required in emergency scenarios documented and supplies identified | No | Identify of emergency vendors, classified & well documented |
| List of providers and preferred vendors exists and is updated to include vendors of emergency suppliers | All location have update their vendor list and sent to Atlanta | Need to include emergency vendors |
| Regular reporting system | We have reporting system applied at South Darfur & Khartoum | To be applied for Kordofan, and north & west Darfur. |

Additional Personnel Requirements:

Additional persons to be deployed on temporary contract to do the field procurement

Equipment, Supplies and Resources Requirements:

Thuraya phone, VHF hand set, laptops, soft and hard copies of donors’ regulations etc

Coordination and Partnership Considerations

Coordination between the partners for providing emergency materials (UNCIEF, UNJLC, WFP, Local NGOs and government counterparts

#### Program Logistics

Goal and Objectives:

- Transportation, warehousing, dispatch and distribution of supplies and commodities to the program areas in a timely manner in adherence to donor requirements and CARE policies.

- Maintenance of controls and inventory system.

- Coordination with other authorities and stakeholder to ensure effective logistics

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Appropriate plans for storing and transporting of materials in place | Yes, can benefit from current capacity in JLC and Food projects. Also, JLC project keeps updated list of available warehousing in JLC project locations. |  |
| Appropriate plans for distribution of materials in place | Depending on project |  |
| Contracts/MoUs with key services providers are developed and ready | yes/no | Need to outline which services will be needed during an emergency and then work on contracts |
| Reliable transportation service providers identified | Yes – current CARE contracts for more than 1,000 locations in North Sudan | Share list of contracted locations with ERT |
| Appropriate warehousing management procedures in place. | Yes – through JLC and Food projects |  |
| Inventory management and control system in place | Yes – through JLC and Food projects |  |
| Staff trained in management of program logistics. | Yes – through JLC and Food projects |  |
| Good contacts with authorities and other agencies on logistics matters | Yes/no – JLC transporters arrange permissions so staff aren’t doing this |  |
| Security procedures in place | Not clear to everyone | Need to ensure that everyone is aware of security procedures for program logistics such as convoy protocol |

Additional Personnel Requirements:

Distribution personnel (5-8 people per distribution)

Additional warehouse staff and guards if more warehouses needed

Equipment, Supplies and Resources Requirements:

4WD vehicles for staff transport

Temporary warehousing (rub halls) petty cash for loading/offloading, cleaning of warehouses, food/water for distribution

CARE-branded hats and shirts

Maps of affected areas

Coordination and Partnership Considerations

Partnerships with WFP and UNJLC in place so food and NFIs can be accessed readily during emergency.

CARE-JLC project has provided spare warehousing and transport capacity to UNJLC, UNICEF, and UNHCR and so CARE may benefit from these relations in the future.

#### Information Technology and Telecommunications

Goal and Objectives:

Ensure rapid establishment of appropriate information technology and telecommunications services in the emergency areas, including internet connection, landline and mobile connections, faxes, satellite phones, radios, etc.

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Potential requirements on number and type of computing, printing, and telecommunication equipment identified. | Current communication equipment will not be enough to respond to emergency | Additional Radios and Satellite phone and Modems is needed Plus desktops, laptops and printers to be in the emergency shelf |
| Government regulations on import and use of radio, satellite, and telecommunication equipment identified. | Currently we have a bulk license to buy addition equipment. | Start ordering more tel equipment to cover basic requirement |
| Back up communication plan prepared. | For vehicles and office locations will be using radios and mobile phone, Satellite phone will be used as backup |  |
| Check for available equipments, and the prepare specifications and quantities need for the response. | Current staff capable of doing this job |  |
| Hire additional IT /communication specialist | We have 3 IT staff and 1 communication staff | Start Preparing the Job Descriptions and clearly identifying the capacity needed for the hired staff |
| Start contacting and coordinating with UN agencies for •Interagency telecommunication coordination mechanisms identified, and agreements with UN or other agencies developed for access to their communications systems in event of crisis. | The current telecommunication officer can handle this task | As the current handler is single, the required is to appoint a backup for him and to be oriented in dealing with the UN procedures. |
| Start contacting H AC to issue licenses to use the telecommunication media | We already have the license to the telecommunication media in all Sudan |  |
| Provide the ICT Policy and orientation packages and brief manuals of installing and using the ICT equipment and systems. | Manuals and concise training policies are ready and in place in the ICT department | Produce the manuals and policies in both hard copy and softcopy. |

Additional Personnel Requirements:

Hiring of additional IT specialist, telecommunication technician, and electric Technician.

Equipment, Supplies and Resources Requirements:

We will need the following items: desktops, Laptops. Printers, scanners, photocopiers, fax machines, HF/VHF radio stations, hand set and car sets for HF/ VHF, and Satellite modem

Coordination and Partnership Considerations

We need to coordinate with UN agencies in the area of telecommunications

#### Staff Safety

| Action to address gaps | Current Situation of Country office | Minimum level of preparedness |
| --- | --- | --- |
| Identify National staff safety officer for Darfur operation | It was exited in Kht &NK only | Identify staff safety committees and focal person |
| Updating on regular basis | Available in all the locations | Evacuation and contingency plan development |
| To encourage the SSCs to work on regular basis | No | Listing the Key Risks |
| Involve in training and develop the skill for analysis | Yes | Capacity building of Staff safety focal person |
| Provide all staff with hard/Soft copy of personal S&S procedure (Arabic/English) | Yes | CARE Safety & Security Training course |
| To be more closed to the relevant institutions | Good relation with UNDSS,ST is in place | External Relationship |

#### Fundraising

Goal and Objectives:

- To ensure that adequate financial resources are available for the mitigation, preparedness and response measures.

- Situation Awareness, Donor and Sector Awareness, and Proposal Development.

- Public Fundraising activities- press, appeals, stories and photos

- Provide information, stories and photos for fundraising purposes

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Prepare draft proposals based on the three scenarios agreed at the EPP workshop | To be addressed (TBA) | Each of the locations (SK, Khartoum and Darfur) to complete the scenario and share with Salah and then supported by Liz form a draft proposal writing team (consist of PU, Finance, administration, procurement and Indira) and Team who will then finalize the draft proposals |
| Share completed EPP with donors and other stakeholders (more detail below) and raise awareness of CARE’s EPP and readiness to react to the three scenarios outlined, highlighting the emergency activities and transition | TBA | Liz, either on a one-to-one basis or workshop or INGO forum |
| Share with UNDP CARE’s EPP, promoting our readiness to be part of any Emergency Task Force and that we are ready for immediate funds when a emergency strikes | TBA | Immediate on completion of EPP, Liz share and coordinate with John Clarke and discuss the setting up of a permanent Sudan Emergency Task Force, much along the same line as was running during floods last year, UN, Government, Local and National NGOs, and meet at least once per month or thereabouts |
| Share EPP plan with Government at each area of operation and try to obtain their commitment in working directly with CARE, including their commitment of materials, staffing etc that they could provide to CARE if the inevitable happens | TBA | Salah prepare a plan for SK and Darfur, as well as Khartoum (Salah, Liz and Adil) to sit with government officials and share EPP, and try to get buy in and to see how our EPP fits in with government plans (The EPP may have to be changed to accommodate this updated information from the government. |
| Create donor and other stakeholder contact list, after the above three points are completed | TBA | Adil - Once above points are completed and shared with Information Officer, then a contact list should be designed and put on the knowledge sharing site |
| Let it be known at national and local level, that CARE will play a major role in any emergency committees established | TBA | During sharing of EPP to all stakeholders mentioned above |
| Once the EPP is fully completed, share with all CI Members and try to keep them updated on the three scenarios outlined in the EPP | TBA | Salah - The easy part is sharing the EPP, the difficult part will be keeping them updated on any possible activities, the Information Officer and field offices must play a crucial role in this and a action plan must be thought through quite carefully |
| Once Emergency is underway, immediately work on draft proposals together with finance and appropriate teams to finalize and submit to relevant donors (including UN bodies) who have shown interest in that particular emergency, share the proposals with all CI members etc |  | Salah/Liz/Proposal /Indira, with appropriate proposal team. Liz then submits to donors within Sudan and to CI Members to submit accordingly. |

Additional Personnel Requirements:

National staff capacity building through training and hiring additional report and proposal writer as the need arises.

Equipment, Supplies and Resources Requirements:

Computers

Coordination and Partnership Considerations

Partnership with Government, LNGOs, UN and possible joint proposals with other INGOs

#### Media

Goal and Objectives:

- External Liaison and Communications in a professional manner: with international and local journalists, filmmakers, and photographers

- Raise awareness internationally and promote fundraising

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Produce an emergency media strategy | TBA | Liz (with Information Officer) in the meantime coordinates with Bea (Media Officer) from the Regional Unit and finalizes a CARE Sudan media strategy keeping in mind CARE USA policies. |
| Strengthening CARE Sudan Media | TBA | Further training to be provided to Information Officer and field staff (Jacqui provide training to Adil who will then become a trainer himself, he should also coordinate with Bea and receive further training) also on how to deal directly with media, in the meantime the CD or ACD-P should deal directly with media (currently following CARE’s policies) |
| During the emergency – write up of articles, media etc | Liz addresses this together with RMU | Liz review Indira’s JD and bring into it article writing and also to provide capacity building to Information Officer. A lot of work is required in this and needs to be strengthened; In any case, the RMU is back-up for this. It maybe that if an emergency comes up soon, then a TDY would need to come and assist on this |
| Documentation, photos etc | TBA | Information Officer with support from Indira, play a crucial role in this and together with the field staff, gather the stories, photographs etc and make sure they are shared to a wide audience and archived accordingly |

Additional Personnel Requirements:

- Report and Proposal Writer (will join in March)

- Media Officer in RMU

- Possible TDY required

Equipment, Supplies and Resources Requirements:

Camera and other simplified and portable media equipments

Coordination and Partnership Considerations

CARE will work in coordination with CEG and ECARMU in relation to media

#### Information Management

Goal and Objectives:

- Gather and disseminate information on the emergency situation and CARE’s response back to CARE International Member offices for use in emergency response, fundraising and communications activities.

- Ensure appropriate and effective internal information flow to CI, CARE Lead member, and other Country Offices.

- Quality information gathered, processed and disseminated

- Generation of reports and response to requests for information

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Focal person Identified | Central information focal person and his backup are identified | Additional training on emergency information management. Identification of focal point at filed level. |
| Development of reporting formats (soft copy) with tight schedule of submission. | Regular reporting and info. sharing with updates to specified channels (CD, ACD/P, TLs, and concerned PMs) on weekly and monthly). With moderate delay. | More share on the info. Timely submission of reports and feedback. Review and updates of the reporting formats (Adil).* |
| Identification central location of data and information. | Central archiving unit (CAU) in the public folders is established and functioning. | Regular update of the CAU. Develop ToR for the CAU on emergency issues and accessibility authorization to emergency reports. |
| Train of focal point on SITREP ….etc | Limited orientation on SITREP. | Train of focal points in filling on SITREP, alerts, Assessment Reports, and other formats. |

* Adil needs to work closely with the mission M&E Coordinator on monitoring emergency updates and reporting issues.

Additional Personnel Requirements:

- Identification of emergency information focal points at field level,

- Establishing an information sharing site

- Familiarizing information focal person with CET

Equipment, Supplies and Resources Requirements:

- Communication equipments (Thuraya, Radio, mobile phone)

- Incorporation of emergency update information into the newly developed program

Knowledge Sharing Website

Coordination and Partnership Considerations

Building of a network of information sharing at various levels from field, local authorities, partners and Local and international NGOs, HAC Federal (Early Warning Unit), RMU, and CI members

# Action Plan

| No | Actions Item | Person Responsible | Date of Completion | Budget Requirements |
| --- | --- | --- | --- | --- |
| EPP Development |
|  | Finalize draft EPP document (ERT structure, CO Capacity Inventory, etc) | Salah Mohammed & Dereje Adugna | July 3, 2008 |  |
|  | Share with the Sub-Offices | Salah Mohammed | July 10, 2008 |  |
|  | Share with EHAU to obtain funding | Salah Mohammed | July 3, 2008 | $15,000 |
|  | Share with partners | PMs | July 30, 2008 |  |

# Footnotes

In normal situations, CARE will rely on quarterly/monthly situation reports from other partners such as UN agencies, e.t.c. However should a situation deteriorate; CARE will need to activate internal monitoring so as to be able to make intervention decisions.

The available Emergency Coordinator is not fully assigned but can be fully deployed when emergency arises.

# Text boxes

Procurement Coordinator

Ibrahim Elnour

Sr.Liasion Officer

Abubakar Salah

Sr.Admin Officer

Abubakar Ahmed

Logistic Officer Vacant

Administrator

Tafour Osman

Ass/ Finance MGR

Isam Balla

Commodity /Accountant

Ahmed Mohamed Naser

Head of Finance & Budget

Idris Mansour

Finance Accountant

Rebecca Yawa

Finance Accountant

Sarah Mutafa

Accounting Clerk

Head of Finance Accounting

Mona Elamin

ACD Program

Liz McLaughlin

Director F/A/IT

Yassir Deafalla

Community development

Coordinator

Ahlam Abdelmajeed

Fleur Just Policy &Advocacy

Internal Auditor

Elhadi Yahia

HR Training Manager Salah Elsharif

Documentation Officer

Osailat

Payroll Officer

Mehad

Staff Develope Officer

Ibrahim Ahmed

HR Department

El Shazali

Staff Safety  Officer

Abdien FadalMula

Country Director

Navaraja Gaywali

IT Department

Vacant

Sr. IT officer

Sami Salim

IT Officer

Salah

Khidir

Communication

Ashraf Ibrahim

ROS/PC

Salah Mohd

M&E Coordinator

Faisal Ishag

WORLP PM & GED Coordinator

Ilham

Canada Fund Coord. Aymen Musamar

Vacant

Information Officer

Adil Eisa

Logistics – Geneina

Mario Nduna

M&E Officer

Vacant

Logistics – Fasher

Ashraf A. Elmaghrabi

Logistics – Nyala

Zuhal Ahmed

Logistics –Elobeid

Abdulmoniem Ahmed

Logistics – Kadugli

Jayendra Rathore

Logistics Coordinator

Sarah McNiece

Deputy L. C.

Md. Shah Alam

CTC Officer

Richard Terer

Food Security Coord

Jacqueline George

RPP

Vacant

Livlihood Dilling / Bakheit Mohammed

EC

Zainab Elnour

FSWD

May AbdelAzim

Nuba Mt. Team Leader

Cecilia Poni

Dupty food/Mukjar Henry Khon.

Vacant

Team Leader Darfur

Dereje Adugna

Staff Safety Coordinator Ake T.

Finance

Binod, Mariam, Karama, Yagob

WatSan PM Tom Maisiba

Health PM

Benson

Food PM Chalres Mule

Dupty//WatSan PM

Chaungo Barassa

Dupty/FOOD PM

Chalamati Virendra

Dupty food/kass-Caroline Waithira

Dupty food/Zalingi Prime Nkurunziza