CARE Indonesia

Emergency Preparedness Plan

Based on

CARE International

Emergency Preparedness Planning Guidelines

Initial draft developed: EPP workshop 3-6 March 2008

Updated:

Finalised:

Table of Content

Executive Summary	5

1.	Formation of Emergency Response Team	6

2.	Information Requirements	10

3.	Country Office Capacity Inventory	10

3.1.	Country Office Organization Chart	10

3.2.	Country Office Human Resources	10

3.3.	Country Office Physical Resources	11

3.4.	Country Office Key Staff Contact Information	12

3.5.	RMU, CARE Lead Member, and CARE International Key Contacts	12

3.6.	In Country Coordination Mechanisms and Contacts (GoI, local Partner, satkorlak, Bakornas, NGO/INGPO, UN Body)	12

4.	Risk Analysis	12

5.	Scenario Development	15

5.1.	Scenario 1 - Earthquake/Tsunami in Sumatra	15

5.1.1.	Scenario Description	15

5.1.2.	Impact Analysis and Identification of Risk Reduction Measures	15

5.1.3.	CARE Prevention and Mitigation Measures	16

5.1.4.	CARE Response Strategy	18

5.1.4.1.	Goal and objectives of CARE response	18

5.1.4.2.	Geographic Focus and Target Beneficiaries	18

5.1.4.3.	Response Interventions	18

5.1.4.4.	Implementation Phases/Timeline	18

5.1.4.5.	Partnership Arrangements	18

5.1.4.6.	Key personnel requirements	19

5.1.4.7.	Relief Item requirements	19

5.1.4.8.	Logistics/Equipment Requirements	20

5.1.4.9.	Trigger Indicators	20

5.1.4.10.	Key issues/challenges affecting CARE response	21

5.1.4.11.	Entry and Exit/Transition Strategy	21

5.1.4.12.	Funding requirements-summary budget	21

5.2.	Scenario  - Flood & Landslide in Java	22

5.2.1.	Scenario Description	22

5.2.2.	Impact Analysis and Identification of Risk Reduction Measures	22

5.2.3.	CARE Prevention and Mitigation Measures	23

5.2.4.	CARE Response Strategy	24

5.2.4.1.	Goal and objectives of CARE response	24

5.2.4.2.	Geographic Focus and Target Beneficiaries	24

5.2.4.3.	Response Interventions	24

5.2.4.4.	Implementation Phases/Timeline	24

5.2.4.5.	Partnership Arrangements	25

5.2.4.6.	Key personnel requirements	25

5.2.4.7.	Relief Item requirements	25

5.2.4.8.	Logistics/Equipment Requirements	26

5.2.4.9.	Trigger Indicators	26

5.2.4.10.	Key issues/challenges affecting CARE response	26

5.2.4.11.	Entry and Exit/Transition Strategy	27

5.2.4.12.	Funding requirements-summary budget	27

5.3.	Scenario 3 - Drought and Fire in NTT & Kalimantan	28

5.3.1.	Scenario Description	28

5.3.2.	Impact Analysis and Identification of Risk Reduction Measures	28

5.3.3.	CARE Prevention and Mitigation Measures	31

5.3.4.	CARE Response Strategy	34

5.3.4.1.	Goal and objectives of CARE response	34

5.3.4.2.	Geographic Focus and Target Beneficiaries	34

5.3.4.3.	Response Interventions	34

5.3.4.4.	Implementation Phases/Timeline	35

5.3.4.5.	Partnership Arrangements	35

5.3.4.6.	Key personnel requirements	36

5.3.4.7.	Relief Item requirements	36

5.3.4.8.	Logistics/Equipment Requirements	37

5.3.4.9.	Trigger Indicators	37

5.3.4.10.	Key issues/challenges affecting CARE response	38

5.3.4.11.	Entry and Exit/Transition Strategy	38

5.3.4.12.	Funding requirements-summary budget	38

5.4.	Scenario 4 – Floods in Sulawesi	39

5.4.1.	Scenario Description	39

5.4.2.	Impact Analysis and Identification of Risk Reduction Measures	39

5.4.3.	CARE Prevention and Mitigation Measures	40

5.4.4.	CARE Response Strategy	40

5.4.4.1.	Goal and objectives of CARE response	40

5.4.4.2.	Geographic Focus and Target Beneficiaries	40

5.4.4.3.	Response Interventions	40

5.4.4.4.	Implementation Phases/Timeline	40

5.4.4.5.	Partnership Arrangements	41

5.4.4.6.	Key personnel requirements	41

5.4.4.7.	Relief Item requirements	41

5.4.4.8.	Logistics/Equipment Requirements	42

5.4.4.9.	Trigger Indicators	42

5.4.4.10.	Key issues/challenges affecting CARE response	43

5.4.4.11.	Entry and Exit/Transition Strategy	43

5.4.4.12.	Funding requirements-summary budget	43

6.	Management Considerations and Gap Analysis	44

6.1.	Key Personnel Requirements	44

6.2.	Assessment and Analysis	44

6.3.	Design, Monitoring and Evaluation	45

6.4.	Human Resource Unit	46

6.5.	Finance	47

6.6.	Administration	48

6.7.	Procurement	49

6.8.	Program Logistics	50

6.9.	Information Technology and Telecommunications	52

6.10.	Safety and Security	52

6.11.	Fundraising	52

6.12.	Media	53

6.13.	Information Management	54

7.	Action Plans	56

# Executive Summary

To be completed after the finalisation of all other parts, and to provide the following information (1-2 pages):

- When this EPP was completed

- Who participated in this EPP design

- General structure of the Emergency Response in the CO: such as an number of ERT members in the HQ, location of ERTs in the Field Offices, etc

- Insert Country Map (replace with a better map, if available

- What are the key disaster scenarios considered and for which timeframe

- What are the elements of CARE response strategies for those disaster scenarios

- What are the funding and other requirements to successfully implement these strategies

# Formation of Emergency Response Team

ERT in Jakarta

| ERT Function | Title, and Name of the Staff | Title and Name of Back Up | Preparedness Responsibilities | Response Responsibilities |
| --- | --- | --- | --- | --- |
| Emergency Response Coordinator | Johan Kieft | Heather Van Sice | 1-2 key responsibility | 1-2 key responsibility |
| Field Coordinator | Fachrurrazi | To be identified | 1-2 key responsibility | 1-2 key responsibility |
| Logistics / Procurement | Bambang/Purwanti | Swesty | 1-2 key responsibility | 1-2 key responsibility |
| Information Management | Wiwik/Ema | Nita | 1-2 key responsibility | 1-2 key responsibility |
| Security | Abdulmalik | To be identified | 1-2 key responsibility | 1-2 key responsibility |
| Administration | Purwanti | Rahayu | 1-2 key responsibility | 1-2 key responsibility |
| Human Resources | Nilawaty | To be identified | 1-2 key responsibility | 1-2 key responsibility |
| Finance | Linda | Sihol | 1-2 key responsibility | 1-2 key responsibility |
| IT and Telecommunication | Santanu | Aries | 1-2 key responsibility | 1-2 key responsibility |
| Media | Wiwik | Ety | 1-2 key responsibility | 1-2 key responsibility |
| Fundraising (Program design/proposal writing) | Johan/Heather | Fachrurrazi | 1-2 key responsibility | 1-2 key responsibility |
| Government Liaison | Bahtra | Sihol | 1-2 key responsibility | 1-2 key responsibility |
| Field Office Representative | Aris (Btn) Tonny(WT) Fatur(CK) Jon(Sim) Sajedul(NAD) Abdulnasser(MKS) JonnyThomas(Gor) Sudarto(MND)/ Boyke(Jog_CJ) | Marcel (Btn) Dus(WT) Ois(CK) Jordan(Sim) Nasrul(NAD) Chaidir(MKS) Baso(Gor) tbd(MND) tbd(Jog_CJ) | 1-2 key responsibility | 1-2 key responsibility |
| Technical Specialist | Facrurrazi – DRR&EH Pietra W – Livelihood&Early Recovery Kusuma Hartani – Health Partners ITB/CDC/IRI/KO |  | 1-2 key responsibility | 1-2 key responsibility |

ERT Banteen

| ERT Function | Title, and Name of the Staff | Title and Name of Back Up | Preparedness Responsibilities | Response Responsibilities |
| --- | --- | --- | --- | --- |
| Emergency Response Coordinator | Frank C. Page | Maria Aruan | 1-2 key responsibility | 1-2 key responsibility |
| Field Coordinator | Aris Buhari | Marcel Beding | 1-2 key responsibility | 1-2 key responsibility |
| Logistics | Frans Herlawinardi | Ariyanto Lenggu | 1-2 key responsibility | 1-2 key responsibility |
| Procurement | Anggi Mahfud Arifin | Mahfud | 1-2 key responsibility | 1-2 key responsibility |
| Information Management | Frank C. Page | Maria Aruan | 1-2 key responsibility | 1-2 key responsibility |
| Security | Eko Pranandhita | Rosalia E. T. Widyastuti | 1-2 key responsibility | 1-2 key responsibility |
| Administration |  |  | 1-2 key responsibility | 1-2 key responsibility |
| Human Resources |  |  | 1-2 key responsibility | 1-2 key responsibility |
| Finance | Bagio Kurniawan | Tommy Hilwawan | 1-2 key responsibility | 1-2 key responsibility |
| IT and Telecommunication | Doni Ramanto Efendi | David Elven | 1-2 key responsibility | 1-2 key responsibility |
| Media | Frank C. Page | Maria Aruan | 1-2 key responsibility | 1-2 key responsibility |

ERT - JH

| ERT Function | Title, and Name of the Staff | Title and Name of Back Up | Preparedness Responsibilities | Response Responsibilities |
| --- | --- | --- | --- | --- |
| Emergency Response Coordinator | Head of Programmes Simeulue, Jon Ward | Program Manager, Jordan Hoffmann | 1-2 key responsibility | 1-2 key responsibility |
| Field Coordinator | Alafan Area Manager, Jupriansyah Teupah Selatan Area Manager, Purnomo Agus Priyanto | CCF Alafan, Rohadi CCF Teupah Selatan, Leo Dwikora | 1-2 key responsibility | 1-2 key responsibility |
| Logistics / Procurement | Procurement Specialist, Pam and/or Procurement Officer Medan, Andreas | SCM and Safety and Security Manager, Edi Cahyadi and/or Office Manager Medan, Robertin Sinaga | 1-2 key responsibility | 1-2 key responsibility |
| Information Management | Database Manager, Dwi Wahyuni | Database Assistant, Vendra Harfana | 1-2 key responsibility | 1-2 key responsibility |
| Security | SCM and Safety and Security Manager, Edi Chayadi | Security Guard Leader, Agus Reynaldi | 1-2 key responsibility | 1-2 key responsibility |
| Administration | Administration Manager, Ruri Haryanto | Admin Supervisor, Erna Fitriana | 1-2 key responsibility | 1-2 key responsibility |
| Human Resources | HR Supervisor, Hafni Ritazli | HR Assistant, Irma | 1-2 key responsibility | 1-2 key responsibility |
| Finance | Finance Manager, Haryanto Ginting | Finance Officer, Zilfikar | 1-2 key responsibility | 1-2 key responsibility |
| IT and Telecommunication | Radio/IT Supervisor, Yoni Yumono | Radio/IT Officer, Abdiatul Badri | 1-2 key responsibility | 1-2 key responsibility |
| Media | Head of Programmes, Jon Ward | Program Manager, Jordan Hoffmann | 1-2 key responsibility | 1-2 key responsibility |
| Fundraising (Program design/proposal writing) | Program Manager, Jordan Hoffmann | Health Advisor, Lenore Chrisostomo | 1-2 key responsibility | 1-2 key responsibility |
| Government Liaison | DRR Specialist, Yuli Sari Yeni | TPO DRR, Nurdianawaty | 1-2 key responsibility | 1-2 key responsibility |
| Technical Specialists | Livelihoods Specialist, Akhmad Arif, Watsan Specialist, Fabianus Ndapa, Health Advisor, Lenore Chrisostomo | TPO VSL, Suwajib, TPO Watsan, Dedy Fresly Damanik, Health Specialist, Fachmi | 1-2 key responsibility | 1-2 key responsibility |

ERT - WT

| ERT Function | Title, and Name of the Staff | Title and Name of Back Up | Preparedness Responsibilities | Response Responsibilities |
| --- | --- | --- | --- | --- |
| Emergency Response Coordinator | To be identified | To be identified | To be identified | To be identified |
| Field Coordinator | Tonny Bengu | Wilfridus Nahak/Marthen Malo | To be identified | To be identified |
| Logistics / Procurement | Otje Taopan | Hermin | To be identified | To be identified |
| Information Management | Gabriel Bina | Neni | To be identified | To be identified |
| Security | Gabriel Bina | Ivony Fuah | To be identified | To be identified |
| Administration | Neni | Maria Yosephina | To be identified | To be identified |
| Human Resources | Ivony Fuah | Neni | To be identified | To be identified |
| Finance | Selvi P | Pauline Djaga | To be identified | To be identified |
| IT and Telecommunication | Tri | Milson B | To be identified | To be identified |
| Media | Dani W | Milson | To be identified | To be identified |
| Fundraising (Program design/proposal writing) | Johan Kieft | Fachrurrazi | To be identified | To be identified |
| Government Liaison | Ludovikus K | Gabriel Bina | To be identified | To be identified |
| Field Office Representative | Andrew (Belu) Caecilia Sadipun (TTU) Ferdi Adoe (TTS) Yeremias Pandegani (Kupang) | Dr. Aking/Yohanis Mungga (Belu) Jhon Lory/ (TTU) Ois(CK) Agus Undji (TTS) Theo Da Costa | To be identified | To be identified |
| Technical Specialist | Facrurrazi – DRR&EH Pietra W – Livelihood&Early Recovery Kusuma Hartani – Health Partners ITB/CDC/IRI/KO | Andrew Winokan (TPO Livelihood & Government) Frans Pello (specialist health) Yosep Leki (PO GIS) | To be identified | To be identified |

ERT – BA – TO BE DEVELOPED

# Information Requirements

Ema, please list all the information you and others collected for the EPP, such as:

- Information from the EM-DAT website

- Lessons Learned from Previous emergencies

- Disaster Risk Mapping,

- Others

# Country Office Capacity Inventory

## Country Office Organization Chart

Insert the current Country Office Organization Chart here

## Country Office Human Resources

TO BE COMPLETED BY:

Who:

Sim : Jordan

Jkt: Abdulmalik

Banten: Eko

NTT: Tonny

CK: Fatur

NAD: Sajedul

Sulawesi: Abdulnasser

When: 14 March, 2008

| Function or Sector | Number of Staff | Name of Staff | Positions of Staff |
| --- | --- | --- | --- |
| Program functions |  |  |  |
| National Emergency Coordination |  |  |  |
| Food Security Early Warning |  |  |  |
| Political Early Warning |  |  |  |
| Emergency Assessment |  |  |  |
| Project Design |  |  |  |
| Camp Management |  |  |  |
| Warehouse & Logistics |  |  |  |
| Distribution of Food & Non-food |  |  |  |
| Supplementary & Therapeutic Feeding |  |  |  |
| Primary Health Care |  |  |  |
| Reproductive Health |  |  |  |
| Water & Sanitation |  |  |  |
| Shelter |  |  |  |
| Road & Infrastructure Construction |  |  |  |
| Social Services |  |  |  |
| Environmental Protection & Management |  |  |  |
| Humanitarian Protection |  |  |  |
| Staff Security |  |  |  |
| Advocacy |  |  |  |
| Conflict Sensitivity |  |  |  |
| Other: |  |  |  |
| Other: |  |  |  |
| Support functions |  |  |  |
| Staff Recruitment: |  |  |  |
| Staff Payroll: |  |  |  |
| Procurement: |  |  |  |
| Inventory: |  |  |  |
| Transport: |  |  |  |
| Vehicle Management: |  |  |  |
| Finance: |  |  |  |
| Staff Psycho Social Support |  |  |  |
| Commodity Management: |  |  |  |
| Communications/Radio |  |  |  |
| Other: |  |  |  |

## Country Office Physical Resources

TO  BE COMPLETED BY:

Who: Abdulmalik

When: March 14, 2008

| Item # | Asset Description | Number of assets per each office (indicate name of sub-office) | TOTAL |
| --- | --- | --- | --- |
| 1 | Offices |  |  |  |  |  |  |  |  |  |
| 2 | Guesthouses |  |  |  |  |  |  |  |  |  |
| 3 | Light Vehicles 2WD |  |  |  |  |  |  |  |  |  |
| 4 | Light Vehicles 4WD |  |  |  |  |  |  |  |  |  |
| 5 | Trucks |  |  |  |  |  |  |  |  |  |
| 6 | Motorcycles |  |  |  |  |  |  |  |  |  |
| 7 | Computers |  |  |  |  |  |  |  |  |  |
| 8 | HF Radios - base stations |  |  |  |  |  |  |  |  |  |
| 9 | HF Radios – mobile |  |  |  |  |  |  |  |  |  |
| 10 | VHF Radios – Base Stations |  |  |  |  |  |  |  |  |  |
| 11 | VHF Radios - Mobile Units |  |  |  |  |  |  |  |  |  |
| 12 | VHF Radios - Handhelds |  |  |  |  |  |  |  |  |  |
| 13 | VHF Repeaters |  |  |  |  |  |  |  |  |  |
| 14 | Generators |  |  |  |  |  |  |  |  |  |
| 15 | Satellite phones |  |  |  |  |  |  |  |  |  |
| 16 | Mobile Phones |  |  |  |  |  |  |  |  |  |
| 17 | Printers |  |  |  |  |  |  |  |  |  |
| 18 | Photocopiers |  |  |  |  |  |  |  |  |  |
| 19 | Fax Machines |  |  |  |  |  |  |  |  |  |
| 20 | Water Drilling Rigs |  |  |  |  |  |  |  |  |  |
| 21 | Backhoe |  |  |  |  |  |  |  |  |  |
| 22 | Water Tanks |  |  |  |  |  |  |  |  |  |
| 23 | Water Bladders |  |  |  |  |  |  |  |  |  |
| 24 | Portable Warehouses |  |  |  |  |  |  |  |  |  |
| 25 | Tents for Beneficiaries |  |  |  |  |  |  |  |  |  |
| 26 | Other (specify) |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  |  |  |  |  |

## Country Office Key Staff Contact Information

Who: Abdulmalik

When: March 14, 2008

| Position | Name | Telephone | Email | Radio Call Sign |
| --- | --- | --- | --- | --- |

## RMU, CARE Lead Member, and CARE International Key Contacts

Who: Ema

When: March 14, 2008

| Office | Position | Name | Telephone | Email |
| --- | --- | --- | --- | --- |

## In Country Coordination Mechanisms and Contacts (GoI, local Partner, satkorlak, Bakornas, NGO/INGPO, UN Body)

Who: Fachrurrazi

When: March 14, 2008

| Organization | Position | Name | Telephone | Email |
| --- | --- | --- | --- | --- |

# Risk Analysis

Historical disasters in the country for the past fifty years:

| Area | Disasters | Frequency and Impact |
| --- | --- | --- |
| Sumatra | Earthquake | Every year for the past 20 years |
|  | Tsunami | 1907 and 2004 |
|  | Flood | Every year in the rainy season, 1 major impact in 2003, 2004, 2005, 2006, 2007?? |
|  | Landslide | Every year in the rainy season, 1 major impact in 2003?? |
|  | Social conflict | NAD since 1968, big from 1999 to 2004 |
|  | Forest fires | Every year for past 20 years, 2003?? |
| Java | Banjir, Earthquake Lapindo Mud Eruption Avia Flu Disease (Deman berdarah Dengue) Tsunami Landslide Ulat Bulu. Drought Wedus gembel Cold lava Riot, Volcano eruption Poisonous Gas from the volcano Monetary Crises | B. Solo (2007, 2008, 65/66)( wonogiri, solo, ngawi, bojonegoro, tuban, pati, Jakarta, Situbondo 2006, Jogjakarta East Java Pangandaran, Banyuwangi (1994) Tawang mangu (lawu tua sudah rentan) Indramayu( perubahan iklim 1967, 2007, 2003 ( gunung kidul, pantai utara G. Merapi 1994, G. Kelud 1989, G. Merapi, 2006 1998 G. Galunggung, 1980an G.Dieng Since 1997-now |

Note:

Based on the frequency, the ranks are:

- Floods,

- Drought,

- Penyakit,

- Longsor,

- gempa,

- Waves/rob,

- hightide,

- volcanos

Based on the impact, the ranks are:

- Volcano,

- Earthquake,

- Landslide,

- Floods,

- Disease,

- Waves,

- High tide,

- Drought

| NTT & Kalimantan | Drought, Fire, Flood, Low level of Nutrion, epidemic diseases (DBD, Malaria), Volcano eruption, Smoke, Storm, Social Conflict, Tsunami, Extreme Temperature | These disasters are always happened every year, like the routine for NTT and Kalimantan. Drought is affected almost every areas in NTT, more than 30% children are underweight, and have nutritional crises. Upon 12-18 months later still going to be happened. |
| --- | --- | --- |

| Sulawesi | Flood, every year in Central Sulawesi, Gorontalo, and North. It’s all combination effect from heavy rain and seawater. Flood in Maluku because of many river there were used to build houses and buildings. Earthquake: Central Sulawesi, Maluku (Somlake), Gorontalo, and North Sulawesi. Conflict: Maluku, South Sulawesi (causes: conflict of multi ethnic and fanatism of race or religion), Southeast Sulawesi (Number of refugees from Maluku is more than native people), Central Sulawesi. Volcano, North Sulawesi, (2 active mountain in Tomohon), Sangir Talaut, North Maluku (G. Gamalama). Drought: Central Sulawesi, Maluku (Northwest Maluku: Tual). These disasters are the most affected to people, impact to IDP and lives of people. Conflict in Maluku, Central Sulawesi: Conflict in Ambon can be spreading to central Sulawesi because of Moslem IDP move to P.Buton, and the Christian move to Manado. |
| --- | --- |

All potential disasters in country within the next 12-18 months:

| Area | Disasters | Frequency and Impact |
| --- | --- | --- |
| Sumatra | Earthquake | Every bloody month, 50,000 people at least |
|  | Tsunami | High probability, more than 100,000 people affected |
|  | Forest fires | High probability, particularly Riau and Bengkulu, within provinces only |
|  | Social conflict | High prob in NAD, if happens, big spread within NAD |
|  | Flood | High prob, medium impact |
|  | Landslides | High prob, medium impact |
| Java | All the disasters that was happened in the past will still happen in the future. |
| NTT & Kalimantan |  |
| Sulawesi |  |

Top potential disasters in terms of frequencies and impact on lives, livelihoods, and economies:

Sumatra: Earthquake/Tsunami

Java: Flood and landslide

NTT and Kalimantan: Drought and Fire

Sulawesi: Flood

The EPP team therefore decided to develop one top risk level scenario per each region, as follows:

Group 1 (Sumatera Reg) (Scenario: Earthquake/Tsunami.

Group members: Sajedul, Jordan, Wiwik, Nasrul, Yuli

Group 2 (Java Reg) – Scenario: Flood & Landslide.

Group members: Santanu, Marcel, Linda, Boyke, Rahayu, Swesty, Wiwid, Nila

Group 3 (NTT & Kalimantan Reg) ( Scenario: Drought and Fire

Group members: Johan, Dwi, Sentis, Tony, Dus

Group 4 (Sulawesi Reg)( Scenario: Floods

Group members: Fachrurrazi, Heather, Abdulmalik, Eko, Bambang, Ari, Ema

# Scenario Development

## Scenario 1 - Earthquake/Tsunami in Sumatra

### Scenario Description

Sumatera is situated between Indo-Australia and Pacific continental shelves.  It is most likely that along the West Sumatera coast, between Simeulue and Nias islands, a large earthquake will occur (above 7.5 on the Richter scale – vertical movement) , causing a 5 metre high wave that hits the south-west coast of Simeulue, north-east and north-west coasts of Nias and the west coast of Sumatera from South Aceh to West Sumatera.  The affected areas would be along the coast of South Aceh, Simeulue, Nias, West Sumatera, Bengkulu and North Sumatera.

It could happen at any time, with a quick impact and within 24 hours damage would have occurred.  Due to experience of communities along the west coast, the likelihood of large numbers of casualties as a result of either the earthquake or the tsunami would be about 2,000 people, with numbers of casualties rising depending on whether this occurs: higher during night-time, and lower during the daytime.  The community is not too vulnerable to casualties, due to experience, however, livelihoods, assets, shelter and support services from the government are extremely vulnerable as all infrastructure and services are old.

Number of people affected would be more than 1 million, facing the majority of infrastructure, including roads, electricity, communications, bridges, buildings and individual houses destroyed. Livelihoods assets would be swept away, and agricultural land ruined by the tsunami.  Erosion and destruction of the beaches and coral reefs would be high. The percentage of women and children on average in the region is 70% of the population.

Immediate needs of the affected population would be food, non-food items, shelter, replacement of livelihoods assets and recovery of essential government services and infrastructure. Key constraints would be transportation and communication access to IDP sites, shelter for essential services, technical experience in all services, rescue equipment and ships.

Typology:

- Earthquake/Tsunami

Severity Level:

Very serious

Immediate Impact:

Total number of affected population:	1 million people

Number of affected population in CARE working areas: 88,000

Children (% of affected pop.): 	30%

Women (% of affected pop.):  	40%

Number of Deaths: 			2-3,000 people

### Impact Analysis and Identification of Risk Reduction Measures

| Impact on Social, Economy, Infrastructure and Environment | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Population migrations | Higher earthquake-resistance in building code | Predetermined evacuation centres, with proper water and sanitation facilities | Providing immediate shelter options, with water and sanitation facilities | Rebuilding of earthquake-resistant housing with water and sanitation facilities |
| Decline in food production and disrupted food supply | Support the establishment of fields in safe areas from tsunamis | Support stocking of emergency food by communities at evacuation points/safe areas | Provide and distribute food | Provide and distribute seeds, tools and other livelihoods assets lost |
| Water supplies | Building water supply systems that are resistant to earthquakes | Awareness raising in vulnerable communities of safe drinking water. Identify alternative water sources | Distribution of jerry cans and SWS and/or clean water | Repair and rebuild water supply systems |
| Transportation system | Consider earthquake and tsunamis in placement and building of roads, bridges, jetties | Support communities to determine evacuation and alternative routes | Create emergency access roads, bridges and jetties | Repair and rebuild roads and bridges |
| Telecommunications system | Build earthquake and tsunami-resistant telecommunication systems | Establish common use of community radio for information sharing. Extension of telecommunication systems to all earthquake prone areas. | Distribute AM/FM radios. Repair radio stations/towers. Put in portable VSAT. |  |
| Power supply | Build earthquake and tsunami-resistant power supply systems. Create alternative energy sources. | Provide training to power supply officers on response to earthquakes. | Distribute torches, generators, laptops, batteries, etc. Repair power supply system |  |
| Costs and losses to agricultural producers | Support the establishment of fields in safe areas from tsunamis | Support the establishment of fields in safe areas from tsunamis |  | Replacement of lost assets, financial support for re-starting production |
| Conflicts over water, land and other resources | Ensure community and individual ownership of water, land and other resources is clear and documented | Ensure community and individual ownership of water, land and other resources is clear and documented | Conduct open discussions and legal processes for solving issues | Ensure community and individual ownership of water, land and other resources is clear and documented |
| Sea erosion of soils, reduced soil quality | Build dykes and drainage in vulnerable areas | Build dykes and drainage in vulnerable areas | Ensure drainage of sea water from land |  |

### CARE Prevention and Mitigation Measures

Activities that CARE can focus on or implement in its current or upcoming projects.

| Impact | Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible person |
| --- | --- | --- | --- | --- |
| Population migrations | Advocate for higher earthquake-resistance in building code Predetermined evacuation centres | Simeulue Island Program (DRR) Aceh Shelter Project Government Liaison | June 2008 | Yuli Sari Yeni Bahtra Tarigan Sajedul |
| Decline in food production and disrupted food supply | Support the establishment of fields in safe areas from tsunamis Support stocking of emergency food by communities at evacuation points/safe areas | Simeulue Island Program (Livelihoods & DRR) | December 2008 | Akhmad Arif |
| Water supplies | Awareness raising of vulnerabilities of water supply systems to earthquakes Awareness raising in vulnerable communities of safe drinking water. Identify alternative water sources | Health and ACCESS projects in Aceh Simeulue Island Program (Watsan & Health) | Ongoing | Jeff Franklin Fabianus Ndapa Lenore Chrisostomo |
| Transportation system | Support communities to determine evacuation and alternative routes | Simeulue Island program (DRR) Aceh Shelter Project | May 2008 Done | Yuli Sari Yeni |
| Telecommunications system | Advocate for government policies of earthquake and tsunami-resistant telecommunication systems Advocate for common use of community radio for information sharing | Simeulue Island program (DRR) Aceh psychosocial project Simeulue Island program (Livelihoods) | June 2008 | Yuli Sari Yeni Bahtra Tarigan Guntur Akhmad Arif |
| Power supply | Advocate for government policies of earthquake and tsunami-resistant power supply systems. Create alternative energy sources. | Government Liaison | June 2008 | Bahtra Tarigan |
| Costs and losses to agricultural producers | Support the establishment of fields in safe areas from tsunamis | Simeulue Island Program (Livelihoods) Aceh Livelihoods Program | December 2008 Done | Akhmad Arif |
| Conflicts over water, land and other resources | Ensure community and individual ownership of water, land and other resources is clear and documented | Simeulue Island Program (Gov Liaison) Government Liaison | June 2008 | Jordan Hoffmann Bahtra Tarigan |
| Sea erosion of soils, reduced soil quality | Build dykes and drainage in vulnerable areas | Simeulue Island Program (Watsan) | December 2008 | Fabianus Ndapa |

### CARE Response Strategy

#### Goal and objectives of CARE response

Emergency response project:

Goal - Provide immediate basic emergency assistance to people affected by the earthquake or tsunami

Objective 1 – Provide food and non-food items to affected people

Objective 2 – Provide temporary shelter, water and sanitation facilities to affected people

Objective 3 – Provide required temporary infrastructure for affected people

Recovery and rehabilitation project:

Goal - Assist people affected by the earthquake or tsunami in recovering their shelter, livelihoods, infrastructure and services

Objective 1 – Rebuild safe and hygienic shelters for affected people

Objective 2 – Support affected people in recovering their livelihoods

Objective 3 – Ensure basic infrastructure rehabilitation for affected people

Objective 4 – Ensure recovery and strengthening of community services for affected people

#### Geographic Focus and Target Beneficiaries

| Geographic Area | Total Number of beneficiaries | CARE Target Beneficiaries Emergency Recovery |
| --- | --- | --- |
| Simeulue | 88,000 | 8,000 | 5,000 |
| Bengkulu | 200,000 | 60,000 | 20,000 |
| South Aceh | 100,000 | 50,000 | 5,000 |
| West Sumatera | 500,000 | 150,000 | 50,000 |
| North Sumatera | 300,000 | 150,000 | 50,000 |

#### Response Interventions

Seems too many – would be good to focus on a few

Emergency project: Water, Sanitation, Shelter, Non Food Items, Food Aid, Temporary Infrastructure

Recovery and Rehabilitation project: Water, Sanitation, Economic Development Livelihoods, Health and Nutrition, Shelter, Community Planning, Community Radio

#### Implementation Phases/Timeline

Emergency project : 3-6 months

Recovery and Rehabilitation project : 2 years

#### Partnership Arrangements

| Organisation | Typical Role in Emergency | Existing Relationship with CARE | Expected/Required relationship with CARE | Action to improve relationship |
| --- | --- | --- | --- | --- |
| Ulayat (Bengkulu) | Collecting data, assessment, distributions, community facilitation | Unofficial partner | Formal partnership | Joint planning, capacity building for staff |
| South Aceh local NGO – must find | Collecting data, assessment, distributions | Tbd | tbd | Joint planning, capacity building for staff |
| Simeulue local NGO – must find (PMI?) | Collecting data, assessment, distributions, community facilitation | Tbd | Tbd | Joint planning, capacity building for staff |
| West Sumatera – P2SD | Collecting data, assessment, distributions, community facilitation | Unofficial partner | Formal partnership | Joint planning, capacity building for staff |
| North Sumatera – Yakmi | Collecting data, assessment, distributions, community facilitation | Official partner | Formal partnership | Joint planning, capacity building for staff |
| North Sumatera - Yayasan Karang | Collecting data, assessment, distributions, community facilitation | Official partner | Formal partnership | Joint planning, capacity building for staff |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Can the position be filled with the existing staff? |
| --- | --- |
|  | If YES - Name and Current Position of the staff | If NO – Actions needed to identify and recruit |
| Project Manager | To be identified |  |
| Procurement Officer | To be identified |  |
| Warehouse Manager | To be identified |  |
| Distribution Manager | To be identified |  |
| Assessment Team Manager | To be identified |  |
| Finance Manager | To be identified |  |
| Inspection Officer | To be identified |  |
| Radio/IT Officer | To be identified |  |
| Government Liaison Coordinator | To be identified |  |
| Office Manager | To be identified |  |
| M&E Officer | To be identified |  |
| Media Officer | To be identified |  |
| Information Management Officer | To be identified |  |
| Security Officer | Nazrul – Guard Officer |  |
| Recovery, but arrives at first: | To be identified |  |
| Livelihoods Specialist | Akhmad Arif – Livelihoods Specialist |  |
| Watsan Specialist | Jeff Franklin – Watsan Specialist |  |
| Shelter Specialist |  |  |
| Comm Engagement Specialist | To be identified |  |
| DRR Specialist | Yuli Sari Yeni – DRR Specialist |  |

#### Relief Item requirements

| Item description | Unit Measure | Quantity Required | Potential Sourcing (Local Purchase, International Purchase, Available from partner, etc) |
| --- | --- | --- | --- |
| Food items: |  |  | From WFP? |
| Tents | 4X4 M | 104,500 | Medan |
| Hygiene kit | Packet | 104,500 | Medan |
| First aid kit | Packet | 104,500 | Medan |
| Generator | Unit | 18 | Medan |
| Jerry Can | Pcs | 104,500 | Medan |
| Radio with batteries | Packet | 104,500 | Medan |
| Chainsaw and safety equipment | Packet | 66 | Medan |
| SWS | Pcs | 313,500 | Medan |
| Kitchen set | Packet | 104,500 | Medan |
| Blue box | Packet | 104,500 | Medan |
| Aqua gallon | Unit | 104,500 | Medan |
| Rope | Metres | 660 | Medan |
| Nails | Kg | 660 | Medan |
| Hammer | Pcs | 66 | Medan |
| Shovel | Pcs | 26,125 | Medan |
| Cement | Bags | 78,375 | Medan |
| Plastic Slabs | Pcs | 26,125 | Ask UNHCR? |
| Timber 4x7x10 | Metres | 52,250 | Make sure environmentally friendly |

#### Logistics/Equipment Requirements

| Items per locations | Quantity Needed | Is this available in the Country Office? |
| --- | --- | --- |
|  |  | If YES – identify project/location/status | If NO – Actions required to identify items |
| Office | 5 | 1 office in Medan 1 office in Simeulue | 3 offices (West Sumatera, South Aceh, Bengkulu) Fully equipped tents/prefabricated containers Create basic design and then find vendor in Indonesia |
| Guesthouse | 4 | 1 guesthouse in Simeulue | 3 guesthouses (West Sumatera, South Aceh, Bengkulu) Fully equipped tents/prefabricated containers. Create basic design and then find vendor in Indonesia |
| Warehouse | 4 |  | Rubbhall. Vendor from outside Indonesia |
| Vehicles for staff | 6 10 | Cars: BA? Motorbikes: 5 spare in Simeulue | Cars: Rent from Medan. Motorbikes: buy/rent from Medan |
| Transportation of relief items | 60 1 | 15 tonne trucks: rent from Medan/Bengkulu/South Aceh/Simeulue 70 tonne ship in Simeulue | Identify vendors in Medan, South Aceh for truck rental |
| Computers | 19 | Each CARE staff has computer |  |
| Sat Phones | 2 | In CARE Simeulue office |  |
| Radios | 2 | Codan radios in Simeulue |  |

#### Trigger Indicators

| Indicator | Critical Values | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible for monitoring |
| --- | --- | --- | --- | --- | --- |
| No need for earthquake |  |  |  |  |  |

#### Key issues/challenges affecting CARE response

| Dimension | Challenge / Consideration (if ANY) | Recommendation |
| --- | --- | --- |
| Language | Not considered an issue |  |
| Culture | Not considered an issue |  |
| Ethnic tensions | Not considered an issue |  |
| Sectarian violence | Not considered an issue |  |
| Security | Throughout all areas, there are issues of poverty that could cause those not receiving assistance to attack CARE distributions. Aftershocks could occur, hurting staff | Make no promises to communities. Work closely in terms of security with local partners. Hold discussions/conduct socialisation with all surrounding communities and community leaders to explain the purpose of the project. Provide key messages on earthquake awareness. |
| Local Government | Unclear and complicated bureaucracy, slow response, low capacity | Identify one contact person to liaise with the local government bodies to ease processes |
| Economy | Inflation, rising prices | Put high inflation calculations into budget. Purchase materials fast, with predetermined vendors or have ready stock |
| Infrastructure | Access and transportation issues due to damaged roads and high demand for trucks | Predetermined vendor for renting of trucks and put chainsaw in every car. |
| Local Organisations | Miscommunication and mistakes in finance and documentation | Joint planning and capacity building of local NGO staff beforehand |
| International Organisations | Overlapping of beneficiaries | Coordination meetings between all international organisations, including INGOs and with government |
| Regional implications | Not considered an issue |  |

#### Entry and Exit/Transition Strategy

To be completed

#### Funding requirements-summary budget

To be completed

| No. | Item description | Unit Measure | No of Units | Unit Cost (US$) | Total Cost (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | STAFF SALARIES & BENEFITS |  |  |  |  |
| 2 | TRAVEL & LODGING |  |  |  |  |
| 3 | RELIEF ITEMS |  |  |  |  |
| 4 | HANDLIN/TRANSPORTATION |  |  |  |  |
| 5 | OPERATING/SUPPORT COSTS |  |  |  |  |
| 6 | SHARED COSTS |  |  |  |  |
| 7 | ICR |  |  |  |  |
| 8 | TOTAL FUNDING REQUIREMENTS |  |  |  |  |

Number of Beneficiaries:

Cost per Beneficiary:

## Scenario  - Flood & Landslide in Java

### Scenario Description

What :

Flood/Landslide (Banjir atau tanah longsor).

Why:

- penebangan hutan,

- daerah resapan yang sudah berkuran perilaku manusia.

Where:

Jabodetabek

Jawa tengah

Jawa Timur

When:

Nov-April, Pucak buan Februari. populasi yang akan kena 2-8 juta (seluruh jawa) jabotabek (200-300 ribu).

Vulnerable community

Anak 30% dan ibu2/perempuan 20%. Banjir dan longsor sedikit lebih punya dampak hanya beberapa saat tidak panjang waktunya (dalam 1 bulan sudah bisa dicover).

Capacity to cope :

Untuk sementara korban akan pindah ke saudara, gereja maupun komunitas. Akses komunitas sudah lebih baik, kaena makanan sudah tersedia, sudah biasa dilakukan. Tapi kalau yang diluar Jakarta, masalah/dampaknya akan lebih lama. Dampaknya: penyakit, gagal panen (daerah jawa), kehilangan mata pencaharian, water and sanitation

Typology : Type FLOOD

Severity Level : Serious

### Impact Analysis and Identification of Risk Reduction Measures

| Impact on Social | Prevention | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- | --- |
| Disease Outbreak |  | Health education Medicine Stock Advocating government | Medicine stock Training for Health Staff | Medicine distribution Water Distribution NFI Distribution (Hygiene Kits, etc) | Improvement in sanitation PHBS Health Post (Puskesmas) |
| Loss human life |  | First aid action knowledge Evacuation Plan | Simulation | Evacuation for dead body and other victim who is still alive Sanitation | Trauma/Psychosocial Program |

| Impact on Economy | Prevention | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- | --- |
| Cost and losses to agriculture producers |  | Reforestation Improvement in drainage system | Early warning System |  | Seed distribution |
| Decline in food production and disrupted food supply |  | Food stock Plant pattern management | Rice Stock | Food Distribution | Plant pattern management (schedule, type of plant, etc) |

| Impact on Environment | Prevention | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- | --- |
| Damage to animal species, such as reduction and degradation of fish and wildlife habitats |  | Conservation area |  |  | Conservation Area |
| Water erosion of soils |  | Reforestation land used |  |  | Reforestation |

| Impact on Infrastructure | Prevention | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- | --- |
| Road |  | Elevated road Improve drainage system | Mapping Free Flood Area | Socialization and road route map | Improvement for the road |
| House, schools health facilities and other buildings |  | Safety building Relocation |  |  | Relocation Special House design |

### CARE Prevention and Mitigation Measures

Activities that CARE can focus on or implement in its current or upcoming projects.

| Impact | Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible Person |
| --- | --- | --- | --- | --- |
| Social |  |  |  |  |
| Disease Outbreak | Health training Advocating government Sanitation PHBS | BERSIH | SEPT 2008 | Frank Page |
| Loss human life | Trauma Centre | Psychosocial |  |  |
| Economy |  |  |  |  |
| Economy agriculture lost | Micro Credit Seed fair Training about Agriculture Technology | SENSE BISMA | SEPT’2008 | Tony. S Ari |
| Decline in food production and disrupted food supply | Food stock Plant Pattern Management Early Warning Systems | BERSIH | Sept’2008 | Frank Page |
| Environment |  |  |  |  |
| Damage animal species and wildlife habitats | Conservation Area Reforestation | ALAM/Peatland/CKPP | Juni 2008 | Benjamin Tular |
| Infrastructure |  |  |  |  |
| Houses, schools and other buildings | Safety and Healthy Building | GRIYO AMAN/ALERT | April 2008 | Boyke |

### CARE Response Strategy

#### Goal and objectives of CARE response

Goal for emergency response “Saving Human Life”

Objective :

- Quick Response (Merespon lebih cepat dalam waktu 2 x 24 Jam)

- Capacity Building and Training( Meningkatkan Kapasitas Tenaga Medis )

Recovery program :

1. Protection of livelihood (Perlindungan terhadap mata Pencaharian)

Objective:

  - Increase of competencias and knowledge (Peningkatan Keterampilan & pengetahuan)

  - Micro Credit ( access permodalan )

  - To facilitated production marketing (Memfasilitasi Pemasaran Hasil Produksi)

- Promote of good environment (Peningkatan Kualitas Lingkungan)

Objective :

- Behavior Change ( Ramah Lingkungan )

- Government Advocate ( Advokasi pemerintah tentang kebijakan lingungan hidup)

#### Geographic Focus and Target Beneficiaries

| Geographic Area | Total Number of beneficiaries ( A ) | CARE Target Beneficiaries ( 10% x A ) |
| --- | --- | --- |
| Daerah aliran kali Ciliwung & Cisadane (Jakarta) | 300,000 | House hold |
| Tangerang Bekasi | 700,000 | House hold |
| Jawa Barat, Bandung, | 200.000 | House hold |
| Bogor | 50.000 | House hold |
| Daerah aliran Bengawan Solo, (Solo, Lamongan, Ngawi,Pati, Bojonegoro, Gresik, Sragen) | 1.500.000,- | House hold |
| Karang Anyar, Situbondo, Sukabumi |  | House hold |

#### Response Interventions

- Water

  - Distribution Jerrycan and Water purifier (PUR or Air Rahmat)

- Sanitation

  - Distribution of Hygiene Kits and family kits

- Shelter

  - Distribution of tarpaulin (temporary shelter)

D. Economic Development/Livelihoods

- Seed fair

- Micro finance

E. Environmental Health

- Behaviour change

- Health education

#### Implementation Phases/Timeline

| Assessment Analysis Target location Target beneficeries Action Plan Procurement Distribution Monitoring & Evaluation ( daily ) Exit strategy (depend on M&E result) | 1x24 jam 1x24 jam 1x24 jam |
| --- | --- |

#### Partnership Arrangements

| Organisation | Typical Role in Emergency | Existing Relationship with CARE | Expected/Required relationship with CARE | Action to improve relationship |
| --- | --- | --- | --- | --- |
| Local Government (Satlak, Satkorlak) | secondary data, | Base on previous ER by CARE, current project intervention area. | Coordination in ER | Capacity building in ER |
| Local NGO Kompib Yayasan Dian Desa Lakpesdam | Assesment, Distribution, | Griyo project partner | MOU Subgrant agreement | Capacity building in ER |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Can the position be filled with the existing staff? |
| --- | --- |
|  | If YES - Name and Current Position of the staff | If NO – Actions needed to identify and recruit |
| Team Leader | Yes, Fachrurrazi (DRR Program Leader) |  |
| Project Manager | Yes, optional base on location : Marcel, Aris Bukhari, Boyke |  |
| Logistic & Procurement | Bambang, Yanto Lenggu (Logistic Manager) Swesty (Procurement Officer) |  |
| Administration Personnel Finance | Potential Candidate ( Nunuk ) Maria (under certain circumtancies) – (Finance Officer) |  |

#### Relief Item requirements

| Item description | Unit Measure | Quantity Required (to start up) | Potential Sourcing (Local Purchase, International Purchase, Available from partner, etc) |
| --- | --- | --- | --- |
| Jerry Can (20 Litre ) | Unit | 50,000 | Local Purchase ( Purchase – PT. Carlina Makmur Plastikindo, serang banten for Jakarta and Tangerang ) or Local Vendor base on location (MBR) |
| PUR/Air Rahmat | Sachet /bottle | 100,000 | Local Purchase (PUR – John Hopkins Institute & Air Rahmat – PT. Ultra Salur) |
| Hygiene Kits & Family Kits | package | 50,000 | Local Purchase (General Supplier) local vendor base on location (MBR) |
| NFI (blanket & tarpaulin) | package | 50,000 | Local Purchase (Blanket – PT.B&B Indonesia for Jakarta & Tangerang) (Tarpaulin – PT. Seraya Dinamika Mandiri for Jakarta & Tangerang) and Local Vendor base on location (MBR) |

#### Logistics/Equipment Requirements

| Items per locations | Quantity Needed | Is this available in the Country Office? |
| --- | --- | --- |
|  |  | If YES – identify project/location/status | If NO – Actions required to identify items |
| Office |  |  |  |
| Guesthouse |  |  |  |
| Warehouse | 1 |  | No, Rental |
| Vehicles for staff | 1 |  | No, Rental base on location |
| Transportation of relief items | 2 |  | No, transporter or rental |
| Computers | 2 | Yes ( HQ ) |  |
| HandPhones | 2 | Yes ( HQ ) |  |
| Printer | 1 | Yes ( HQ ) |  |
| Safety Equipment (Life Jacket, Raincoat) | 10 |  | No. to be procure |

#### Trigger Indicators

| Indicator | Critical Values | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible for monitoring |
| --- | --- | --- | --- | --- | --- |
| Water Level at water gate ( Tinggi Pintu Air) – Heavy Rain | Base on Government Statement (Siaga 1,2,3) | News, Province or District Media Centre | (Manggarai, Bendungan Katulampa, Waduk Gajah Mungkur) | Every hour base on situation | Team Leader |
| Weather forecast (Prakiraan Cuaca) | Heavy Rain (Rain falls continuously) | BMG | Every Province and area in Java | Daily | Team Leader |

#### Key issues/challenges affecting CARE response

| Dimension | Challenge / Consideration (if ANY) | Recommendation |
| --- | --- | --- |
| Language | Javanese, Sundanese, | At least one of the Personnel can communicate in their languages |
| Infrastructure | Limited access to locations (road access) | Flood Area Map Contact Person in each area for information sharing |
| Local Organisations | Difference standard in Process and Procedure for Finance, Administration, Procurement and Technical arrangement | Capacity Building, Create Manual/SOP for local partnership Guidelines to select local partner Standard agreement in ER partnership with local partner |
| Local Vendors | Payment Term (Cash on Delivery), Limited Stock | Project advance, back up supply from outside disaster location |
| Personnel Mobilization | Getting suitable ER person within short time. Procedure in staff mobilization, safety security, appropriate accommodation, insurance protection, compensation. | Roaster of person, Standard ERT Compensation, accommodation and Insurance protection. |

#### Entry and Exit/Transition Strategy

- Entry Strategy

  - Coordination with local government and stake holder (presentation of our assessment and action plan)

- Exit Strategy

- Transfer knowledge and handover asset or infrastructure to local government, beneficiaries and stake holder.

- Ensure all activities well documented and final report all completed.

#### Funding requirements-summary budget

To be completed

| No. | Item description | Unit Measure | No of Units | Unit Cost (US$) | Total Cost (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | STAFF SALARIES & BENEFITS |  |  |  |  |
| 2 | TRAVEL & LODGING |  |  |  |  |
| 3 | RELIEF ITEMS |  |  |  |  |
| 4 | HANDLIN/TRANSPORTATION |  |  |  |  |
| 5 | OPERATING/SUPPORT COSTS |  |  |  |  |
| 6 | SHARED COSTS |  |  |  |  |
| 7 | ICR |  |  |  |  |
| 8 | TOTAL FUNDING REQUIREMENTS |  |  |  |  |

Number of Beneficiaries:

Cost per Beneficiary:

## Scenario 3 - Drought and Fire in NTT & Kalimantan

### Scenario Description

Presentation: NTT. Scenario: kekeringan dan banjir. Penyebab: elnino dan la nina, perubahan iklim. Tempat: dataran rendah (<500 dpl). Kapan: Sept, Oktober, Nov sampai Jan (3-5 bulan). How: gagal panen , tanaman umur panjng (terbakar), ispa (kalteng), gizi buruk (NTT). Who: petani, anak2, perempuan (NTT dan Kalteng),

NTT (1,5 juta, wanita/anak2 900 ribu) kalteng (1 juta, wanita dan anak2 600 ribu).

Seberapa parah: high vulnerable, terutama pada masyarakat yang penghasilannya murni ke lahan), High Vulnerable ( karena lahan gambut mudah terbakar ( penyebab tidak saja manusia, tapi juga suhu yang sangat panas.

Capacity to cope: NTT dan Kalteng punya pengetahuan dan pengalaman dalam mengatasi masalah kebakaran dan asap.

Strategy: NTT (Jual ternak, cari pekerjaan lain, kurang jatah makan, berhutang, merantau ke Malaysia), Kalteng (jadi buruh, sadap karet, pindah sector kerja).

Effect: livelihood (berubah mata pencaharian, merantau, ke sector jasa, pengangguran, kehilangan modal (asset, sarana produksi, finance). People (kesehatan).

Needs: NTT (makanan, obat, meningkatkan pelayanan kesehatan). Kalteng (tools( alat-alat pemadam kebakaran, masker, bibit tanaman, sarana produksi pangan, peningkatan kapasitas masyarakat (teknologi, akses informasi tentang climate, pengolahan makanan lokal).

Key constraint action: sebelum terjadi bencana (el-nino) ( dibuat market base tools dan pangan. Model penanganan/estimasi el-nino dan fire. Kebakaran dan kekeringan bisa diprediksi ( market based, model penanganan estimasi ( building kapasitas untuk vendor local.

Severity level :  2  serious

### Impact Analysis and Identification of Risk Reduction Measures

| Impact on Social, Economy, Infrastructure, and Environment | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Social : Reduced bargaining power Increased poverty in general Population migration Health status of population Diseases outbreak | Meningkatkan saving di community Bantuan langsung Tunai harus tepat waktu dan sasaran Meningkatkan ketrampilan / memberi pelatihan untuk mencari alternatif usaha lain Food for work untuk membuat embung atau jebakan api. Mempersiapkan system kesehatan yang mantap Mempersiapkan system water suplay Meningkatkan kemampuan health worker | Market based food system Data akurat dan system distribusinya. Ews-- Menyiapkan stock food, identifikasi Data atau informasi beneficiaries, stock obat. | Distribusi voucher Bantuan langsung Distribusi food Distribusi makanan dan obat-obatan | Meningkatkan system berkelompok (VS& L) Peningkatan jenis usaha baru Pengembangan livelihood..(Sesuai potensi alam) Penyadaran tentang kesehatan |
| Economy: (Droght) Income of the local household Household economy National, regional, and local economy Local businesses Price of major food items Costs and losses to agricultural producers Costs and losses to livestock producers Decline in food production and disrupted food supply Water Supplies Unemployment Reduction of economic development | Peningkatan alternative mata pencaharian lainnya Climate forecast training Meningkatkan ketrampilan Memberikan peluang mikro finance Meningkatkan jaringan terhadap pasar Meningkatkan akses ke pasar Pengelolaan air dilahan gambut Jebakan api Panen air Hujan Pengelolaan air Tanaman tahunan, konservasi Meningkatkan pertanian selaras alam (konservasi) | Market based Relief Early warning system (EWS) Identifikasi potensi sumber alam Penyediaan stock Identifikasi Pasar Food Stock (Lumbung desa) Peningkatan kapasitas masyarakat (teknologi air) | Bantuan alat (modal kerja) + sarana produksi Distribusi informasi Bantuan modal kerja Bantuan finance (modal usaha) Food voucher distribution (operasi pasar) Seed & Tools fair Food for work Cash for work | Peningkatan teknologi yang sesuai dengan perubahan iklim. Mengembangkan jaringan informasi Mengembangkan usaha pada sumber alam yang belum optimal Meningkatkan kerjasama dengan penyedia jasa/industri Meningkatkan system manajemen bisnis Peningkatan produksi Menggunakan varietas tahan kering, umur pendek, produksi tinggi, asam (pH) Pengembangan livestock sesuai agroklimat |
| Environment: Damage to animal species, such as reduction and degradation of fish and wildlife habitat. Migration and Concentration of wildlife habitat Loss of biodiversity Increased number and severity of fires Wind and water erosion of soils, reduced soil quality. Air quality effects (e.g., dust, pollutants) | Membuat kesepakatan tentang pengelolaan hasil hutan (bukan kayu) Memastikan hak atas tanah Identifikasi terhadap plasma nutfah Pemberdayaan terhadap masyarakat (enclave) Agroforestry Mengurangi daerah terbuka Peningkatan kemampuan staff kesehatan | Menyiapkan sarana Menyiapkan dokumen (MoU). Survay terhadap plasma nutfah Pembentukan masyarakat sadar api Fire control (EWS) Penyediaan obata-obatan dan sarana kesehatan lainnya (masker) Penyiapan sarana pengobatan (pengobatan berjalan) | Bantuan pada alat masak yang sifatnya minimum penggunaan kayu bakar. Memberikan bantuan alat pemadam kebakaran. Uji coba (Trial) Pemadaman /aksi pemadaman Penanaman kembali Distribusi obat-obatan and sarana lainnya. (Masker) | Rehabilitasi atau kegiatan konservasi pada hutan-hutan yang rusak/mengalami degradasi. Negosiasi kepada pemilik ulayat atau pemerintah untuk dapat mengakses lahan guna kegiatan pertanian. Pengembangan benih local unggul Penegasan tagungjawab hak dan kewajiban masyarakat Water management Reboisasi or konservasi lahan Penyadaran .(BCC) |
| Infrastructure: Transportation systems |  | Stock food | Stock food |  |

### CARE Prevention and Mitigation Measures

Activities that CARE can focus on or implement in its current or upcoming projects.

| Impact | Identified prevention and mitigation activities | Project to be integrated | Due date | Responsible Person |
| --- | --- | --- | --- | --- |
| Social : Reduced bargaining power Increased poverty in general Population migration Health status of population Diseases outbreak | Meningkatkan saving di community Market based food system Bantuan langsung Tunai harus tepat waktu dan sasaran Data akurat dan system distribusinya. Meningkatkan ketrampilan / memberi pelatihan untuk mencari alternatif usaha lain Early Warning System Food for work untuk membuat embung atau jebakan api. Mempersiapkan system kesehatan yang mantap Mempersiapkan system water suplay Meningkatkan kemampuan health worker | Nekafmese SENSE Nekaf mese, SENSE, CKPP SENSE, CKPP, Sluice SENSE, IYCF, MIAT | October 2009 February 2009 October 2009 February 2009 June 2008 October 2009 February 2009 June 2008 | PM Nekafmese Project PM SENSE Project PM CKPP, SENSE, Sluice |
| Economy: (Droght) Income of the local household Household economy National, regional, and local economy Local businesses Price of major food items Costs and losses to agricultural producers Costs and losses to livestock producers Decline in food production and disrupted food supply Water Supplies Unemployment Reduction of economic development | Peningkatan alternative mata pencaharian lainnya Climate forecast training Meningkatkan ketrampilan Memberikan peluang mikro finance Meningkatkan jaringan terhadap pasar Meningkatkan akses ke pasar Pengelolaan air dilahan gambut Jebakan api Panen air Hujan Pengelolaan air Tanaman tahunan, konservasi Meningkatkan pertanian selaras alam (konservasi) | SENSE, NEKAF MESE, CKPP NEKAF MESE, SENSE CKPP, SENSE, NEKAF MESE |  |  |
| Environment: Damage to animal species, such as reduction and degradation of fish and wildlife habitat. Migration and Concentration of wildlife habitat Loss of biodiversity Increased number and severity of fires Wind and water erosion of soils, reduced soil quality. Air quality effects (e.g., dust, pollutants) | Membuat kesepakatan tentang pengelolaan hasil hutan (bukan kayu) Memastikan hak atas tanah Identifikasi terhadap plasma nutfah Pemberdayaan terhadap masyarakat (enclave) Agroforestry Mengurangi daerah terbuka Peningkatan kemampuan staff kesehatan | SENSE, CKPP SENSE SENSE, CKPP CKPP, SENSE CKPP, SENSE CKPP, SENSE SENSE, CKPP, IYCF, MIAT AYUNGKUH, SENSE, CKPP, SLUICE |  |  |
| Infrastructure: Transportation systems |  |  |  |  |

### CARE Response Strategy

#### Goal and objectives of CARE response

Goal:

- to protect the affected community from the emergency situation (chain of hazards) where local capacities/ supports are insufficient

Melindungi masyarakat yang terdampak dari ancaman yang mungkin ditimbulkan oleh bencana yang terjadi, dimana kapasitas lokal tidak memadai.

Objectives:

1. Ensure and/ or provide standard need for the affected communities

Memenuhi standard kebutuhan minimal agar masyarakat dapat melangsungkan kehidupannya sehari-hari dalam menghadapi ancaman-ancaman yang ditimbulkan akibat kekeringan dan kebakaran.

#### Geographic Focus and Target Beneficiaries

| Geographic Area | Total Number of beneficiaries | CARE Target Beneficiaries |
| --- | --- | --- |
| Kalimantan | 1 million people | 600 thousand people |
| NTT | 1,5 million people | 900 thousands people |

#### Response Interventions

Seems too many – would be good to focus on a few

Water: Tracking and distribution of clean water for consumption

Sanitation: Hygiene kit

Non Food Items: Fire extinguisher Face-Mask

Food Aid:

Blanket food distribution (pay attention to carbohydrate, protein, vitamin, mineral contents, etc)

Health and Nutrition:

Monitor water-borne diseases and nutrition status

Ensuring that basic emergency health services are available, such as:

- Primary health service provision (e.g. mobile clinic, general examinations, reproductive health services)

- Medicines

Education: Key messages to ensure the most vulnerable groups in the affected communities are protected

Environment: Jebakan Api, check dam, using Food for Work

#### Implementation Phases/Timeline

Emergency response should be done for 3 months.

| No | Activities | Details/ remarks | Timeline |
| --- | --- | --- | --- |
| 1 | Rapid need assessment | Areas affected, Number of people affected, Problem identification that need immediate attention | Since day 1 to 1 week |
| 2 | Coordination with government (local and national) e.g. Satkorlak | Need to get clear statement of emergency from the government | Since day 1 and continues |
| 3 | Contingency planning | ERT takes charge Recruitment for site management staff | Since day 1 without waiting for Government |
| 4 | Action | Procurement and distribution of basic needs, Activities start (e.g. check dam, jebakan api (fire trap), etc) | Once government declare the emergency situation |
| 5 | Monitoring and updates |  |  |
| 6 | Recording and reporting |  |  |

#### Partnership Arrangements

| Organisation | Typical Role in Emergency | Existing Relationship with CARE | Expected/Required relationship with CARE | Action to improve relationship |
| --- | --- | --- | --- | --- |
| YTM (NTT) |  |  |  |  |
| Badan Ketahanan Pangan NTT |  |  |  |  |
| Satkorlak province |  |  |  |  |
| SatLak in district |  |  |  |  |
| HKTI (Himpunan Kerukunan Tani Indonesia) |  |  |  |  |
| Dinas Pertanian |  |  |  |  |
| Konsorsium (BOS, Wetlands, etc) |  |  |  |  |
| BKSDA Balai konservasi sumber daya alam |  |  |  |  |
| Yayasan Cakrawala (CK) |  |  |  |  |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Can the position be filled with the existing staff? |
| --- | --- |
|  | If YES – Name and Current Position of the staff | If NO – Actions needed to identify and recruit |
| Program Leader | Fachrurrazi |  |
| Project Manager | - | (HR) We need to have and update list of CVs of the potential project managers from existing projects or new candidates to ensure in time mobilization |
| El Nino monitor staff (not a full time task ( check on websites, etc) | Ema Yunida |  |
| Pusat Informasi Lingkungan | Faturrachman |  |
| Food security early warning center | Tonny Bengu |  |
| Consultant/ in house staff to do contingency plan with the government | Damayanti Soekarjo Johan Kieft IRI |  |
| Local Governments Liason officer | Apekoniti Ludoficus Korbaffo |  |
| Health and Nutrition specialist | Damayanti Soekarjo (Nutrition) Kusuma Hartani (Health) Caecilia (IYCF-E) |  |
| Market-based relief specialist | Wilfridus Nahak |  |
| Environmental Health | Fachrurrazi |  |
| Physical infrastructure specialist | Theo Dacosta | Tbd |
| Procurement officer | Hermin Alda |  |
| Administration | Bertha Neny Bertha (CK) |  |
| Logistic | Bambang Oche Taupan |  |

#### Relief Item requirements

| Item description | Unit Measure | Quantity Required | Potential Sourcing (Local Purchase, International Purchase, Available from partner, etc) |
| --- | --- | --- | --- |
| Face mask | 1 mask per person |  | MBR |
| Higyiene kit | 1 per HH |  | MBR |
| Fire extinguisher kit | 2 per village | 200 kit | MBR |
| Blanket food ration (pay attention to fulfilling protein and caloric needs) e.g. of: Canned Sardines Vitamin A&D Enriched oil Eggs Mungbean Rice (Food for Work) | ~ SPHERE standards | 20% of target | Local purchase, available from partners |
| PUR |  | 20% of target | International partner |
| SWS |  | 20% of target | Local partner |
| Village package | 1 per village based on PRA | NTT: ~ 300 CK : 200 | Grant to communinties |
| RUTF | ~ number of acute malnourished children |  | UNICEF |

#### Logistics/Equipment Requirements

| Items per locations | Quantity Needed | Is this available in the Country Office? |
| --- | --- | --- |
|  |  | If YES – identify project/location/status | If NO – Actions required to identify items |
| Office | 1 for each location | Palangkaraya, Sampit Kupang Atambua, Kefa |  |
| Guesthouse | - |  | Not needed |
| Warehouse | - |  | Not needed |
| Vehicles for staff | Need-based |  |  |
| Transportation of relief items | Depend situation because MBR |  | Depend situation |
| Computers | 1-2 per location | Yes |  |
| Sat Phones | - | Land line and internet connection available |  |

#### Trigger Indicators

| Indicator | Critical Values | Source of information | Location Monitored | Monitoring Frequency | CARE Staff Responsible for monitoring |
| --- | --- | --- | --- | --- | --- |
| SOI (Southern Ocillation Index) | (Negative) | ADPC (IRRI, PIL) | CK and NTT | Weekly | Ema Yunida, Fatrur |
| # Titik api (Luasan area) |  | Fire danger Rating System | CK | daily | Fatur |
| Wasting (W/H) | > 15 % | Posyansdu data | CK and NTT | monthly | Caecil/Dr. Tani/ |
| Underweight (W/A) | > 40 % | Posyansdu data | CK and NTT | monthly | Dr. Tani |
| Food Stock | < 1 Bulan | BKP | CK and NTT | montlhly | Tonny |

#### Key issues/challenges affecting CARE response

| Dimension | Challenge / Consideration (if ANY) | Recommendation |
| --- | --- | --- |
| Language | Bahasa (bermasalah) | Hire Staff Lokal & Kerjasama dengan GOI atau stakeholder |
| Culture | Ada | Pendekatan adat |
| Ethnic tensions |  |  |
| Sectarian violence |  |  |
| Security | Ada | Security plan based on location |
| Local Government |  | Koordinasi |
| Economy |  |  |
| Infrastructure | Transportation | Memaksimalkan potensi vendor lokal |
| Local Organisations |  | Partnership |
| International Organisations |  | Koordinasi |
| Regional implications |  |  |
| NGO |  | Partnership |

#### Entry and Exit/Transition Strategy

Strategy untuk masuk :

- Jika indicator SOI dan titik api melewati batas ambang, maka segera lakukan koordinasi dengan Pemerintah. Juga langsung mencek data posyandu dan food security.   Jika Pemerintah menyatakan bahwa dana /kemampuan pemerintah tidak memadai dalam hal penanganannya, maka kita nyatakan emergency untuk wilayah ini. Dan bersama pemerintah kita membuat perencaanaan penaggulangannya (Contingency Planing).

- Action activity

Exit/Transition strategy :

- Handover (asset, data, dokumen,  system data base, teknik approach, etc) dan perlu dipastikan keberlanjutannya

- Merencanakan bersama untuk project recovery (untuk donor yang berminat)

#### Funding requirements-summary budget

To be completed

| No. | Item description | Unit Measure | No of Units | Unit Cost (US$) | Total Cost (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | STAFF SALARIES & BENEFITS |  |  |  |  |
| 2 | TRAVEL & LODGING |  |  |  |  |
| 3 | RELIEF ITEMS |  |  |  |  |
| 4 | HANDLIN/TRANSPORTATION |  |  |  |  |
| 5 | OPERATING/SUPPORT COSTS |  |  |  |  |
| 6 | SHARED COSTS |  |  |  |  |
| 7 | ICR |  |  |  |  |
| 8 | TOTAL FUNDING REQUIREMENTS |  |  |  |  |

Number of Beneficiaries:

Cost per Beneficiary:

## Scenario 4 – Floods in Sulawesi

### Scenario Description

| What is the disaster that occurring | Flood |
| --- | --- |
| Why is this disaster occurring? | Peak of rainy season (Nov-Mar) and the deforestation and erosion |
| Where is it happening? | Central Sulawesi, South Sulawesi, and Gorontalo |
| When is it happening and for how long ? | Between November and March for 3 months |
| How are people being affected ? | damage of livelihood, communication, watsan, electricity, transportation and infrastructure. The 90% livestock will be gone, poverty increased, unable to buy basic necessity, waterborne diseases, need medicines, inflation of prices |
| Estimated number of affected people | 1.500.000 people, which based on formula introduced by WHO, will be; 75% displaced = 1,125,000 0.5% death = 7,500 4% injuries = 60,000 |
| Estimated number of children and women affected | Women -> 59% of total affected (about 885,000 person) Children -> 31% of total affected (about 465,000 children) (based on proportion of women and children in the family of those 3 province) |
| How vulnerable are the community | Vulnerable to Water, Sanitation, Food and Shelter |
| What are the coping strategies and capacities of men and women? | Migration to city either going to forest to “pembalakan liar” or hunting the protected animals. The Gov just provide the rice. |
| How is the disaster going to affect livelihoods of the affected people? | The 90% livestock will be gone, poverty increased, unable to buy basic necessity, waterborne diseases, need medicines, inflation of prices |

### Impact Analysis and Identification of Risk Reduction Measures

| Impact on social, Economy, Infrastructure, and Environment | Mitigation | Preparedness | Response | Recovery |
| --- | --- | --- | --- | --- |
| Loss of human life | EWS Drill Supportive government regulation | Develop safe building Village planning | Evacuation Food, water and sanitation, and family kit supply | Counselling |
| Increased poverty in general | Skill training Entrepreneurship Campaign of saving money in bank | Capacity building | Village Saving Loan (Kelompok simpan-pinjam desa) |  |
| Health status of population | Health campaign | Health stock Medical resources | Distribute Health kit/medicine |  |
| Disease outbreak | Hand washing, drainage system, campaign | Mobile hospital | Isolation, treatment, | Watsan rehab, well cleaning |
| Water supplies | Memperbaiki sumber air, |  | SWS, PUR |  |
| Disease outbreak | Health environment , Hand washing campaign, watsan rehabilitation (Well cleaning, Latrine rebuilding, Sewage system) | DAP, SWASH, ACT | 31 Sept 08, Dec 09 | Frank Page, Abdulnasser |
| Water Supply | Safe water system: To elevate the well ring Stock filing of jerry cans | DAP, SWASH, possible project with UNICEF | 31 Sept 08 | Frank Page; Abdulnasser |
| Environment degradation | Reforestation, biodiversity campaign, strengthening of customary laws | BASIC, CCC (Gorontalo, Sultra) | Possible 2009 | Johan Kieft |

### CARE Prevention and Mitigation Measures

Activities that CARE can focus on or implement in its current or upcoming projects.

TO BE COMPLETED

### CARE Response Strategy

#### Goal and objectives of CARE response

GOAL

“Provide immediate basic needs of affected people and saving lives for families with lactating-pregnant mothers and children under five”.

Objectives:

- Provide Food and NFI

- Water, Sanitation and Hygiene

- Temporary shelter

- Access to basic health services

#### Geographic Focus and Target Beneficiaries

| Geographic Area | Total # of beneficiaries | CARE target beneficiaries |
| --- | --- | --- |
| Central Sulawesi | 100.000 IDPs | Family with children under 5, lactating & pregnant women |
| South Sulawesi | 300.000 IDPs |  |
| Gorontalo | 100.000 IDPs |  |

#### Response Interventions

Response Intervention:

- Temporary shelter ( tarpaulins

- Water & hygiene ( water container, water purifications plus hygiene kits

- Sanitations ( temporary latrine & sewage management

- Food item ( rice, cooking oil, green peas

- Monitoring nutritional and water-borne diseases

#### Implementation Phases/Timeline

Implementation phases/timeline (first 3 months after disaster occurred)

- National and local coordination (Nat’l/ local GoI, UN, other I/NGO, other local stakeholder) – 24hr

- Rapid need assessment (RNA-joint with UN or ECB team); to get overview IDP’s basic need – 48hr

- Joint daily coordination meeting with Bakornas/Satkorlak ( to reduce an overlapping & update situation – 2/day

- To identify accessibility to affected area and potential resources – 48hr

- Verification of IDP’s data/information, and their basic needs – 72hr

- Phase distribution & technical assistance – 3rd/4th  day

- Monitoring - weekly

- Reporting - daily

#### Partnership Arrangements

| Organizations | Typical Role in Emergency | Existing relationship w/CARE | Expected/required relationship w/CARE | Action to improve relationship |
| --- | --- | --- | --- | --- |
| Local GOI in CS, SS, Gorontalo (pemprov, satkorlak, satlak, kecamatan, kelurahan/desa) | Coordination, permission, local support, | Yes | Recommendation for humanitarian assistance; up date situation; |  |
| tbd | Join Assessment, distribution, | Yes, training capacity | Implementing agencies: general agreement, capacity building, | Strengthening local partnership: SPHERE; administration, logistic & financial management |

#### Key personnel requirements

To implement the emergency response strategy the following key personnel are immediately needed:

| Position | Can the position be filled with the existing staff |
| --- | --- |
|  | If YES – Name & Current Position of the staff | If NO – Actions needed to identify and recruit |
| Project Manager/GOI liaison | Abdul Nasser (SS) / Jhoni Thomas (Gor/CS) |  |
| Project Officer | Haidir (SS) / |  |
| Watsan Specialist | Yayan (SS) / |  |
| Logistic-warehouse officer | Bambang Setiabudhi (Jkt) |  |
| Procurement-admin officer | Helviani Pasang (SS)/ |  |
| Finance officer | Amrin |  |
| Program Leader | Fachrurrazi (Jakarta) |  |
| Program Officer | Ema (Jakarta) |  |
| Media officer | Wiwik (Jakarta) |  |
| HR | Nila (Jakarta) |  |

#### Relief Item requirements

| Item description | Unit measure | Quantity Required | Potential Sourcing (Local purchase, international purchase, available from partner, etc) |
| --- | --- | --- | --- |
| PUR (water purifier) | Sachet (1 sachet for 10 liters). One person is equal to 10 liters/day. The needs is 30 sachets/person/ month | CS ( 9.000.000 for 3 months Gorontalo ( 9.000.000 for 3 months SS( 27.000.000 for 3 months | John Hopkins – vendor (Jakarta) |
| Jerry Cans | 20 liters/jerry can | CS ( 20.000 Gorontalo ( 20.000 SS( 60.000 | Local vendor in CS, SS & Gorontalo |
| tarpaulin | 1 tarp for 1 hh (5-6 person) | CS ( 20.000 Gorontalo ( 20.000 SS( 60.000 | Local vendor in CS, SS & Gorontalo |
| Hygiene Kits (body soap, tooth brush adult/kid & paste, towels, feminine pad, mosquito repellent, shampoo, garbage bag, hand soap, detergent) | 1 package for 1 hh/month | CS ( 60.000/3 moths Gorontalo ( 60.000/3 months SS( 180.000/3 months | Local vendor in CS, SS & Gorontalo |
| Food items (rice) | Rice 400gr/person/day | CS ( 36 thousand ton Gorontalo ( 36 thousand ton SS( 108 thousand ton |  |
| cooking oil | Cooking oil 4 liter/month/hh | CS ( 60.000 Gorontalo ( 60.000 SS( 180.000 |  |

#### Logistics/Equipment Requirements

| Items per locations | Quantity Needed | Is this available in the CO? |
| --- | --- | --- |
|  |  | If YES - identify project/location/status | If no – Actions required to identify |
| Office | 3 cum warehouse | YES |  |
| Guesthouse |  | YES |  |
| Warehouse | 3 | YES |  |
| Vehicle for staff | 3 (depending on area) | YES |  |
| Transportation of relief items | 30 trucks |  | N/A |
| Computers | 6 | YES |  |
| Sat Phones | 6 | YES |  |
| Radios | Thanks to HP | YES |  |

#### Trigger Indicators

| Indicator | Critical Values | Source of Information | Location Monitored | Monitoring Frequency | CARE staff responsible for monitoring |
| --- | --- | --- | --- | --- | --- |
| Gov Alert | Rain volume Water speed | BMG | Water gate | Daily (normal) Hours (emergency) | Fachrurrazi, Ema, PM/PO |
| Mortality rate | deaths | Bakornas, Satkorlak |  | Daily (normal) Hours (emergency) | PM, PO |
| IDPs | 50 % of vulnerable people in each province | Bakornas, Satkorlak | Official IDPs shelters | Daily (normal) Hours (emergency) | PM, PO |

#### Key issues/challenges affecting CARE response

| Dimensions | Challenge / Consideration (if ANY) | Recommendation |
| --- | --- | --- |
| Language | Consideration | Strengthening local organization capacity and work close with community |
| Culture | Consideration | Strengthening local organization capacity and work close with community |
| Ethnic tensions | Challenge | Strengthening local organization capacity and work close with community |
| Sectarian violence | Challenge |  |
| Security | Challenge |  |
| Local Government | Consideration | Joint coordination and capacity building |
| Economy | Consideration |  |
| Infrastructure | Challenge |  |
| Local Organizations | Consideration | Joint coordination |
| International Organizations | Consideration | Joint coordination |
| Regional implication | Consideration |  |
| NGO | Consideration | Joint coordination |
| Other | Challenge |  |

#### Entry and Exit/Transition Strategy

To be completed

#### Funding requirements-summary budget

To be completed

| No. | Item description | Unit Measure | No of Units | Unit Cost (US$) | Total Cost (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | STAFF SALARIES & BENEFITS |  |  |  |  |
| 2 | TRAVEL & LODGING |  |  |  |  |
| 3 | RELIEF ITEMS |  |  |  |  |
| 4 | HANDLIN/TRANSPORTATION |  |  |  |  |
| 5 | OPERATING/SUPPORT COSTS |  |  |  |  |
| 6 | SHARED COSTS |  |  |  |  |
| 7 | ICR |  |  |  |  |
| 8 | TOTAL FUNDING REQUIREMENTS |  |  |  |  |

Number of Beneficiaries:

Cost per Beneficiary:

# Management Considerations and Gap Analysis

## Key Personnel Requirements

Need to Complete- this basically is the summary of personnel requirements from all scenarios, and from the operational unit analysis below

| Position required | Currently Available? YES / NO, number | If currently Available, Name (remove position) | If not available, action during the preparedness phase (prepare TOR, pre-select, etc) |
| --- | --- | --- | --- |
| A | B | C | D=B-C |
| Finance Manager | Y. 2 people | Haryanto Ginting, Guntur |  |
| Administration/Office Manager | Y. 2 people | Eko, Nunung |  |
| Security Manager | N |  | TOR prepared. |

Need to ensure portfolio of projects in Indonesia to ensure constant availability of these staff.

## Assessment and Analysis

Goal and objectives during emergency:

- Assessments provide an understanding of the disaster situation and a clear analysis of threats to life, dignity, health and livelihoods to determine in consultation with the relevant authorities, whether an external response is required, and if so, the nature of the response

- Provides immediate assessment of a rapid on-set emergency as well as continual review and updating for slow on-set

- Ensures capacity in reviewing scenarios and on-set of emergencies.

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| B | C | D=B-C |
| Assessment format is available (Clear Objectives Team Logistical support Information Requirements Assessment tools Data Collection Methods Informants Analysis Frameworks Recommendations Reporting | Yes | Update the “Assessment Format” A brief guidelines/protocols on assessment. Database Matrix Partners capacity building on Assessment Determine clear roles of Field Offices for Assessment. |
| Assessment team/staff have been identified and assessment training conducted | Yes | Refreshers Training |

Additional Personnel Requirements:

…………………………………………………………………………………………

Equipment, Supplies and Resources Requirements:

- Logistics map for the affected area(s)

- Basic information about the affected areas (pre collected)

- GPS

- Camera

- Satellite Phone

- Personal Emergency Tool Kit ( rain coat, torch, first aid, etc.}

- Mini Satellite (for data Transfer)

- Lap top

- Cash money

Coordination and Partnership Considerations: BAKOSORTANAL, SAKORLAK, BMG

## Design, Monitoring and Evaluation

Goal and objectives during emergency:

- Provides the strategy and direction for developing programming for mitigation, preparedness, and response activities including the ability for CARE to analyze and assess the impact these programs have in reducing risk

- Provides information for CARE management to make decisions and ensure the quality of emergency programs

- Ensures CARE’s accountability throughout emergency response

Required capacity and level of preparedness:

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Full time M&E on the CO level | Not available | Develop M & E system (vision/concept, tools, technical) |
| Monitoring system and formats developed using and addressing Sphere Standards, Participation, Gender, and Vulnerable groups. | Not available | Develop M & E protocol/SOP; Develop M & E data Centre; networking and coordination with secondary data resources. |
| DM&E standards linked with existing projects, integrating emergency and development into single DM&E procedure | Not available | Need to be integrated all of tools, data, document, reporting, lesson learned from all CARE project |
| Early Warning Systems, both formal and informal, are included in DM&E | Not available | Integrated all Early Warning System tools from all project to be one standard system |
| The CO is aware and capable of conducting the After Action Review required by CARE | Not available | Collecting and develop all of evaluation review from all CARE projects by internal and external resources |

Additional Personnel Requirements:

Need full time staff and unit or including the M&E function on existing unit

Equipment, Supplies and Resources Requirements:

Standardized M&E system

Coordination and Partnership Considerations

Program Managers from all project should be ensured that all of data and document submitted to M&E unit in CO (when if it is available and establish???)

## Human Resource Unit

Goal and objectives during emergency:

Ensure appropriate policy, procedures and systems are in place to support an emergency response, including any necessary adjustments to existing policy and procedures. Identify and deploy experienced staff through internal deployment, external recruitment, and standby arrangements with partners.  Ensure that CARE ongoing programs continued with minimum disruption during emergency.  Recruitment shall be undertaken in a manner of fairness and respecting CARE Core Values, without any discrimination.  HR plays a role in the organization structure planning and other strategic decision making for emergency planning and responses (safe staff arrivals, orientation and staff support).

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Emergency Response Team Identified | Team member has been define during the EPP workshop but not formally assigned yet. | Database of ERT internal or external, contact, skill, area, coordination line |
| Job Descriptions of ERT members updated to include additional roles in emergencies | Not available | Will work on it soon, HR will coordinate with Johan and Adjie for detail job responsibilities. |
| Staff Back-up in place | Team member has been define during the EPP workshop but not formally assigned yet. | Define back up role |
| Emergency Hiring Procedures updated | Not available | We will work on it. Simplify the process of hiring staff. |
| Databases of existing, former, and potential staff updated | Not available | We will get information from Johan and will use HRIS system to maintain the roster. |
| Stress Management Plan in place – to ensure provision of ongoing or emergency stress management support | Not available | SMT needs to consider such activity for the future |
| Staff Emergency Record updated | We believe what we have is enough but we need to look at Standard SER | Will coordinate with ER team leader to gather complete data and maintain the record |
| Antiterrorism requirements (OFAC) followed | Not available | We are looking at implementing the antiterrorism requirement. This activities has been included in current AOP of Administration Unit |
| Orientation for all new staff provided, and Orientation Package (preferably both in hard copy and electronic format) updated to include the recent information | Not available | We need to work on it |
| Ensure appropriate conditions, benefits and support are provided to all staff, including, R&R provisions, Insurance, Health and psychosocial support, Living conditions and provisions | We ensure that all benefit and support are provided to the staff but some of this are not formally documented especially for staff in emergency response mission | We need to work on it. Documented all in Emergency Response HR procedure. |
| Have up to date personnel contracts and files and ensure contract closure occurs for short term staff | HR is currently working on updating the database for all staff. Yes, contract closure does occur for short term staff. | Optimize HRIS system to maintain this specific information. |

Additional Personnel Requirements:

…………………………………………………………………………………………

Equipment, Supplies and Resources Requirements:

Fully used the HRIS as a tool to keep track of all staff information and maintaining a staff roster where we could contact previous staff for current emergency.

Coordination and Partnership Considerations

Coordination with other NGO HR, sourcing the candidates, networking, information sharing.

## Finance

Goal and Objectives:

- Ensure the establishment of an efficient financial management structure for effective implementation of the program.

- Coordinate cash, cash flows, and donor reporting for all projects and program support

- Use effective procedures for the design and management of budgets

- Ensure effective cash flow and management in field

- Cope with increase in donors, funds and transactions

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Finance Manual is updated and includes emergency situations | - | Consult with CCAN to add one chapter on emergency or adopt from CUSA/CEG |
| Authorization levels of approval of expenditure for emergency situation | - | Develop one based on CUSA or other CO |
| Increased level of signatory authorities for the key field staff | - | Develop one based on CUSA or other CO |
| Revise the existing cash flow procedures to reduce time required to approve and process payments, without compromising on accountability, transparency and integrity | - | Develop one based on CUSA or other CO |
| Effective cash management procedures established– making sure that sufficient cash is always available in the bank account | - | Set up minimum balance in the bank account and establish safe cash in Jakarta and in field office if the access to the bank is limited |
| Expedited preparation and submission of financial reports | - | Formalized policy of daily expenditure tracking system |
| Potential staff to work in emergency finance management identified | - | Will be identified |
| Emergency field office cash flow controls and cash handling for insecure situation are in place | - | Develop one Emergency Financial Guidelines and Tool Kits |
| Provide daily cash management updates and cash positions, updates on budgets and expenditures, and funding matrix/portfolio | Funding matrix and budget already updated periodically | For cash management, it will be included in emergency financial guidelines. Keep updating the funding matrix possibly weekly. Expenditure update is done through daily tracking system |
| CO has understanding of donor requirements for emergency contexts | - | Develop do and don’ts for each donor and include it in the emergency financial guideline and tool kits |
| Ensure proper coordination with the program and emergency units | Done. Emergency team leader usually call a coordination meeting and Finance is one of the participant |  |

Additional Personnel Requirements:

Possibly one finance officer to be assigned in the field office depending on the scale of emergency and how CARE operates.

…………………………………………………………………………………………

Equipment, Supplies and Resources Requirements:

Computer, access to internet, SCALA, safe deposit box, office supplies, cellular phone

…………………………………………………………………………………………

Coordination and Partnership Considerations

Local partners and Sub-grantee

## Administration

Goal and Objectives:

- Ensure establishment of an efficient administrative management structure that provides timely support for effective implementation of the program.

- Effective administrative procedures used at national and field levels

- All assets and inventory requirements are effectively managed

- Effective fleet management to meet emergency needs

- Administrative support provided to staff and visitors for travel, accommodations, supplies and provisions

- Compliance with all Government requirements and permits

- Offices, houses, warehouses and other buildings rented, equipped and maintained

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Current and appropriate procedures which permit a rapid and effective response | No Standardisations | Based on lesson learned Need to develop new Admin Manual which Include Emergency procedures |
| Filing system in place | Yes, all doc related to emergency are being placed separately |  |
| Clarity of roles and responsibilities of Admin Staff, including clear Job Descriptions | Yes, each position has a detail JD |  |
| Fleet management system in place | Yes, based on current vehicle manual and previous experience/best practice |  |
| Government requirements and systems well understood | Not complete | Working together with GOI unit Need to provide written information about GOI’s rules |
| Rental agreements available | Yes, using our current standard |  |
| Offices have back up systems in place (power, water, etc) | Yes, depend on the scale intervention |  |
| Communication equipment is available and functional (hand-held radios, mobile and land-line phones, etc) | Yes, we have Mobile Ph, Radio, Sat Phone, etc standby and ready to use |  |
| All import, shipping, customs clearance, travel and other authorizations are obtained and in place | Yes, working together with Log, Proc, GOI unit |  |
| Back-up plan for vehicles, equipment, and assets in place | Yes, by rental or using the available CII asset or borrow from others partners |  |

Additional Personnel Requirements: YES, for running daily support activities

Equipment, Supplies and Resources Requirements: YES, Computer, Comm Equipment, Stationary n Office Equipment

Coordination and Partnership Considerations: YES, with Local NGO n Local Government

## Procurement

Goal and Objectives:

- Timely procurement of goods and services for effective implementation of the program in adherence to donor requirements and CARE policies.

- Ability to procure internationally.

- Required supplies, specifications and sources quickly identified.

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Procurement policy for emergency situation in place | YES ( Emergency Justification sign by Country Director ) we have standard MBR |  |
| Knowledge of international procurement and import requirements | Not completed | We need to update procurement manual to include such requirement |
| Knowledge of major donor procurement guidelines/ changes in emergency situation | Not completed (only can access from donor website ) | Donor regulation training only can access through donor website procurement manual needs be updated to include the basic donor requirement relating to procurement e.g ECHO, CIDA, USDA, etc. |
| Knowledge of the latest customs clearance regulations for import and export | Not completed ( only for import, we never conduct activity for export ) | Training for import regulation |
| Knowledge of prohibited items | No | The procurement should be updated for the prohibited items as well |
| Supplies likely to be required in emergency scenarios documented and suppliers identified | Yes ( base on location of intervention area ) |  |
| List of providers and preferred vendors exists and is updated to include vendors of emergency supplies | Yes | Yellow pages Website Supply from Head Quarter or other sub offices near from disaster area |
| Regular reporting system exists | Yes ( Procurement status report on weekly ) and daily for emergency procurement | However base on the last CARE USA audit it was recommended that we updated and improved of PSR |
| Contract agreement from each donor | No | copy and confirmation about donor agreement Meet donor requirement of items line purchase (update report from donor reporting or finance) |

Additional Personnel Requirements:

Yes, Procurement assistant

Equipment, Supplies and Resources Requirements:

HP, Computer, Internet Connection (Broad band internet), completed yellow pages form every area in Indonesia, Database of potential vendor list

Coordination and Partnership Considerations

Coordination of vendor list for specific items ( WFP, Jhon Hopkins, etc )

## Program Logistics

Goal and Objectives:

- Transportation, warehousing, dispatch and distribution of supplies and commodities to the program areas in a timely manner in adherence to donor requirements and CARE policies.

- Maintenance of controls and inventory system.

- Coordination with other authorities and stakeholder to ensure effective logistics

THIS SECTION NEEDS TO BE REWORKED: basically here we need to identify what are logistical needs based on the scenarios, and what are the gaps related to the needs.

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Appropriate plans for storing, transporting and distribution of relief items in place | N/A | Obtaining information from program on the plan of distribution, type and amount of stuff. Received the information from procurement on the receiving / schedule of items from vendors. Obtained the sufficient condition of warehouse and proper transportation obtained by coordination with procurement. In case of no warehouse needed due to the direct distribution or market based, we have to ensure that all the logistics SOP / administration is in place. The distribution plan prior to the distribution has been prepared. Proper logistics administration for receiving (GRN) and for dispatch (Waybills). Ensure that the beneficiaries is received the stuff proofed by the distribution list. Management on the reporting system, collecting the file and decide to submit it to CARE HQ Manual for logistic SOP summarized from CARE Manual |
| Contracts/MOU with key service providers are developed and ready to be activated (e.g. with private contractors, government, UN and other agencies) | Available | Contracts with services provider (i.e. transporter) have been prepared by the procurement. MOU with other parties related to this activity IS AVAILABLE |
| Reliable transportation service providers identified |  | Fleet of transportation are available |
| Appropriate warehousing management procedures in place |  | Logistics administration for warehousing is available |
| Inventory management and control system in place |  | Logistics administration for receiving and distribution available |
| Staff trained in management of program logistics |  | Staffs for logistics have been trained prior to the project implementation |
| Good contacts with authorities and other agencies on logistics matters |  | The contacts have been established to ensure that the receiving, storage and distribution are properly done. |
| Security procedures in place |  | Preparation for distribution based on the Distribution Plan to ensure that distribution will be implemented properly. Security / guards are available during the storage and delivery of the stuff from warehouse. |

Additional Personnel Requirements:

Storekeeper to maintain the storage and delivery including the logistics administration

Special staff for logistics is deemed necessary because they will focused on the works. (tapi masalah FC)

Equipment, Supplies and Resources Requirements:

Equipment for storage (pallets, tarps, spare bags, weighing scale, etc.), office supplies for warehouse (desk, chair, filing system, PC, etc). Need to develop new form of waybill for the materials distribution as the previous one is designed for commodity.

Coordination and Partnership Considerations

Coordination internal unit (procurement) and external

## Information Technology and Telecommunications

I remember we completed this during the workshop, but I don’t have it in my computer. The group that worked on this must have it.

## Safety and Security

I remember we completed this during the workshop, but I don’t have it in my computer. Abdulmalik and the group that worked on this must have it.

## Fundraising

Goal and Objectives:

- To ensure that adequate financial resources are available for the mitigation, preparedness and response measures.

- Situation Awareness, Donor and Sector Awareness, and Proposal Development.

- Public Fundraising activities- press, appeals, stories and photos

- Provide information, stories and photos for fundraising purposes

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Have relevant formats and guidelines for emergency funds easily accessible | Y | Put on CD – put on intranet in one file |
| Have contact details for donors and CARE members updated | Y | Put on intranet in one file |
| Maintain good relationships with CARE members, donors and UN agencies | Y. USAID, AusAID, ECHO, OCHA, CIDA, WFP, UNDP, DGIS, CAREs Canada, USA, Aust., Austria, Deutsch, Ned, Norge, Japan | Maintain relationships, and work on improving relationship with CARE UK, UNICEF and WHO |
| Ensure awareness of different types of funds and donors available and how to access them, such as: CARE emergency response funds Bilateral Multilateral and UN Private foundations Public appeals | Y | N/A |
| Access to or capacity to write human interest stories and take photos | N | Conduct capacity building of M&E staff to create human interest stories |
| Identify person responsible for donor liaison | Johan, Heather, Adjie | N/A |
| Concept notes for each scenario prepared | Yes | Johan |
| Basic budgets for each concept notes | NO | Sihol |

Additional Personnel Requirements:

Proposal writers contactable within Indonesia are available.  Will create list of these people and put on intranet.

Equipment, Supplies and Resources Requirements:

OK within CO.

Coordination and Partnership Considerations

ECB, local partners, GoI.  Need to create agreements with these bodies for coordination in emergency responses.

## Media

Goal and Objectives:

- External Liaison and Communications in a professional manner: with international and local journalists, filmmakers, and photographers

- Raise awareness internationally and promote fundraising

| Minimum level of preparedness | Current situation in the CO | Action to address gaps |
| --- | --- | --- |
| Focal points identified | Yes. Focal point based on priority: ER Team Leader. Comms Specialist If not required to be on the ground: CD ACDs | Develop SOP for media included in the emergency SOP. Formalise and circulate Memo on list of authorized spoke persons for the CO to all staff. |
| Key messages developed | Not always, only if we respond to the emergency. If not, we don’t go proactive | Develop common key messages for various scenarios. i.e: if we aware but not responding, aware and responding (send assessment team). |
| Focal points trained in media relations, media monitoring and evaluation | Yes but only to talk to media. Media monitoring and evaluation is still done by Comms specialist | Developed guidelines on how to deal with media is made available and accessible to focal points. Identify and train other personnel to monitor the media in HQ. |
| Staff are trained on how to deal with media | Only authorized spokes persons. | Train Assessment and ERT members on how to deal with media if being approached |
| Documentations on CARE activities and programs developed and available (reports, stories, photos, etc) | Photos are the most basic one. Story only avail if comms person is avail on the ground. | Train Assessment and ER Team on how to take photos that useful and gather basic information for the story Define in the SOP who is in charge of sending photos, stories and reports to HQ if comms person is not avail on ground (to share with COMWG, FCWG) |

Additional personnel requirement:

  - No need to hire new personnel but need to identify personnel that can support communications

Equipment, Supplies, and Resources Requirements:

- Camera

- PDA Phone to allow mobile access of internet

- Satellite phone

- Voice recorder

Coordination and Partnership Considerations:

- COMWG, ACORN

## Information Management

Goal and Objectives:

- Gather and disseminate information on the emergency situation and CARE’s response back to CARE International Member offices for use in emergency response, fundraising and communications activities.

- Ensure appropriate and effective internal information flow to CI, CARE Lead member, and other Country Offices.

- Quality information gathered, processed and disseminated

- Generation of reports and response to requests for information

| Minimum Level of Preparedness | Current situation in the CO | Actions to Address Gaps |
| --- | --- | --- |
| A | B | C=A-B |
| Focal point (a person with superior written communications skills, and three to five years writing experience) for information management is identified | Johan Kieft (Leader) Fachrurrazi (coordinator) Heather van sice Ema & Wiwik (situation+information updates and monitoring) Challenges: travel schedule, communication, overlapping role and responsibilitis | Document the protocols (when who do what) and guidelines ( refer to CII EPP |
| Internal reporting/information sharing mechanism established | CI has Alert, Sitrep, ERF CII ER SOP present at headquarter but can not be fully utilized and EPP is under development CII working area ( need support from field office Non-CARE working area --> ? (refer to ER SOP) | Utilize EPP as soon as it is completed Conduct periodic review of EPP and adjust accordingly |
| Identify central location of data and information | CII-HQ management GoI (Satkorlak, Bakornas, MoH through Regional crisis center; MoSocial, BMG) UN agencies, iNGOs, local NGOs Local GoIs ( sometimes have different data and information compared to others. Media (national, local) | Better coordination with Bappenas |
| Focal point and other staff trained and familiar with formats of Situation reports, Alerts, Assessment Reports, and other formats. | Ema (learning by doing; on the job training; needs support from other focal points and field office) Johan Kieft Wiwik Fachrurrazi Heather van sice | CII need to hold staff capacity building (mechanism and reports formats, etc) in EPP. |

Additional Personnel Requirements:

      - Point person in each field office for updated information

      - Support staff in HQ to be involved in information management

Equipment, Supplies and Resources Requirements:

No specific additional equipment necessary as long as communication is sufficitent.

Coordination and Partnership Considerations

      - CII GoI unit has to be involved in the coordination with GoI

      - Assessment team to be proactive in reporting and written communication

# Action Plans

| No | Actions Item | Person Responsible | Date of Completion | Budget Requirements |
| --- | --- | --- | --- | --- |
| 1 | Identify gaps in EPP and determine responsible people | David/Johan | 10/3/08 | None |
| 2 | Collecting missing information from workshop results for draft EPP | Johan/Heather/Adjie | 14/3/08 | None |
| 3 | AAR of Java floods | Johan | 20/3/08 | None |
| 4 | Finalise draft EPP | Johan/Adjie | 31/03/08 | None |
| 5 | Circulate draft EPP to participants and presenting/sharing to partners | Ema | 1/04/08 | None |
| 6 | Create power-point presentation to explain EPP in Indo | Adjie | 1/04/08 | None |
| 7 | Finalise EPP | Johan | 30/04/08 | None |
| 8 | Circulate to CARE Members, CEG, GoI, local partners and UN | Tess | 1/05/08 | None |
| 9 | Submit to ERF for socialisation and implementation of finalised EPP | Johan | 1/05/08 | None |
| 10 | Include gaps in EPP plan into AOPs/IOPs for responsible departments/individuals | Tess | May/June 08 | None |
| 11 | Roll-out of EPP identified activities | Adjie | July-Oct 08 | ERF USD15,000 |
| 12 | Conduct monthly meeting of ERT | Johan | Mar-Dec 08 | None |
| 13 | Update SMT on EPP progress | Johan | Mar-Dec 08 | None |
| 14 | Review and update EPP | Johan | Mar 09 | USD 8,000 |